jjj

Joint Programme to: Support the Availability, Accessibility, and Provision of High Quality Sexual and Reproductive Health, Neonatal and Child Services and Nutrition.

programme NARRATIVE progress report

TEMPLATE

REPORT COVER PAGE

| Participating UN Organization(s): UNICEF, WFP,WHO, UNFPA |  | Cluster / Theme/Priority Area: Maternal, Neonatal & Child Health and Nutrition / Theme/Priority Area: Health and Nutrition |
| --- | --- | --- |
| Prepared by: Dr Alicia Carbonell, JP coordinator, WHO Contact information: 00258 21 491991 |  |  |

| Programme No. Title: Support the Availability, Accessibility, and Provision of High Quality, Reproductive Health, Neonatal and Child Health Services and Nutrition. |  | Report Number: 1 |
| --- | --- | --- |

| Reporting Period: 1st January to 31st December 2010 |  | Programme Budget: Total planned: 7,629,340 Total allocated: 3,190,237 Total Unfunded: 4,439,003 |
| --- | --- | --- |

| List Implementing Partners: |  | Programme Coverage/Scope: |
| --- | --- | --- |
| UN Organizations: UNICEF, WFP, WHO, UNFPA Ministry of Health, Provincial Directorate of Health and the districts Other International Organizations National (government, private sector, NGOs & others) |  | Specify in which region and/or national coverage/scope of the programme National level with focus on 66 RED (Reaching Every District ) districts |

| Abbreviations and acronyms: |  | Programme Duration / Closed Programme: |
| --- | --- | --- |
| List the main abbreviations and acronyms that are used in the report. |  | Programem duration 2010-2011. Report on budget revisions and extensions and provide the new dates. Indicate if the programme has been operationally closed during the reporting period. |

# NARRATIVE REPORT FORMAT

# Purpose

The primary purpose of the Joint Programme is to support and ensure  the Availability, Accessibility, and Provision of High Quality, Reproductive Health, Neonatal and Child Health Services and Nutrition by re-enforcing the capacity of the government and civil society in designing, implementating and monitoring comprehensive maternal and child health services, with the objective of reaching every mother and child, and even the hard to reach, with an integrated package of maternal and child survival interventions.

The two outcomes with specific outputs that were defined for this Joint Programme are:

Outcome 1 and its Outputs

Sexual and reproductive health, neonatal and child health and nutrition issues are adequately addressed in health policies, plans and strategies at all levels:

  - Development and /or formal approval of the key strategic documents to support access, quality and use of maternal, neonatal and child health and nutrition supported.

  - Capacity for planning, monitoring and evaluation of maternal and child health programmes at national and sub-national level strengthened.

Outcome 2 and its Outputs

Access to and use of cost effective mother, newborn and child and nutrition interventions increased through integrated health services:

  - Government and community capacity improved for the implementation of integrated MNCH key interventions, including nutrition in RED (Reaching Every District) plus districts

  - Government and community capacity improved to strengthen key nutrition interventions for reducing vulnerability and improving nutritional status of the mothers and children in selected food insecure districts.

- Resources:

Financial Resources:

A total of USD 5,607,937 was made available for the implementation of activities planned in this Joint Programme in 2010, of which USD 2,889, 360 was contributed from the ONE fund with an utilization rate of 79%. Regarding to the agencies resources, 89% of the an amount of USD 2,718,557 committed was utilized. The total Programme delivery rate in 2010 was 84%

Human Resources:

A total of 11 UN staff members are involved in the management and implementation of the Joint Programme funds:

- 2 programme officers from UNFPA working on reproductive and neonatal health areas;

- 5 from UNICEF dealing with Maternal and Child Health and Nutrition;

- 1 from WFP who supports nutrition (basically supplementary feeding); and

- 3 from WHO who support the areas of maternal, neonatal and infant nutrition.

Implementing Partners

The MOH is the main implementing partner through the National Directorate of Public Health, the Provincial Directorates of Health, the districts, the health facilities and the community health workers.

Participating Agencies: WHO (Lead), UNFPA, UNICEF, WFP

- Implementation and Monitoring Arrangements

The implementation mechanisms:

The implementation of this Joint Programme was coordinated by WHO, with the active participation of the other agencies (UNFPA, UNICEF, WFP and WHO). A matrix for regular monitoring was developed by the JP team to assess the progress of the implementation of planned activities. Joint visits were conducted in selected provinces to test and discuss the M&E matrix with provincial programme managers and also to follow up the PoA implementation.

Quarterly meetings of the Joint Programme were conducted for information sharing on the progress of activities carried out by different agencies and to discuss the effectiveness of the JP matrix to reflect the adjustments made to the agency-specific detailed activities.

The MOH was supported by the participating UN agencies for implementation of the activities defined in 2010 for the Joint Programme focusing in the following strategic areas:

Policy and advocacy: Promotion, support and mediation of policy dialogue to ensure the development and/or adoption of the keys strategic documents related to SRH, NCH and nutrition and their dissemination at all levels.

Capacity development: In order to implement the MNCH health intervention packages, focus was placed on training health personnel on Essential MNCH Services, EmOC, Essential Newborn Care, IMCI, Basic Nutritional Package, nutritional rehabilitation and treatment of children in a severe condition, as well as the supplementation of moderate cases. The community health workers were trained in Community IMCI (C-IMCI) and good nutritional practices. To strengthen the planning and M&E capacity, MCH managers were trained in supply and commodities management and programme management. Both are viewed as to ensuring the quality of services provided.

In order to improve the quality of programme management, including the monitoring of programme development, formative supervision visits were supported at the various levels as well as micro-planning of the integrated package for maternal and child health interventions in the 66 RED districts.

MCH and nutrition commodities: To ensure that commodities are available in the right place at the right moment, besides the training of health service providers, this JP includes the purchase of essential commodities (mainly solar panels, communication radios, IEC materials, MCH equipment and Corn Soya Blend (CSB).

Community involvement: The mobilization and participation of the community, particularly for the provision of preventative health services and identification, referral and follow-up of children with acute under-nutrition, is an important component of the approach.

### IV. RESULTS

Progress in relation to the outcomes and outputs expected for the reporting period

Although the activities and achievements are described below, it is important to highlight key achievements and identify where UN agencies have played a strong role:

- Revitalization plan for the community health workers with paid community health worker cadres implementing community case management (CCM) for major child killers has been finalised, and training of 18 APEs per district conducted in 8 districts.

- RED approach and the Child Health Weeks continue to reinforce the capacity of districts to plan and implement routine child survival activities, creating a platform for the integrated delivery of maternal and child survival packages. Over 3 and a half million children are now being reached each year with two doses of vitamin A, representing over 90 per cent of the target population, in comparison with 50 per cent in 2006. Ten times more children compared to an average week in a year are given the chance of being immunized against measles and DPT3 during the Child Health Weeks.

- A rapid evaluation of the RED approach in December 2010 indicated the need for a re-orientation meeting for all provincial directors and teams on the integrated approach and the use of the RED concept as a platform for integrated Mother and Child Survival interventions.

Main activities undertaken and achievements in 2010

Under the outputs related to Outcome 1, most of the planned activities were carried out.

Expected Output 1.1: Development and/or formal approval of key strategic documents to support access, quality and use of maternal, neonatal and child health services and nutrition supported

The UN agencies supported the development of the Multi-Sectoral Action Plan for the Reduction of Chronic Malnutrition 2011-2015. The Plan was developed and approved by the Council of Ministers. Technical support was provided for the drafting of the National Food Fortification Strategy, to consolidate the inputs from the multi-sectoral working group on staple food fortification (government, private sector and development partners). The National Committee for Food Fortification was also created, together with a project for the initiation of food fortification. The agreement between MOH, WFP and UNICEF for the period March 2010 to February 2011 was also renewed, which allows for the expansion of the Supplementary Feeding Programme for children with moderate acute malnutrition in 48 districts in five provinces and 88 districts all provinces.

National health weeks, aimed at promoting and providing key interventions for women of reproductive health age and children under 5, were carried out. The UN Agencies (WHO, UNICEF and UNFPA) provided technical and financial support to all provinces duringthe roll-out of the two National Health Weeks. Vitamin A supplementation, de-worming, and routine immunization interventions were offered to children and Vitamin A and iron & folic acid supplementation was provided for postpartum women and TT vaccination for women. For the first time the National Health Weeks included a strong component of family planning and adolescents and has as a result increased demand by these important targets groups.

Specific results obtained during the National Child Health Weeks for children were as follows:

First Phase:

- 3,787,289 children aged between 6-59 months (106% of the target)  received Vitamin A supplementation;

- 3,205,53 children aged 12-59 months (102% of the target) were de-wormed.

Nine-fold increase in coverage for under-one year old children immunized compared to a weekly average for routine: BCG - 89,552; POLIO 1 - 94,289; POLIO 2 - 83,433; POLIO 3 - 80,567; MEASLES - 118,920. Results of the second phase from 1-7 November 2010 show similar trends.

- 212, 1999 postpartum women were supplemented with Vitamin A;

- Approximately one million women received vaccination against tetanus;

- 320,631 women received iron & folic acid tablets for 30 days;

- Family planning counselling and contraceptives: 126,880 women received pills, 1,755 women received IUDs and 60,228 received injectables; and 917,590 male condoms were distributed.

Second Phase NHW:

- 3,352,132 children aged between 6-59 months (94% of the target)  received  Vitamin A supplementation;

- 2,812,335 children aged between 12-59 months (90% of the target) were de-wormed;

- 3,002,824 children aged between 6-59 months (84% of the target) were assessed for acute malnutrition, of which 0.7% were found to have severe acute malnutrition and were referred for treatment;

- Additional interventions included in the second phase were adolescents iron folic acid and de-worming;

- Sexuality education and the promotion of family planning: 155,751 women received contraceptives (data not yet available by method) and 954,401 male condoms were distributed.

The Human Resource Directorate, in coordination with the national public health directorate, updated the pre-service training curricula. This curriculum was developed as a competency-based approach to allow for a better quality of training. At the same time the in-service training curricula on the MNCH essential packages have been developed and a more comprehensive and integrated approach. This was done in order to maximize resources as well as the time spent on different and vertical training, and as part of key activities to support the operationalization of the INP for MDGs 4 and5.

Relevant guidance documents were developed for improved services and cost-effective MNCH interventions such as the national norms for Antenatal Care, EmOC, Post Partum Care, ENBC, and are currently awaiting approval. The Family Planning Strategy was also finalized and approved and its operational plan developed. For child health, the  Community Health Worker programme (APE) has been revitalized, and should assist in advancing access to health care at community level and will allow for better community case management of malaria, diarrhea and pneumonia for children under five.

A consultancy to collect the existing IEC materials for MNCH programmes was carried out in order to identify the IEC materials available, as well as to update them if necessary, and to reproduce and distribute them to provinces and districts. A compilation of Information, Education and Communications materials on family planning was undertaken, although  materials for some key components are still missing.  The finalization of the package, together with the Community Department, will be a priority for the first quarter of 2011.

Output 1.2: Capacity for planning, monitoring and evaluation of maternal & child health and nutrition programmes at national and sub-national level strengthened.

30 programme managers from central and provincial level were trained on planning and implementation of MNCH programmes in order to strengthen managerial skills and health services provision capacities. There are currently 15 trainers across the country. In addition, Maputo province has conducted one course for district programme managers and selected Joint Programme districts were assisted in planning, implementing and monitoring the integrated MNCH plans.

sThe launch of the National Partnership for Maternal, Newborn and Child Health, that includes relevant sectors and partners, will strengthen the national and sub-national capacity for the implementation of maternal and child health programmes. The policy and strategic orientation for paid Community Health Workers (APEs) implementing CCM was finalised and the implementation of APEs training in five districts (out of eight supported by MOH) was financed.

Several activities under Outcome 2 were also carried out.

Output 2.1: Government and community capacity improved for the implementation of integrated MNCH key interventions, including nutrition in RED Plus districts.

With regard to Essential / Emergency Obstetric Care, training of health workers with a focus on selected JP districts was provided to:

- In-service training of MCH nurses in Emergency Obstetric Care for approximately 350 MCH nurses across the country.

- Provincial training for approximately 480 MCH nurses who were trained in the new data collection instruments (registry books) for SRH / MNCH services. This is an essential activity supported by UNFPA as an important step for improved monitoring of SRH/MNCH programmes.

- Five training courses have taken place in the last quarter in Niassa, Nampula, Zambezia, Tete and Manica provinces. Through this intervention approximately 94 health personnel in all provinces have been trained in general management, supply chain management, and warehouse management for central warehouses containing durable equipment.,

- Through the partnership support for MNCH, with UNFPA (coordinator), UNICEF and WHO working together, approximately 330 new basic MCH nurses were trained at Provincial Training Institutions in 2009/2010. These basic MCH nurses are now in the process of being integrated into the health system.

- Another key activity supported was the development, approval and dissemination of the maternal and newborn audit committee terms of reference and the establishment of the national maternal and newborn audit committee.

With regard to child survival interventions, the RED APPROACH was consolidated in 66 districts. Positive trends were noted in the process indicators, including micro-planning, mobile brigade outreach, supervision, monitoring for action and community linkage, and access indicators, including 58% DTP-HepB-Hib 3 or 146,850 children under 1, and 92% measles coverage or 195,736 children under 1. However, the planned expansion to 33 districts was not achieved due to a lack of funding from MoH and other partners. The training of health workers, with a focus on 66 Red districts in the Integrated Management of Neonatal and Childhood Infections (IMNCI), achieved the following results:

- Support was given to the expansion and strengthening of the IMNCI programme, with training and supervision provided to staff in the implementation of the new protocol, which includes neo-natal care and HIV/AIDS. 90 % of health facilities in target provinces are implementing updated IMNCI as a result of increased capacity (273 new health staff trained in IMNCI in addition to over 800 trained in 2009).

- Support was also provided for training, implementation and monitoring of Community IMNCI (C-IMNCI), with a focus on community follow up of newborns. Community based ACSD was implemented in 66 RED districts. 26 out of 66 focus districts (39%) implement C-IMNCI including home based new born care. Analysis of the first semester data from 18 out of the 26 RED districts implementing home-based new born care in Niassa, Zambezia, Sofala and Nampula, show that a total of 203 trained Community Health Workers visited 9,763 newborns at home i.e. 8% of expected deliveries compared to 3% at the end of 2009. Among them, 3,095 (33% compared to 28% end 2009) were referred to health centers for various reasons.

- To improve the mosquito net coverage, the funds for the JP allowed for the procurement of 19,000 out of 569,093 LLIN. These were procured and distributed and more than 95% of children under 3 years old in unsprayed districts own nets.

Another key activity undertaken was the conducting of 3 Training of Trainer  on Care of Children in severe conditions. Due to the lack of proper anatomical models for training, the provincial training sessions were postponed for 2011.

To better support programme performance and the implementation of the PMNCH / JP, a supervision and monitoring tool was developed by UNICEF, WHO and UNFPA that aims to do the following:

- Assess mother, newborn and child health coverage trends,

- Monitor implementation of activities;

- Assess progress on interventions at community level;

- Assess referral systems;

- Monitor water and electricity conditions; and

- Define actions / interventions to increase coverage and improve quality of care and management in a consistent manner.

After the first round of field visits, the conclusions were:

- The tool is too complex and extensive to be utilised during the visit. This did not allow the team, in collaboration with the province, to analyze trends, or discuss possible causes and propose actions. As a result the tool was simplified so that it could be used to assess progress on the main indicators (as set out in the M&E plan), get the information from the province and then analyze it prior to the visit in order to spend more time analyzing the findings with the province and monitoring activities at provincial and district level.

- The analysis of routine data reflects the existence of weaknesses at provincial level in terms of data collection, information flow, data analysis and reporting.

- Several of the indicators, mainly the neonatal and child indictors, are difficult to gather information for on a regular basis.

Through PMNCH funding, UNFPA has supported regular supervision visits from provincial to district and health facility level in the 12 districts. UNFPA also supported co-management committees in the 12 districts between health facilities and community leaders.

Output 2.2: Government and community capacity improved to strengthen key nutrition interventions, reducing vulnerability and improving the nutritional status of mothers and children in selected food insecure districts.

Under the nutrition programme several activities planned in this Joint Programme were carried out, as well as other relevant activities that complement the efforts put into this JP. As planned, 10,000 children under the age of five suffering from moderate acute malnutrition received CSB+ supplementation. Other key activities include:

- From January to March 2010, the provincial programme managers for nutrition and provincial managers from the pharmaceutical department were trained in the protocol for supplementary feeding, data collection, registration and reporting and CSB handling and stock, as well as warehouse management. The training was conducted in the 11 provinces.

- Health workers in two general hospitals in Maputo City were trained in the Baby Friendly Hospital Initiative (BFHI), and support was provided for social mobilization activities in the context of the World Breastfeeding Week, the theme of which focused on the BFHI.

- Expansion of Outpatient Treatment for Severe Acute Malnutrition with Community Involvement in the provinces of Nampula, Gaza, Zambézia and Sofala, with in depth technical assistance to the MoH at central, provincial, district and health facility level, in collaboration with Save the Children.

- Evaluation of health workers’ knowledge and practices as incorporated in the Basic Nutrition Package. The implementation of this package has been supported for about five years and at least two health workers per health facility have been trained. The evaluation is required to provide information about the impact of the package and possible ways to improve it. It was initiated in December 2010, and the results are expected in the first quarter of 2011.

MCH and nutrition commodities / infrastructure / referral system: For effective health services there is a need to ensure that commodities are available in the right place at the right moment. Besides the training of health service providers, agencies have supported the procurement, purchase and distribution of some of the essential commodities, as well as for the reinforcement of the referral system as follow:

- Anatomical models for IUD insertion (41) were procured in 2010 to improve the quality of family planning training.

- 400 Manual Vacuum Aspirators (MVA) were purchased, with an expected time of arrival in February 2011.

- In 2010, 504,000 microgynon cycles, 1,452,438 microlut cycles, 3,400 IUDs, 75,240,000 male condoms, and 1,500,000 female condoms were received and distributed during regular services and during the Mother and Child Health weeks through UNFPA Global Programme funding. The national health week provided an opportunity to promote the utilization of female condoms, as there is still a lack of knowledge and understanding of female condoms especially in rural communities.

- Procurement and purchasing of communication radios. Following government procurement processes, UNFPA acquired 40 radio-communications, including accessories for their installation and were stored in the Central Warehouse in accordance with standard procedures. The distribution plan for 2010 aimed to cover Niassa, Nampula, Sofala and Zambezia provinces. However, it was only possible to install 26 radios and solar panels  in Niassa and Zambezia provinces. In Niassa, 11 radios were installed in Marrupa, Nungo, Ntembo, Lissiete, Mepapa, Lipuzia, Meluluca, Lussangase, Mississi, and Mandimba. Health facilities in Zambezia, Pebane, Pele Pele, Mulela, Muligode, Impaca, Txalalane, Alto Maganha, Muzu, Alto Mutola, Tapata,Mabala, Carina Mapira benefited from the installation of communication radios. The installation included job training for maintenance.

It was not possible to install the remaining 14 radios due to the “disappearance” of various components in the Warehouse. This serious issue had implications for the procurement of the set of communication radios that were planned to be purchased in 2010 with JP funds. UNFPA took a decision to cancel any further procurement until they received an official letter explaining the disappearance of the radios and other equipment and expressing a commitment by government to purchase the various components needed for the installation of the 14 radios with MoH funds.

- Through JP funds, UNFPA supported the rehabilitation of 2 waiting homes for pregnant women in Mandimba and Marrupa districts, two waiting homes in Nampula (CS Quissimanjulo/Nacala Porto); and one in Iapala (Monapo/Ribaue). In Sofala province funds from the Joint Programme were used for the construction of 5 waiting homes, although these are still under construction.

- Financial support was provided to improve the water and electricity systems in selected district of Maputo and Gaza provinces

Implementation constraints and challenges:

Through this JP, UN Agencies have consolidated efforts in support of the Ministry of Health at different levels, from central to district level, to scale-up Maternal, Neonatal and Child Health interventions including EPI and Nutrition. However, it is important to note that the implementation of the proposed actions and interventions needs more time and also more staff to ensure successful implementation.

The capacity development of the National Directorate of Public Health and programmes such as SSR/maternal health, child health, EPI and nutrition programmes at central level have made positive progress, but further strengthening of provincial and district level capacity should continue .

In general terms, the constraints and challenges are applicable across the different programmatic areas that this Joint Programme is supporting. The key challenges experienced have been:

- Severe shortage of human resources;

- Lack of PMNCH programme management skills, leading to poor data quality and stock outs of essential medicines;

- Low access especially for clinical individual-oriented care and huge urban / rural disparities;

- The country is prone to natural disasters, cholera outbreaks and the HIV/AIDS pandemic;

- There are administrative bottlenecks that are delaying the movement of resources from the MoH to the provinces;

- Weak data quality, including lack of data reporting; and

- Lack of vehicles at district level to transport nutritional supplements to health facilities.

## Opportunities for acceleration

- Community Health Worker Operational Plan and Curriculum Development  with focus on remuneration of community health workers being finalised;

- Revised and extended comprehensive multi-year plan for immunisation 2009- 2013; and

- Approved strategic plan for MDG 4 and 5 for 2009-2015

Key partnerships and inter-agency collaboration impact on results

Implementation is done in synergy with the participating UN organizations, in collaboration with the government and NGOs. This is very useful as technical resources are reinforced through the leveraging of the different existing capacities. Collaboration with NGOs, community activists and community leaders, especially in the implementation of large scale interventions such as the Child Health Weeks, has been very useful in giving support to grassroots social mobilization, and increasing coverage and adherence.

### FUTURE WORK PLAN 2011

- Support the government in the implementation of key interventions defined in the PNI to achieve MDGs 4 and 5 to ensure the continuum of care.

- Support the government in the consolidation of the RED approach in 66 existing districts selected as of 2010 through routine interventions and through national health weeks, as well as assist in facilitating dialogue with the MoH and partners on the use of RED as platform for health system strengthening.

- Given the limited access to health facilities, a key priority for addressing the burden of malaria is to support community-based preventive and curative health services.  Support will be given for the reinforcement of IMNCI and C-IMNCI in focused districts. Support will be provided for the distribution and social mobilization of the effective use of bed nets procured by funds from the Gloabal fund (GFATM).

- Improve the nutritional status of children by improving the Basic Nutrition Package, Micronutrient Supplementation, further strengthening Outpatient Treatment for SAM and MAM with community involvement, and further strengthening the fortification of iodised salt and staple foods.

Estimated Budget Required: Period 2011

| Agency | Total Budget (US$) | Total Allocated (US$) | Total Unfunded (2011 AWP requirement) |
| --- | --- | --- | --- |
|  |  | Agency resources | Balance from 2010 JP |  |
| UNFPA | 1,740,787 | 256,976 | 246,996 | 1,236,815 |
| UNICEF | 3,430,000 | 1,508,700 | 0 | 1,921,300 |
| WFP | 1,900,000 | 700,000 | 0 | 1,200,000 |
| WHO | 1,290,000 | 115,000 | 269,120 | 835,880 |
| Total | 8,360,989 | 3,096,792 | 516,116 | 5,193,995 |

UN Mozambique

Title: Enhance the Quality and Accessibility of Sexual and Reproductive Health Services, Neonatal, Child Health Services and Nutrition. (One UN Joint Programme)

UNDAF Outputs:    2.2.3, 2.2.4, 2.2.5; 2.2.6

UNDAF Pillar Outcomes:

Human Capital:  Increased access to and use of quality basic services and social protection for the most disadvantaged populations, particularly children, youth and women, to reduce their vulnerability by 2011.

Expected UNDAF CP Outcomes:

HC 2.2 Access to and use of quality basic health services increased, especially for the most disadvantaged populations.

Expected UNDAF CP Outputs:

HC: 2.2.1 MDGs 4 and 5 well reflected in the national and provincial plans; 2.2.2 Improved access to SRH services through the implementation of defined interventions packages; 2.2.3 Reinforced implementation of institutional & community IMNCI at all levels, including the neonatal component; HC 2.2.4 At least 95% of 1 year old children are fully immunised through implementation of the RED (Reaching Every District) approach in 99 districts; HC 2.2.5 Malaria treatment and prevention packages (ACTs, IPT, home based treatment, LLINs) implemented in all districts; HC 2.2.6  Capacity of the health sector enhanced for emergency preparedness and response to reduce mortality and morbidity levels in districts affected by natural disasters and high cholera incidence; 2.2.7. Health Information System providing quality disaggregated data on key variables in accordance with international guidelines for the collection of selected indicators of health; 2.2.10 The capacity of the MoH enhanced to improve health promotion, and 2.2.11. Expansion of the treatment of moderate malnutrition to children 6-59 months of age from 22 districts to 72 districts

Implemented by: Ministry of Health (MoH),

Other Partners: MIC, INNOQ, Save the Children, PSI, Malaria Consortium, HKI, other NGOs, USAID,

Agreed by Ministry of Health: __________________________________________

Agreed by (UN Agency): _________________________________________________

UN Mozambique Annual Work Plan

Implementing Partner

FACE authorization specimen:

-------------------------------------

Name and Title: Enhance the Quality and Accessibility of Sexual and Reproductive Health Services, Neonatal, Child Health Services and Nutrition.

| Component 1: |  |
| --- | --- |
| CPAP Output(s): |  |
| EXPECTED RESULTS | KEY ACTIVITIES | TIMEFRAME (2011) | RESPON-SIBLE PARTY | PLANNED BUDGET | Unfunded Amount |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Planned Amount | Amount Allocated | Source of Funds |  |
| Output 1. Development and/or formal approval of the key strategic documents to support access, quality and use of maternal, neonatal and child health services and nutrition supported | 1.1.Key MNCH policy documents approved, reproduced and disseminated, including nutrition component | x | x |  |  | MISAU |  |  |  |  |
|  |  |  |  |  |  | WHO, | 30,000 | 15,000 | WHO -RR | 15,000 |
|  |  |  |  |  |  | UNFPA, UNCEF & WFP |  |  |  |  |
|  | 1.2. Reproduce and disseminate the orientation / advocacy package on MNCH for key stakeholders; IEC materials, media, protocols and norms; |  | x |  |  | MISAU |  |  |  |  |
|  |  |  |  |  |  | WHO | 30,000 | 15,000 | WHO - RR | 15,000 |
|  |  |  |  |  |  | UNFPA | 150,000 | 120,000 | UNFPA OR | 30,000 |
| Output 2 Capacity for planning, monitoring and evaluation of maternal & child health and nutrition programmes at national and sub-national level strengthened. | 2.1. Report on the National Integrated Plan (NIP) for MDG 4 and 5 implementation progress | x | x |  |  | WHO, UNFPA, UNICEF & WFP MISAU | 0 | 0 | 0 | 0 |
|  | 2.2 Translate and adapt the RMR tool and train health managers on the RMR process |  |  |  |  | WHO | 50,000 | 30,000 | OR | 20,000 |
|  | 2.3.Revise and update the NIP for MDG 4 and 5 |  | x |  |  | WHO, UNFPA, UNICEF & WFP | 20,000 | 10,000 | WHO- OR | 10,000 |
|  |  |  |  |  |  | MISAU |  |  |  |  |
|  | 2.4. Train district/ provincial MNCH programme managers on planning, M&E and MNCH programmes | x | x | x | x | WHO MISAU | 80,000 | 40,000 | OR | 40,000 |
|  | 2.5 Conduct an IMCI Health Facility Survey |  |  |  | x | MISAU, WHO | 120,000 | 39,120 | OR | 80,880 |
| Output 3 Government & community capacity improved for the implementation of integrated MNCH and nutrition key interventions including specific nutrition interventions in RED- Plus districts. | 3.1 Support the planning and implementation of 2 rounds of National Health Weeks for mothers and children |  | x |  | x | MISAU, DPSs |  |  |  |  |
|  |  |  |  |  |  | WHO | 200,000 | 55,000 | WHO OR | 145,000 |
|  |  |  |  |  |  | UNFPA | 574,899 | 298,664 | UNFPA- OR | 276,235 |
|  |  |  |  |  |  | UNICEF | 630,000 | 200,000 | UNICEF-OR | 430,000 |
|  | 3.2. Support implementation, monitoring and supportive supervision of IMNCI and C-IMNCI activities at provincial, district & HF levels in RED districts. (provide 66 Neonatal resuscitation kits to 33 maternities ) | X | X | x | X | MOH |  |  |  |  |
|  |  |  |  |  |  | UNICEF | 100,000 | 10,000 | UNICEF RR | 90,000 |
|  |  |  |  |  |  | WHO | 60,000 | 50,000 | WHO-RR | 10,000 |
|  | 3.3. Support training and refresher course for 300 health workers in IMNCI, ENBC and neonatal resuscitation /EmOC in RED districts, corresponding to 50% of PES training plan (at least 150 trained in Emergency Neonatal care/EmOC and 150 trained in IMNCI) | x | X | X | X | MOH UNICEF WHO | 100,000 100,000 | 10,000 50,000 | UNICEF –RR - WHO-OR | 90,000 50,000 |
|  | 3.4 Provide support for logistics, supplies, social mobilization, and resources for implementation of MNCH integrated services at HF and outreach levels in RED districts & districts affected by emergency | X | X | X | X | MOH |  |  |  |  |
|  |  |  |  |  |  | UNICEF | 500,000 | 230, 000 | UNICEF- OR | 270,000 |
|  |  |  |  |  |  | WHO | 500,000 | 80,000 | WHO OR/RR | 420,000 |
|  | 3.5 Support for procurement and distribution of LLINS to pregnant women, and to children under 5 years of age through ANC clinics and universal access campaigns. | X | X | X | X | MOH |  |  |  |  |
|  |  |  |  |  |  | UNICEF | 1,100,000 | 738,700 | UNICEF – OR | 361,300 |
|  | 3.6 Conduct joint review meetings between MoH, community and key partners in selected districts | x | x | x | x | MISAU |  |  |  |  |
|  |  |  |  |  |  | WHO, | 50,000 | 30,000 | WHO- OR | 20,000 |
|  |  |  |  |  |  | UNFPA,UNCEF & WFP |  |  |  |  |
|  | 3.7. Acquisition of 67 communication radios |  |  | x |  | UNFPA | 600,000 | 85,308 | UNFPA - OR | 514,692 |
|  | 3.8. Acquisition of 6 ambulances |  |  | x |  | UNPFA | 80,000 | 0 |  | 80,000 |
|  | 3.9. Support training of HW through the procurement of anatomical models (1624 vacuum delivery; 41 pediatric simulators, 27 neonatal simulators, 1459 IUDs) | x | x |  |  | UFNPA | 279,888 | 0 |  | 279,888 |
|  | 3.10 Procurement & acquisition of 1,800 MVA Kits |  | x | x |  | UNFPA | 124,000 | 0 |  | 124,000 |
|  | 3.10. Rehabilitation of 8 waiting homes |  | x | x |  | UNFPA | 56,000 | 0 |  | 56,000 |
| Output 4 Government and community capacity improved to strengthen key nutrition interventions, reducing vulnerability and improving nutritional status of the mothers and children in selected districts | 4.1. Support the finalization of the Basic Nutrition Package (BNP) evaluation, revision of BNP manuals and training /supervision materials, and initiate support to training of atleast 50 health workers in the revised BNP. |  |  |  |  | MISAU, DPSs |  |  |  |  |
|  |  |  |  |  |  | UNICEF, | 200,000 | 20,000 | UNICEF: OR | 180,000 |
|  |  |  |  |  |  | WHO | 20,000 | 20,000 | WHO OR/RR |  |
|  | 4.2. Support the implementation of the Nutrition Rehabilitation Programme for children under five and pregnant and lactating women (this includes technical support, training HWs on treatment of severe and moderate acute malnutrition, and use of recording, reporting, planning and monitoring tools, reproduction of materials, and supervision) | x | X |  |  | MISAU |  |  |  |  |
|  |  |  |  |  |  | DPS, Save the Children |  |  |  |  |
|  |  |  |  |  |  | WFP | 126,000 | 126,000 | WFP-RR | 0 |
|  |  |  |  |  |  |  |  |  | WFP- USAID |  |
|  |  |  |  |  |  | UNICEF: | 500,000 | 200,000 | UNICEF: RR/OR | 300,000 |
|  |  |  |  |  |  | WHO | 30,000 | 20,000 | WHO: RR | 10,000 |
|  | 4.3. Provide monthly nutritional supplements to approximately 8000 moderately malnourished pregnant and lactating women per month in MCH services | x | X | x | X | MISAU |  |  | WFP: One UN funds, USAID |  |
|  |  |  |  |  |  | WFP | 774,000 | 274,000 |  | 500,000 |
|  | 4.4. Provide nutritional supplements to up to 10.000 moderately malnourished children under five per month in MCH on a monthly basis | x | X | x | X | MISAU/ |  |  | WFP: One UN USAID |  |
|  |  |  |  |  |  | WFP, | 1,000,000 | 300,000 |  | 700,000 |
|  | 4.6 In the context of staple food fortification and salt iodisation: |  |  |  |  | MISAU, |  |  |  |  |
|  | Support standard development; |  |  |  |  | MIC, INNOQ, |  |  |  |  |
|  | Feasibility studies; |  |  |  |  | UNICEF, | 300,000 | 100,000 | UNICEF:RR+OR | 200,000 |
|  | Quality assurance /quality control |  |  |  |  | WFP |  |  |  |  |
|  | National iodine deficiency study. |  |  |  |  | WHO | 20,000 | 10,000 | WHO/OR | 10,000 |
|  |  | UNFPA | 1,740,787 | 863,693 |  | 1,236,815 |
|  |  | UNICEF | 3,430,000 | 1,508,700 |  | 1,921,300 |
|  |  | WFP | 1,900,000 | 700,000 |  | 1,200,000 |
|  |  | WHO | 1,290,000 | 384,1200 |  | 835,888 |
|  |  |  |  |  |  | TOTAL | 8,360,989 | 3,096,792 |  | 5,193,995 |

Repeat the exact same table for other components if applicable

M&E Framework

| AWP Expected Results | Indicators, Baselines and Targets | Means of Verification |
| --- | --- | --- |
| List the expected results as in the AWP above | Against each expected result, include the indicator(s) that will be used to measure achievement and the baseline and target for each indicator | Provide the source of data that will be used to measure the indicator |
| National budgets, policies, sectoral strategies and annual plans (POA) prioritise issues related to maternal, neonatal and child health, and nutrition is adequately addressed at all levels. | Basic Nutrition Package Evaluation finalized Number of selected provinces and its districts with NIP operationalized Baseline: 1/6 (2010); Target: 6 | MOH reports and partner reports DPS and MoH monthly reports |
| At least 80% of health facilities and community outreach services have improved quality of care in the prevention and the management of maternal and neonatal conditions, childhood illness in all districts in eight provinces, and during emergencies. | % of health services implementing IMNCI Baseline: Estimated at 75% (2009); Target: 80% Number of APEs trained and equipped to implement CCM Baseline: 0; Target 580 Percentage of pregnant women who received a LLIN through antenatal care services Baseline: 73% (2010); Target (2011): 80% Number of districts implementing Universal Access to LLIN Baseline(2009): 14; Target (2011): 45 | MOH reports and partner reports |
| At least 85% of children under 1 year of age immunized with pentavalent vaccine and 90% against measles through implementation of the Reach Every District (RED) approach in 66 existing RED districts, and follow up Mass Measles Campaign | % children 0-11Months immunized with DPT Baseline:80%; Target: 85% % of children immunized against measles during the 2011 follow up measles campaign Target: 90% | MOH Reports and partners reports |
| At least 70% of vulnerable children under five receive health facility and/or community-level preventive and curative interventions addressing nutritional deficiencies as required in all targeted districts. | Nº of health workers trained in the Nutrition Rehabilitation Programme Baseline: 0 (2010) - only ToTs for new protocols Target: at least 400. Nº of children with severe acute malnutrition that received outpatient treatment Baseline: 22,322 (2010); Target: at least 30,000 Nº of children with moderate acute malnutrition that received supplementation Baseline: 11,471 (2010); Target: 20,000 Nº of pregnant and lactating women HIV+ receiving nutritional support in HCs with MCH-PMTCT Baseline: 4500; Target 2011: 15,000 Nº of children under five at risk and HIV+ receiving nutritional support in HCs with MCH Baseline: 4500; Target 2011: 15000 Coverage of vitamin A supplementation in each round of the National Health Weeks and via routine services Baseline: 2010: >85%; Target: > 85% | MOH Reports and partners reports |
| At least 85% of health facilities offering SSR/Maternal health interventions package according to the level of service provision in selected districts. | Nº of HF offering the complete essential obstetric care package Baseline: A (2010) Target: (85%) Nº of HF in selected districts offering BEmOC Baseline: 2HF/districts (2010) Target: at least 3HF/districts | MOH Reports and partners reports |
| At least 12 districts with a functional referral system. | Nº of selected districts with functional referral system (at least 1 ambulance and radio communication at district health facility) Baseline: 6 Target: 12 | MOH Reports and partners reports |
| Studies, surveys and evaluation (list below all surveys, evaluation and studies that will be conducted during the year – ensure that each activities are also listed and budgeted for in the AWP above) |
| 1. National iodine deficiency survey | National iodine deficiency survey report available | MOH Reports and partners reports |

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.

This information is not included in the UNDG Standard Progress Report

This information is not included in the UNDG Standard Progress Report

# Text boxes

Joint Programme Narrative Progress Report 2010

Report Formatting Instructions

Kindly review the instructions below and follow them in the preparation of your report

- Do not put the narrative text into boxes and do not incorporate boxes, graphs, etc into the narrative report.

- Add additional information including charts, graphs, etc. as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative.

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point Times New Roman & do not use colours.

Estimated annual budget:   US$ 8, 3360,989

Allocated resources:	 US$ 3,096,792

Government:                       See POA 00

Regular Resource:	 US$ 735,000

Other Resource:                  US$ 2,361,792

Pledged:                              US$

Unfunded budget:               US$ 5,193,995

Programme Period: 2007-2011

Programme: MNCH & Nutrition

Budget Code:

Year: 2011

Narrative

The programme will be implemented by the Ministry of Health and its provincial directorates within the framework of the Health SWAp. It will support interventions to address the underlying causes of the high mortality and poor nutritional status of mothers and children, including inadequate access for the most vulnerable to integrated MNCH and nutritional services and gaps in health policy, institutional capacity and quality of service. The programme will contribute to the progressive attainment of the health related Millennium Development Goal targets through the implementation of cost-effective interventions, focusing on health systems-strengthening and support to service delivery at national and sub-national levels. By 2011, the SSR / maternal and Child Health and Nutrition programme will achieve the following results:

- National budgets, policies, sectoral strategies and annual plans (POA) prioritise issues related to maternal, neonatal and child health and nutrition and are well addressed at all levels.

- At least 85% of health facilities and community outreach services have improved quality of care in the prevention and the management of maternal and neonatal conditions, as well as childhood illness in all districts in eight provinces, and during emergencies.

- At least 95% of children under 1 year of age immunised against pentavalent and 95% against measles through the implementation of the Reach Every District (RED) approach in 99 districts.

- At least 70% of vulnerable children under five receive health facility and / or community-level preventive and curative interventions addressing nutritional deficiencies as required in all targeted districts.

- At least 85% of health facilities offering SSR / Maternal health intervention packages according to the level of service provision in selected districts.

- At least 12 districts with a functional referral system.

To ensure the appropriate level of  support to the national efforts, the JP will focus on strengthening institutional capacity and boosting access to and use of integrated Maternal, Neonatal and Child Health (MNCH) and Nutrition services by (i) promoting, supporting and mediating policy dialogue to ensure the development and/or adoption of the keys strategic documents related to SRH, NCH and nutrition; (ii) supporting the establishment of efficient and sustainable planning, monitoring and evaluation systems at national and sub-national levels; (iii) advocating for and supporting the design and implementation of MNCH packages, ensuring in this way that every mother and child, and even the hard to reach, are provided with an integrated package of maternal and child survival interventions, especially good access and quality of sexual and reproductive health; and (iv) strengthening capacity at national and sub-national levels to improve service delivery, focusing on support for sustainable integrated models that can provide evidence for national scale-up.

This AWP for 2011 will focus on accelerating cost-effective maternal, neonatal and child interventions in the following key areas: SSR/maternal health: Promoting and/or reinforcing Essential & Emergency Obstetric Care at health facility and community level, with special attention given to the promotion of family planning services and community and male involvement; Child survival: Re-enforcing IMNCI, C-IMNCI and Community Case Management (CCM) for common diseases, strengthening EPI, implementing the RED approach and measles elimination plan, expanding delivery of LLINs through routine and universal access campaigns and distribution of LLINs, with special attention to children under five years, pregnant women, OVCs, PLWHA and other vulnerable groups. The JP will also focus on accelerating Nutrition elements of the ACSD package and the implementation of the Multi-sectoral Action Plan on Chronic Under-nutrition, by supporting infant and young child feeding interventions at health facility and community level, strengthening the Basic Nutrition Package, the distribution of Vitamin A supplements and de-worming and the National Salt Iodisation Programme and creating demand for iodised salt, introducing the fortification of staple foods and implementing the nutrition rehabilitation programme, including supplementary feeding and the further roll out of outpatient treatment of severe acute malnutrition with community involvement.

The primary geographical focus of the JP in 2010 will continue to be in the 12 selected districts: Maputo province - Manhiça and Matola; Gaza- Chokwe and Xai-Xai; Sofala – Buzi and Dondo; Nampula - Ribaue and Nacala Porto; Zambezia – Maganja da Costa and Pebane; Niassa - Mandimba and Marrupa. However, the JP will continue providing support for the consolidation of the RED approach in the existing 66 districts. This JP will also support nutrition interventions in priority districts that might not be part of the 66 RED districts, though efforts will be in place to ensure complementarities and prioritization in these districts.