Future work plan

2011 is the year for consolidating the results achieved in 2010 by the Decentralization JP. As shown in Annex 2 to the present report, which consists of the Annual Work Plan of this JP for 2011, major interventions planned for the present year will be primarily directed to the output of the strengthening of decentralized government capacity for participatory and inclusive district planning (PEDD and PESOD), Provincial Planning (PEP and PES), and Monitoring and Evaluation. This priority is reflected in terms of the number of agencies working together for this joint output (FAO, UNFPA, UNW, UN HABITAT and UNDP) and also in terms of the amount of JP funds (approximately US$ 1.5 million) and agency or other resources (about 0.7 million) needed for 2011. In this regard the consolidation of methodological frameworks to integrate cross- cutting issues (such as food security and nutrition, gender, HIV/AIDS) in provincial and district development plans is one of the main activities planned for 2011.

Priority will be given to enhancing organs of the state at sub national level through continuing to support participatory, effective, inclusive and accountable good local governance and service delivery.  This is more clearly reflected in terms of the amount of funds budgeted for 2011 to achieve this result (nearly US$ 0.6 million of JP funds and about US$ 0.25 million of agency or other resources), rather than in terms of the number of UN participating agencies (only UN HABITAT, UNDP and ILO) planning to be jointly involved in supporting the achievement of that result. It is very important to note the emphasis that will be given to service delivery, which can be understood as an effective approach for addressing issues such as reform fatigue and greater attention to planning rather than producing results on the ground. This will be reflected in the degree of satisfaction of users of public services at decentralized level.

It is equally important to mention the joint contribution of UNCDF, WHO, UNICEF and ILO, who are engaged in a set of activities focused on the output of getting communities empowered to develop sustainable livelihoods and life skills.  Approximately US$ 0.5 million of JP resources, complemented by nearly US$ 0.2 million of agency and other resources, are required to fund these activities in 2011.  The establishment of a Gender Equitable Local Development Fund (GELDF), designed to supplement Local Government expenditure to support women’s empowerment towards achieving gender equality, is one of the priorities for 2011 for achieving this community empowerment output.

As mentioned above, further details on the future work plan of the Decentralization JP are contained in Annex 2, which consists of its Annual Work Plan for 2011. A total envelop of approximately US$ 4.2 million, of which US$ 2.8 million are JP needs for 2011 and the remaining US$ 1.8 million are UN agency funds and other resources, is what is required for the implementations of various activities under the aforementioned plan.  A summary of needs from and contributions by UN participating agencies in the decentralization JP is contained in the bottom of Annex 2.

Annex 1: 2010 results annual work plan Decentralisation JP

| Annex I | Agency | 2010 AWP Budget | Actual One Fund Disbursement in May 2010 | Total One Fund Budget for 2010 | 2010 Expenditures for One Fund Budget as of 2010 | One Fund Delivery Rate for 2010 | 2010 Agency Budget | 2010 Expenditures for Agency Budget as of 2010 | 2010 Agency Budget Delivery Rate as of 2010 | (13) Total Programme Delivery Rate for 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Support to Decentralization | FAO | 430,799 | 19,800 | 427,790 | 369,316 | 86% | 0 |  | 0% | 86% |
|  | UNDP | 2,152,360 | 336,600 | 1,060,600 | 760,195 | 72% | 1,430,000 | 1,523,566 | 107% | 92% |
|  | UNCDF | 400,000 | 360,000 | 360,000 | 13,000 | 4% | 0 | 0 | 0% | 4% |
|  | UNFPA | 675,000 | 292,500 | 492,500 | 435,056 | 88% | 150,000 | 150,000 | 100% | 91% |
|  | UNICEF | 265,000 | 135,000 | 135,000 | 38,604 | 29% | 115,000 | 19,313 | 17% | 23% |
|  | ILO | 460,000 | 391,500 | 416,500 | 306,604 | 74% | 0 | 0 | 0% | 74% |
|  | WHO | 250,000 | 102,600 | 228,221 | 119,562 | 52% | 10,000 | 10,000 | 100% | 54% |
|  | UNESCO | 420,000 | 113,400 | 336,489 | 52,669 | 16% | 80,000 | 66,500 | 83% | 29% |
|  | UN-HABITAT | 440,000 | 180,000 | 180,000 | 167,000 | 93% | 400,000 | 400,000 | 100% | 98% |
|  | UNHCR | 460,073 | 198,000 | 279,451 | 219,413 | 79% | 179,720 | 179,720 | 100% | 87% |
|  | UNIFEM | 561,270 | 225,000 | 252,720 | 142,548 | 56% | 101,000 | 92,836 | 92% | 67% |
|  | Total | 6,514,502 | 2,354,400 | 4,169,271 | 2,623,968 | 63% | 2,465,720 | 2,441,935 | 99% | 76% |

# Annex 2: CONSOLIDATED ANNUAL WORK PLAN 2011

# Support to Decentralization and Integrated Local Development

| JP Outcome(s): UNDAF CP Outcome 1.1: Decentralized government capacity strengthened in all provinces, at least 50 districts and at least 3 municipalities for participatory and gender responsive planning, monitoring and evaluation, gender sensitive needs assessment as well as coordination and partnership |
| --- |
| Specific Outputs | Annual Targe Indicators | Planned Activities towards stated outputs | TIME FRAME | Implementing Partner / Supporting Agency | PLANNED BUDGET |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Budget / Input Description | Amount JP US$ |
| UNDAF CP Output 1.1.1: Capacities supporting planning, monitoring and the participatory evaluation of strategic integrated plans, with an emphasis on cross-cutting issues such as gender and HIV/AIDS strengthened |
| JP Output 1.1.1.1: Decentralized government capacity for participatory and inclusive district planning (PEDD and PESOD), Provincial Planning (PEP and PES), Monitoring and Evaluation strengthened | Food security and nutritional issues integrated in district and municipal development plans | 1.1.1.1.1 Advocacy, discussion and dissemination of the methodological framework to integrate food security and nutritional issues in district development plans. | X | X | X | X | FAO/MINAG/SETSAN FAO/MINAG/SETSAN FAO/MINAG/SETSAN FAO/MINAG/SETSAN FAO/MINAG/SETSAN | Organize workshops Policy brief publications Publication of articles Elaborate TV/Video report | 70,000 |
|  |  | 1.1.1.1.2 Editing and publication of methodological frameworks, policy briefs, papers and articles related to food security issues. | X | X | X |  |  | 1. Editing and translation of materials 2. Publication of methodological frameworks | 70,000 |
|  |  | 1.1.1.1.3 Support SETSAN in mainstreaming FSN issues in district development plans. | X | X | X | X |  | 1. Train SETSAN Central 2. Train Civil Society Organizations (CSO) 3. Train the provincial and district technicians | 125,000 |
|  |  | 1.1.1.1.4 Support SETSAN in the elaboration of the food security and nutrition baseline study. |  | X | X |  |  | 1. Support for ToR definition 2. Support for data collection 3. Support for elaboration of FSN district and provincial profiles 4. Support for data analyses | 100,000 |
|  |  | 1.1.1.1. 5 Training of trainers (SETSAN Provincial Units) on Food Security Participatory Planning for Mainstreaming Food Security into District Development Plans. | X | X | X | X |  | 1 Organise workshops 2. Train provincial and district teams 3. Elaborate District Plans with FSN mainstreamed | 75,000 |
|  | Sub Total FAO Planned Budget: | Source FAO | 0 |
|  |  | Source JP | 440,000 |
|  |  | Subtotal FAO | 440,000 |
|  | Indicator 1 Harmonized Methodological Framework to integrate cross- cutting issues includingGender and HIV/AIDS, into province and district development plans elaborated and validated. Indicator 2: Nr of district plans including MDG-based approach and cross-cutting issues and in line with district planning guidelines. Indicator 3: Civil society has increased awareness of gender and HIV/AIDS development issues Indicator 4: % of women and young people participating meaningfully in DO. | Activity 1.1: Deliver a harmonized Methodological Framework to integrate cross-cutting issuesincluding gender and HIV/AIDS into Province and District Planning. | X | X | X |  | CAP/MPD | JP: 10,000 0R:10,000 | National Consultant Field mission Printing and dissemination. | 10,000 |
|  |  | Activity 1.2: Finalize training modules for integration of cross-cutting issues (gender and HIV/AIDS) into development plans and harmonize with other cross-cutting issues (Food Security). |  |  |  |  | MPD, CAP Provincial Govt, /UNFPA | JP: 40,000 0R:10,000 | National Consultant, Field mission Printing and dissemination | 40,000 |
|  |  | Activity 1.3: Delivery of training courses on integration of cross cutting issues (gender, human rights, HIV/AIDS) into development plans at district and provincial levels, targeting planners, journalists and members of “Conselhos Consultivos Distritais. |  | X | X | X | MPD, CAP, Provincial Gov in Zambezia, Nampula, Niassa, Tete and Gaza / UNFPA | JP: 65,000 0R:10,000 | National Consultant Field mission | 65,000 |
|  |  | Activity 1.4: Provide technical support to the Secretariat of the Provincial Development Observatories and IPCCs in order to ensure the meaningful participation of women and young people. |  |  |  |  | MPD, Provincial Gov in Zambezia, Nampula, Niassa, Tete and Gaza / UNFPA | JP: 40,000 0R:10,000 | National Consultant Field mission | 40,000 |
|  | Indicator: Capacity of Government and CSOs to analyze and monitor cross-cutting issues such as gender, HIV/AIDS, and to strengthen indicators. | Activity 2.1: Adoption of GIS used for 2007 Population and Housing Census for presentation of district profiles and other relevant socio-demographic data. |  |  |  |  | INE; MAE, Provincial and District Gov./UNFPA | JP: 150,000 0R:50,000 | National Consultant Field mission Printing and dissemination. | 150,000 |
|  |  | Activity2.2: Provide technical and financial assistance to INE for adoption of IMIS and ESDEM management, to make available socio-demographic and geo-spatial data, provision of training and equipment to the IMIS and ESDEM team. | X | X | X | X | INE/UNFPA | JP: 90,000 0R:10,000 | Technical and financial assistance | 90,000 |
|  |  | Activity2.3. Provide technical and financial assistance to the development and dissemination of provincial and district Socio-economic Profiles for the southern and central regions based on the 2007 census data and MICS data. | X | X | X | X | INE/UNICEF UNFPA | JP: 20,000 0R:10,000: | Technical and financial assistance | 20,000 |
|  | Sub Total UNFPA1 Planned Budget: | Source OR: | 110,000.0 |
|  |  | Source JP: (200,000 is 2009 balance; 215,000 is unfunded) | 415,000.0 |
|  |  | Sub Total UNFPA 1: | 525,000.0 |
|  | At least 80% of district planners in the provinces of Niassa, Cabo-Delgado and Gaza familiarized with the concept and/or assisted in undertaking gender responsive planning and budgeting. | Train provincial and district planners on gender responsive planning and budgeting in the provinces of Niassa, Nampula, Cabo-Delgado and Gaza. |  |  |  |  | MPD/ DPPF Niassa/ UNW | UNW15,000 JP136,190 | Technical Advisor National consultants Workshops | 136,190 |
|  | All women members of the local councils in Muembe have been trained and assisted for their participation. | Train and provide technical assistance to community members, particularly women, in their participation in the local levels councils in Muembe, Niassa Province. | X | X | X | X | DPPF Niassa, Muembe Government/ UNIW | UNIW 234,960 | Workshops and travel DSA & equipment |  |
|  | Improved gender responsiveness of district level planning, budgeting and M&E tools. | Assess gender sensitiveness of local plans, budgets and processes, and train and coach stakeholders. |  |  | x | x | DPPF Niassa, Muembe Government/ UNW | UNW | Idem | Included above |
|  | Sub Total UNW Planned Budget: | Source (UNW): | 249,960 |
|  |  | Source JP:) | 136,190 |
|  |  | Sub Total UNW 1: | 386,150 |
|  | Capacity for contributing to effective governance, policy formulation and implementation strengthened at local level. | Support to dissemination of legislation and policy documents on urban development and local governance. |  |  | X | X | MAE/UN-HABITAT | UN-HABITAT One Fund | National consultants Workshops Printed materials | 15,000 45,000 |
|  |  | Translation, adaptation and/or printing of selected local leadership manuals, papers and articles. | X | X |  |  | MAE, UN-HABITAT | UN-HABITAT One Fund | National consultants | 20,000 30,000 |
|  |  | Preparing implementation of simplified land registration demonstrations in Chibuto, Manica and Nacala. |  | X | X | X | MAE, Municipalities/UN-HABITAT |  | Local missions Workshops |  |
|  |  | Implementation of demonstration projects piloting participatory planning and budgeting in Chibuto, Manica and Nacala. | X | X | X | X | UN-HABITAT HQ, MAE, A Politécnica, ANAMM | UN-HABITAT One Fund | Civil works Workshops | 148,000 25,000 |
|  | Sub Total UN HABITAT 1 Planned Budget: | Source OR: | 183,000 |
|  |  | Source JP: | 100,000 |
|  |  | Sub Total UN HABITAT1: | 283,000 |
|  | PESOD/PESOP planning methodologies software validated by MPD with technical manual available Annual Target; at least 85% of districts producing appropriated plans based on PARPA/ODM and owned by the communities | 1.Develop and test PNPFD evaluation tools | X | X | X |  | MPD/UNDP | Planned :24,000 JP:24,000 | National consultants Workshops Printed materials | 24,000 |
|  |  | 2.Contribute to the drawing of SMoDD (PNPFD Performance evaluation system and pilot it in 30 districts in coordination with MAE | X | X | X |  |  |  |  |  |
|  |  | 3. Contribute to the definition of evaluation criteria and performance indicators jointly with MAE |  | X |  |  |  |  |  |  |
|  | Strategic Local Planning Consolidated (PNPFD Result 2.2) Nampula Annual Targets: 6 PEDD´s readjusted including cross-cutting issues (Environment climate change, DRR; gender and other vulnerable groups); 3 Districts (Ribáuè, Memba e Moma) implementing experimental food security and nutrition and risk managements aspects; 4 PDUT (land use plans) approved in Mecubúri, Mogovolas, Murrupula e Muecate. | 1. Assist DPPF and SP in capacity building of the das RPDL and District Technical Council (CPAP 1.1.1, 2.1.1 ;) |  | X | X | X | Nampula/UNDP | Planned :24,000 JP:24,000 | Workshops Printed materials Travel & DSA | 24,000 |
|  |  | Support the districts in the readjustment and alignment of 6 PEDD to the PQG (CPAP 1.1.1, 2.1.5) |  |  |  |  |  |  |  |  |
|  | DEL Integration in the strategic and operational local plans supported Annual targets 6 PEDDs with DEL activity included; 18 Districts with planning and implementing systems improved | 1. Support the district Governments in DEL integration in in 6 PEDD´s and implementation of already readjusted and aligned PEDD´s in 8 districts (Ribáuè,Malema, Mecubúri,Nampula, Meconta, Monapo, Mossuril, Angoche) |  | X | X | X | MPD/Nampula/UNDP | Planned :14,000 JP:14,000 | Workshops travel&DSA | 14,000 |
|  |  | 2. Ssupport the district Governments in implementing |  |  |  |  |  |  |  |  |
|  |  | 3. FDD Dec. with ART-PAPDEL collaboration |  |  |  |  |  |  |  |  |
|  | Financial, budgeting, administrative and revenue collection capacities improved (Result PNPFD; Result CPAP 2.1.5) | 1.Support the accountability and closing of management accounts processes (CPAP 2.1.6; 2.2.3; 2.2.5) |  | X | X | X | MPD/Nampula/UNDP | Planned :36,000 JP:36,000 | Workshops travel&DSA | 36,000 |
|  |  | 2. Support district governments in the SISTAFE e e-SISTAFE implementation |  |  |  |  |  |  |  |  |
|  |  | 3. Ensure pedagogical audits and disseminate the audit reports |  |  |  |  |  |  |  |  |
|  |  | 4. Support district governments in the capacity building of the people involved in the fiscal collection CPAP (2.1.6; 2.2.3; 2.2.5) |  |  |  |  |  |  |  |  |
|  |  | 5. Support the districts in SISRECORE and financial management Periodical evaluations |  |  |  |  |  |  |  |  |
|  | Good practices and innovations under PNPFD framework systematized and disseminated | 1. Produce and disseminate guiding manuals to ensure collection compilation and knowledge systematization | X | X | X | X | MPD/UNDP | Planned :20,000 JP:20,000 | Printing materials Workshops Travel & DSA | 20,000 |
|  |  | 1. Disseminate and discuss ways to implement the Knowledge Management Strategy at all levels 2. Produce and disseminate guidelines for documentation and best practices management 3. Organize a National workshop ongGood practices within PFD |  | X X X | X X X | X X X | MPD/UNDP | Planned :20,000 JP:20,000 | Consultants Printing materials Workshops Travel & DSA | 20,000 |
|  | Good practices and innovations under PNPFD framework registered, processed and submited to Ministério da Planificação e Desenvolvimento Annual Targets: Cabo Delgado Good practices disseminated at TVM, Provincial Government Portal and other mass media Nampula: Rehabilitation of the Namaíta Regional Centre Local concluded Gaza Good practices disseminated at TVM, Provincial Government Portal and other mass media 1 Knowledge exchange with Sofala province conducted; At least 5 inter-district knowledge experience conducted | 1.Document PPFD - Cabo Delgado experience 2.Promote knowledge exchange between SDs, CLs and with other province s- PPFD - Cabo Delgado |  |  | X | X | Cabo Delgado /UNDP | Planned 35,000 JP:35,000 | Workshops Travel & DSA | 35,000 |
|  |  | 2.Assist DPOPH in the strengthening of the Centro Tecnológico Namialo | X | X | X | X | Nampula/UNDP | Planned :8,000 JP:8,000 | Workshops Travel & DSA | 8,000 |
|  |  | 3. Support the operationalization of the Centro de Formação em Administração de Namaita |  | X | X | X | Nampula /UNDP | Planned: 172,000 Carry over from 2010 122,000 JP:50,000 | Local construction companies | 50,000 |
|  |  | 4.Gaza set up a good practice management system |  | X |  | X | Gaza/UNDP | Planned 35,000 JP:35,000 | Printing materials Workshops Travel & DSA | 35,000 |
|  |  | 5.Gaza promotes knowledge exchange between SDs, CLs and with other provinces s- PPFD- Gaza |  |  |  |  |  |  |  |  |
|  | 6.2 Results & impact of the programme monitored, evaluated & documented Annual Targets: 4 quarterly reports appoved and submitted to DNP; 1 Annual report approved and submitted to DNP 4 CDS meetings conducted and reports submitted to DNP | 1.Cabo Delgado: Provide logistic support to the processes and components of the programme | X | X | X | X | Cabo Delgado /UNDP | Planned 20,000 JP20,000 | Printing materials Travel & DSA equipments Miscellanious | 20,000 |
|  |  | 2.Cabo Delgado: Supervision missions to the districts to monitor PNPFD activity implementation |  |  |  |  |  |  |  |  |
|  |  | 3 . Gaza :Ensure Project offices fucnctioning (viagens, visitas, meios, equipamentos e materiais) | X | X | X | X | Gaza/UNDP | Planned 39,000 JP:39,000 | Printing materials Travel & DSA Equipment Miscellanious | 39,000 |
|  |  | 6.2.2 Elaborate trimestrial and annual progress reportswhich help to evaluate the programme. |  |  | X | X |  | Planned 39,000 JP:39,000 |  | 39,000 |
|  | Sub Total UNDP 2 Planned Budget: | Source RR: | 122,000 |
|  |  | Source JP: | 364,000 |
|  |  | Sub Total UNDP 2 : | 486,000 |
| JP Output 1.1.1.2: MDG-based municipal strategic plans, annual plans and budgets developed with emphasis on HIV/AIDS & gender. |  | Strengthen the capacity of municipalities to plan short-term and medium-term development strategies, to coordinate the work of sectoral ministries and donors, to engage with civil society in planning and monitoring. |  |  |  |  | MAE/UNFPA |  |  |  |
|  | Global policy instruments concerning human settlements, namely Habitat Agenda and MDG target 11, disseminated to leadership and civil society at local level. | Mainstreaming municipal development issues into multi stakeholder decentralization fora such as GIDE and others supported by relevant CSOs and academic institutions. | X | X | X | X | MAE, MICOA, MOPH, CSO/HABITAT |  | Workshops Printed materials |  |
|  |  | Undertaking assessments related to basic urban services development / delivery and urban environmental management at municipal level in Mozambique. | X | X | X | X | MAE, MICOA, MOPH, Municipalities / HABITAT | OR : 110,000 | National consultants International consultants Workshops |  |
|  |  | World Habitat Day preparation, events and media campaign. |  |  |  | X | CSOs / HABITAT | JP: 50,000 | Local missions Printed materials Branding materials Workshops | 50,000 |
|  |  | Implementation of Urban Governance Inde in Maputo, Chibuto, Manica and Nacala as a pilot methodology. | X | X | X |  | MAE, ANAMM, Municipalities / HABITAT | JP:50,000 | National consultants Workshops Printed materials | 50,000 |
|  | Sub Total UN HABITAT 2 Planned Budget: | Source OR: | 110,000 |
|  |  | Source JP: | 100,000 |
|  |  | Sub Total UNHABITAT21: | 210,000 |
| JP Output 1.1.4.2: 2 Government institutions have increased access to data on the situation of Mozambican socio-demographic, children and women through ESDEM at national and sub-national level. | Target: Two thematic analyses done using 2007 census data Indicators: # of thematic analyses done using 2007 census data | Activity 2.4. Promote Research and Development in partnership with academic institutions related to Population, national development strategies, decentralization and local development policies and strategies. | X | X | X | X | UNFPA | 0R:30,000 | National Consultant, Field mission, printing and dissemination. |  |
|  |  | Activity 2.5 Undertake and disseminate thematic analysis from existing data of the 2007 Population and Housing Census and other Surveys. |  |  |  |  | MPD; INE, CAP /UNFPA | 0R:10,000: | Technical and financial assistance |  |
|  |  | Deliver training on use of ESDEM management, dissemination and training Support regular management and dissemination of ESDEM and training on its use at national and provincial levels. Provide training to CSOs in the use of ESDEM as a tool for PARPA monitoring. | X | X | X | X | MPD, Provincial Governments (Nampula, Gaza and Cabo Delgado) / UNICEF | TA | Technical Assistance | n/a |
|  | Sub Total UNFPA 2 Planned Budget: | Source OR: | 40,000 |
|  |  | Source JP: 0 | 0 |
|  |  | Sub Total UNFPA 2: | 40,000 |
| JP Output 1.2.2.1: Decentralization and district capacity of local organs of state strengthened to promote participatory, effective, inclusive and accountable good local governance and service delivery. | Awareness on benefits of participatory and gender responsive planning enhanced. | Undertake compilation and disaggregation of urban indicators. | X | X |  |  | MAE, MICOA, MOPH, INE / HABITAT | JP : 60,000 | National consultants International consultants | 60,000 |
|  |  | Undertake assessment on budget allocation trends between municipalities / districts, and mapping of municipal participatory budgeting experiences in Mozambique. | X | X | X | X | MAE, MICOA, MOPH / HABITAT | JP : 45,000 UN-HABITAT : 20,000 | National consultants Workshops | 45,000 |
|  |  | Training and implementation of participatory budgeting in the municipalities of Chibuto, Manica and Nacala. |  | X | X |  | MAE, ANAMM, Municipalities / HABITAT | JP : 15 :000 UN-HABITA : 20,000T | National consultants Workshops | 15,000 |
|  |  | Peer to peer exchanges for learning best practices on participatory planning, participatory budgeting and gender mainstreaming at municipal level. |  | X | X |  | MAE, ANAMM, Municipalities / HABITAT | JP :20,000 UN-HABITAT 35,000 | Local missions Workshops National Consultant | 20,000 |
|  | Sub Total UN HABITAT 3 Planned Budget | Source OR: | 75,000 |
|  |  | Source JP: | 140,000 |
|  |  | Sub Total UN HABITAT 3l: | 215,000 |
|  | . UNDP District profiles updated, provincial profiles prepared and GIS reactivated (CPAP 2.1;2.2) Annual targets 100% district with profiles updated GIS reactivated in 10 Provinces | 1.Conclude district profiles updating |  |  |  |  | MAE/UNDP | Planned:248,800 Carried over 74,400 JP: 174,400 | Contracts Workshops and travel DSA & equipment |  |
|  |  |  |  |  |  |  |  |  |  | 174,400 |
|  |  | 2. Start the production of provincial profiles ; |  |  |  |  |  |  |  |  |
|  |  | 3. Engage all partners that will contribute to results achievement. |  |  |  |  |  |  |  |  |
|  | Sub Total UN DP2 Planned Budget | Source OR: | 74,400 |
|  |  | Source JP: | 174,400 |
|  |  | Sub Total UNDP2: | 248,800 |
|  | Target: 1 Government institution, and 3 tripartite organizations capacitated on employment promotion, vocational training and labour issues Indicators # of partners with capacity building provided | -.Provide capacity building to Government and Tripartite partners - Support training to INEFP managers and staff -Support training to Trade Union and employers’ organizations - Support the promotion of income generation activities for vulnerable groups | X | X | X | X | INEFP/OTM/CONSILMO /CTA/IPEME/ADELs | JP: 300,000 ILO: 100,000 | Organize training Hire consultants Development of tools and revision of employment strategies | 300,0000 |
|  | Sub Total ILO 2 Planned Budget | Source ILO: | 100,000 |
|  |  | Source JP: | 300,000 |
|  |  | Sub Total ILO 2: | 400,000 |
| JP Output 1.2.2.2: Communities empowered to develop sustainable livelihoods and life skills (Millennium Villages) | Indicators HDI adjusted; Access to basic social services increased; Number of CD programmes delivered and community workers trained; Nr of NGOs trained on contractual approach. Nr of BTLs delivered; District implementation reports. Nr of CHWs trained. Reports from implementation partners. | Institutional capacity building on planning at national and decentralized level including dissemination of planning/budgeting tools |  | X | X | X | MoH-District & Provincial Health Directorates / WHO | JP: 30,000 | National Consultants DSA Dissemination Training materials Learning tools | 30,000 |
|  |  | Support organization of 2 national meeting/ workshops. | X |  |  | X | MoH- District Health Local Communities/WHO | JP: 15,000 | Field Missions National Consultants Purchase of Equipment (Computer, printers) | 15,000 |
|  |  | Support supervision visits by DPC( MoH)to assess the collaboration between provincial/district health authorities and NGOs, and sharing of information |  | X | X | X | MoH- District Health Local Communities/WHO | JP: 20,000 |  | 20,000 |
|  |  | Dissemination of health information at decentralized level. | X | X | X | X | MCT/MoH/ WHO | JP: 0 | Local Missions DSA | 0 |
|  |  | Technical and financial support for health-related MDG activities in Millennium villages. |  | X | X | X | MoH- District Health Directorates MCT Local Communities/WHO | JP: 20,000 | Consultants Local travel Printing of reports Dissemination Training materials | 20,000 |
|  |  | Support the operationalization of Community Health delivery programme. | X | X | X | X | MoH- District Health Directorates Local Communities | JP: 25,000 | Consultants Facilitators Printing and translation of reports Dissemination Training materials | 25,000 |
|  | Sub Total WHO Planned Budget | Source WHO: | 0 |
|  |  | Source JP: | 110,0000 |
|  |  | Sub Total WHO: | 110,000 |
|  | Indicator 1: % of Local Government expenditure devoted explicitly to pro-poor and gender equitable local development investments. | Establish Gender Equitable Local Development Fund GELDF to supplement Local Government expenditure to support women’s empowerment towards achieving equality. |  | X | X | X | Provincial Government- UNCDF/UNDP |  | UNCDF 100,000 Carry over from 2010: 360,000 Carry over from 2010: 40,000 JP 325,000 | 325,000 |
|  | Sub Total UNDCF 2 Planned Budget: | Source UNCDF: | 100,000 |
|  |  | Source JP: | 325,000 |
|  |  | Sub Total 1: | 425,000 |
|  | Indicator 1: Nr of provinces that have organized DOs in an effective and timely manner (Target: 7). Indicator 2: Civil society has increased awareness about child development issues (Target: Yes). Indicator 3: % of young people participating meaningfully in DO (Target: 50%). | 4.1. Provide technical assistance to the Ministry of Planning and Development (MPD) for key Development Observatories in order to document lessons learned and experiences of DO in Mozambique | X | X | X | X | Ministry of Planning and Development (National Directorate of Planning) | UNICEF:10,0000 JP: 5,000 | Technical and Financial Assistance | 5,000 |
|  |  | 4.2. Provide technical and financial assistance for the update and dissemination of the Web-enabled version and database of ESDEM v.5 to provincial and district levels. | X | X | X | X | INE) | UNICEF: 15,000 JP:25,000 | Technical assistance | 25,000 |
|  |  | Continued training, capacity development and strategic/policy support. Expand recent experience of aid dialogue to provinces through the Provincial Directorates of Planning and Finance and Provincial Governors (Cabinet of the Governor) |  |  |  |  |  | UINICEF30,000 JP:15,000 |  | 15,000 |
|  | Sub-otal UNICEF | Source UNICEF: 55,000 | 55,000 |
|  |  | Source JP: | 45,000 |
|  |  | Sub Total 3: | 100,000 |
|  | Methodology for cooperation between public investments and local savings and micro-credit groups approved | Support the DNPDR in developing strategy to support savings and micro-credit schemes | X | X | X | X | ILO/DNPDR/LEDAs | Planned: 30,000 JP: 30,000 | Hire consultants and organize workshops | 30,000 |
|  | Sub-total ILO 2 | Source ILO | 0 |
|  |  | Source JP | 30,000 |
|  |  | Sub-totalILO23 | 30,000 |
| JP Output 1.2.2.3: Improved pro-poor delivery of services and income generation projects by strengthening particularly women-led associations, local authorities, community organizations, civil society and the private sector. | Target Indicator 1: Number of development vectors identified and integrated into PEDD per district (Target: At least 1 per focus district). | Activity 1: Support INAR and Line Ministries’ capacity to respond to protection issues in mixed migration flows |  | X | X | X | INAR UNHCR | Planned: 20,000 Allocated: RR 1,000 OR 9,000 Unfunded: 10,000 | Meetings Material DSA Assistance Transport Communication | 10,000 |
|  |  | Activity 2: Support INAR to implement the roadmap for the Comprehensive Review of Rwandese Refugee Situation |  | X | X | X | UNHCR INAR | Planned: 3,000 Allocated: OR 3,000 Unfunded: 0 | Material DSA Meetings Communication Campaigns | 0 |
|  |  | Activity 3: Support training workshops for provincial and district authorities and civil society on protection issues |  | X | X | X | UNHCR INAR | Planned: 7,000 Allocated: RR 5,000 Unfunded: 2,000 | DSA, Transport, Material, Premises | 2,000 |
|  |  | Activity 4: Support Ministry of Justice, Civil Registries and Ministry of Interior, as well as civil society organizations to increase civil registration and reduce the risk of statelessness, especially in bordering provinces. | X | X | X | X | UNHCR MJ MINT Civil Society | Planned: 100,000 Allocated: OR 35,000 Unfunded: 65,000 | DSA Registration Fees Transport Material Meetings Equipment | 65,000 |
|  |  | Activity 5: Support to the implementation of AGDM methodology and participatory assessment by coordinators and those responsible for implementation of projects in Maratane Camp. |  | X | X | X | INAR/UNHCR | Planned: 2,500 Allocated: RR: 1,500 Unfunded: 1,000 | Transport Meeting Material Premises | 1,000 |
|  |  | Activity 6: Support INAR and Line Ministries in Maratane Camp to develop their capacity on programming, budgeting and reporting (Training, COP Meeting). | X | X | X | X | INAR/UNHCR | Planned:6,000 Allocated: RR 4,000 Unfunded: 2,000 | DSA, Material Transport | 2,000 |
|  |  | Activity 7: Support local officials (Police, Health, Social Services, INAR) to provide services in an integrated manner in order to provide appropriate protection and assistance to survivors/victims of violence (SGBV or torture), unaccompanied children and people with special needs. | X | X | X | X | UNHCR INAR | Planned: 5,000 Allocated: RR 3,000 Unfunded: 2,000 | Material, Meeting costs Incentives to local police (sungu sungu) Training on psycho-social counselling for officials | 2,000 |
|  |  | Activity 8: Support to INAR Local Delegations | X | X | X | X | UNHCR INAR | Planned: 6,000 Allocated: RR 3,000 Unfunded: 3,000 | Staff costs Contracts Materials Utilities | 3,000 |
|  |  | Activity 9: Support INAR coordination at camp level as well as provide technical assistance to line ministries in the camp. | X | X | X | X | INAR/UNHCR | Planned: 5,000 Allocated: RR 4,000 Unfunded: 1,000 | Construction material Generator, Fuel and maintenance costs for motorbikes | 1,000 |
|  |  | Activity 10: Support the administration infrastructure in Maratane Line Ministries Offices, including the expansion of warehouses, construction of offices for Security Committee and Refugee Representation. |  | X | X | X | UNHCR INAR | Planned:10,000 Allocated: OR: 8,000 Unfunded: 2,000 | Material Transport Contracts | 2,000 |
|  |  | Activity 11: Support INAR to improve the reception capacity in Maratane Camp through the expansion of the transit centre | X | X |  |  | UNHCR INAR | Planned: 25,000 Allocated: 15,000 Unfunded:10,000 | Material Transport Contracts | 10,000 |
|  |  | Activity 12: Support to Line Ministries (MMAS) to improve Kindergarden | X | X | X | X | UNHCR INAR DPMMAS | Planned: 4,500 Allocated: RR 3,300 Unfunded: 1,200 | Construction Material Furniture | 1,200 |
|  |  | Activity 13: Support to Line Ministries (Education) to retain teachers - construction of teachers' houses | X | X | X | X | UNHCR INAR DPEC | Planned:18,038 Allocated: OR:5,038 Unfunded:13,000 | Construction Material | 13,000 |
|  |  | Activity 14: Support INAR with the improvements of the water sanitation system in Maratane Camp - construction of 4 boreholes and 100 latrines |  |  |  |  | UNHCR INAR | Planned: 50,000 Allocated: RR: 22,500 Unfunded: 27,500 | Construction Material Transport | 27,500 |
|  |  | Activity 15: Support INAR to improve its RSD capacity (equipment, additional staff) |  |  |  |  | UNHCR INAR | Planned: 2,000 Allocated: RR:1,000 Unfunded:1,000 | Equipment Staff Contracts | 1,000 |
|  |  | Activity 16: Support INAR to implement the roadmap for the Campaign against Discrimination (training for local authorities, police, public meetings, information campaign, debates on media) |  |  |  |  | UNHCR INAR | Planned: 15,000 Allocated: RR:5,000 Unfunded: 10,000 | Meetings Campaigns Trainings Transport | 10,000 |
|  |  | Activity 16: Support INAR to implement activities in line with the Policy on Urban Refugees |  |  |  |  | UNHCR INAR | Planned: 7,000 Allocated: RR:1,000 Unfunded:6,000 | Material Meetings Transport Trainings | 6,000 |
|  |  | Activity 17: Joint Programme Coordination and M&E |  |  |  |  | UNHCR | Planned: 20,000 Allocated: RR:10,000 Unfunded: 10,000 | DSA Missions Fees | 10,000 |
|  | Sub Total UNHCR Planned Budget | JP | 166,700 |
|  |  | Allocated: Source UNHCR: | 79,300 |
|  |  | Allocated: Source JP (Balance from 2010): | 60,038 |
|  |  | Sub Total UNHCR 1: | 306,038 |
| Total Planned Budget: | Source Agency / OR: | 1,356,698 |
|  | Source JP: | 2,846,290 |
|  | Grand Total: | 4,202,988 |

| Agency | Agency/OR | JP Needs 2011 |
| --- | --- | --- |
| FAO | 0 | 440,000 |
| UNDP | 194,400 | 538,400 |
| UNCDF | 100,000 | 325,000 |
| UNFPA | 150,000 | 415,000 |
| UNICEF | 55,000 | 45,000 |
| ILO | 100,000 | 330,000 |
| WHO | 0 | 110,000 |
| UNESCO | 0 | 0 |
| UN-HABITAT | 368,000 | 340,000 |
| UNHCR | 139,338 | 166,700 |
| UNIW | 249,960 | 136,190 |
| Total | 1,356,698 | 2,846,290 |