Future Work Plan

The 2011 AWP will continue to work towards the achievement of the three defined results of the Joint Programme on Gender Equality and Women’s Empowerment. An important achievement of the Programme has been the emphasis that has been placed on the economic empowerment component of the 2011 AWP. The result of this is that the 2011 AWP includes more specific and expanded actions in this component. Financial resources should be allocated in order to support the achievement of this objective. Actions on Violence against Women and on Advocacy / Law dissemination will continue to be core action areas in 2011.

Estimated Budget Required

The estimated budget for 2011 is  $ 3,781,435.0, of which $1,349,226.7 is expected to be financed by the One Fund, as outlined in the 2011 Annual Work Plan.

# Annual Plan

# COUNTRY: Mozambique

ANNUAL PLAN: Joint Programme on Women’s Empowerment and Gender Equality.	Year: 2011

| UNDAF JP OUTCOME: By 2011, Government and CSO capacity at national, provincial and local level, strengthened to plan, implement and monitor socioeconomic development in a transparent, t, accountable, equitable and participatory way in order to achieve the MDGs. |
| --- |
| OUTCOME RESULTS | BASE TARGET | PLANNED ACTIVITIES | TIMEFRAME | IMPLEMENTING PARTNERS | PLANNED BUDGET |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Financial Source | Budget/ Contributions/ Description | Amount in US |
| RESULT 1: Democratic governance and legislation reforms reinforced in order to enhance human rights-based approaches at all levels Output 1: National Capacity to formulate, advocate and implement gender responsive legislation, including the participation of civil society, reinforced. |
| (1) Training on gender provided by formal training institutions and the universities (2) Number of institutions with communication toolkit on gender and human rights related issues (3) PNAM published (4) Number of women trained on women workers’ rights defense (5) Reports on CEDAW produced | 5 8 1 284 1 1 | Activity 1.1 Train key partners on tools for gender mainstreaming / analysis and Gender Budgeting ● In the work place (gender auditing) and its implementation. ● In the macro and sector planning. ● Among CCT members (Nampula, Sofala and Maputo) ● COMUTRA ● Assotsi ● Housekeepers ● INSS, Escola Estudos Laborais, INEFP ● Consilmo | X | X | X | X | MMAS, MITRAB, INEFP, MITUR, IPEME, CTA, OTM, CONSILMO UEM (CeCaGe), ISAP DEP/DNM MMAS, DPMAS, Fórum Mulher MPD, CTAM (Zambézia), CTPAM, MISAU | ILO UNIFEM UNDP UNFPA WHO |  | 60,000.00 10,000.00 50,000.00 16,000.00 15.000,00 |
|  |  | Activity 1.2 Disseminate gender related ILO conventions: ● Draft a communication strategy for dissemination of the ILO Conventions ● Produce IEC material in local languages ● Campaigns for dissemination of Conventions ● Research on women and work | X | X | X | X | DNM, MITRAB, INEFP, MITUR, IPEME, CTA, OTM, CONSILMO | ILO |  | 25.000,00 |
|  |  | Activity 1.3 Partner’s participation in gender related training, international meetings / conferences: ● Turin ● CSW ● Other events / conferences | X | X | X | X | MMAS, MITRAB, INEFP, MITUR, IPEME, CTA, OTM, CONSILMO, Fórum Mulher, MMAS, NAFEZA, Other institutions | ILO UNDP UNFPA |  | 40.000,00 25,000.00 38,000.00 |
|  |  | Activity 1.4 Disseminate the CEDAW report and development of a simplified version | X | X | X | X | DNM/DPMAS | UNIFEM UNFPA |  | 15,000.00 15,000.00 |
|  |  | Activity 1.5 Disseminate and implement the II Conference on Women and Gender outcomes | X | X | X | X | DNM / DPMAS | UNDP UNFPA UNIFEM |  | 20,000.00 5,000.00 10,000.00 |
|  |  | Activity 1.6 Disseminate the Law on Domestic Violence and train CSOs on the Laws on Domestic Violence and on family, human rights and other gender related tools, including awareness action for girl and women’s protection during emergencies. | X | X | X | X | Fórum Mulher, MMAS, Interior, PDMAS (Zambézia), NAFEZA | UNDP UNFPA UNIFEM |  | 80,000.00 10,000.00 50,000.00 |
|  |  | Activity 1.7 Develop a toolkit on Gender, Human Rights and Culture to be considered in action plans. | X |  |  |  | DNM | UNESCO UNDP |  | 30,000.00 5,000.00 |
|  |  | Activity 1.8 Train managers and officers on gender, human rights and culture: ● Province and district officers ● Organizations from Tica, Nhamatanda, Beira and community radios ● Parliamentarians, Network of Women Ministers and Parliamentarians, and opinion leaders | X | X | X | X | DNM Assembleia da República / CASGA, DNM, DPMAS, CPAMs, CDPAMs Fórum Mulher MISAU/MTC | UNESCO UNDP UNFPA WHO |  | 20,000.00 50,000.00 19,000.00 20,000.00 |
|  |  | Activity 1.9 Support the dissemination of the National Plan for Women’s Advancement (PNAM) 2010-2014 | X |  |  |  | CNAM | UNDP |  | 30,000.00 |
|  |  | Activity 1.10 Evaluate the degree of implementation of the Gender Policy and Implementation Strategy | X | X | X | X | DNM | UNIFEM UNFPA |  | 10,000.00 5,000.00 |
|  |  | Activity 1.11 Support the production and dissemination of gender related information: ● Boletim Informativo ● Site on information sharing ● Collect and systematize gender disaggregated data (data base) and gender analysis in MMAS (including the Gender Profile in Mozambique) | X | X | X | X | DNM, CNAM, DPMAS DNM, Fórum Mulher, NAFEZA | UNDP UNFPA |  | 17,000.00 40,000.00 |
|  |  | Activity 1.12 Support awareness and lobbying actions for women’s empowerment and gender equality to local and community radios, and other media, including commemoration of events concerning women’s human rights | X | X | X | X | Fórum Mulher MMAS, DPMAS, NAFEZA | UNDP UNFPA |  | 20,000.00 35,000.00 |
|  |  | Activity 1.13 Support CNAM, DNM and DPMAS capacity building development, and promote organizations working on gender equality (administrative costs, training, technical assistance, meetings etc.) | X | X | X | X | MMAS, CNAM, DPMAS, CPAMs, FM, NAFEZA | UNFPA |  | 100,000.00 |
|  |  | Activity 1.14 Support the annual planning, monitoring and evaluation meetings, and create a system of M&E |  |  | X | X | DNM | UNDP |  | 35,000.00 |
|  |  | Activity 1.15 Promote women’s sexual and reproductive rights through lobbying, training and awareness actions, including training the youth on the use of female condoms, production of relevant material. | X | X | X | X | Fórum Mulher, NAFEZA | UNFPA |  | 30,000.00 |
|  |  | Activity 1.16 Support research / publications on: ● Feminization of poverty ● History book on Mozambican Women ● Other research | X | X | X | X | UEM, DNM | UNDP |  | 68,000.00 |
|  |  | Activity 1.17 Enhance / recycle the gender trainer’s network in Zambézia, Nampula and Maputo |  | X | X | X | DPMAS, NAFEZA, Fórum Mulher | UNFPA |  | 10,000.00 |
|  |  | Activity 1.18 Carry out monitoring visits | X | X | X | X | UNDP and partners | UNDP UNIFEM |  | 10,000.00 5,000.00 |
|  |  | Activity 1.19 Provide technical assistance to the Department of Sociology at UEM in the implementation of the project on gender based violence | X | X | X | X | UEM-Dept of Sociology | UNDP |  | 10.000,00 |
|  |  | Activity 1.20 Train MMAS’s HIV/AIDS and gender focal points to form a technical group focusing on planning and development programming on feminization of HIV/AIDS, and promote training of trainers on the use of female condoms. | X | X |  |  | MMAS, DPMAS | UNFPA |  | 8,000.00 |
|  |  | Activity 1.21 Support activities undertaken by men and youth on promoting gender equality (training and production of material) | X | X | X | X | Rede HOPEM, OCS | UNFPA |  | 10,000.00 |
| OUTCOME RESULTS | BASE TARGET | PLANNED ACTIVITIES | TIMEFRAME | IMPLEMENTING PARTNERS | PLANNED BUDGET |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Financial Source | Budget/ Contributions/ Description | Amount in US |
| OUTCOME 2: Institutions responsible for promotion of pro-poor, gender sensitive and sustainable economic development strengthened Output 2: Community access to business-related and financial services, disaggregated by district, area and stakeholders (in particular women and other less privileged groups) increased. |
| (6) Number of women who have completed the 1st cycle of literacy programme (7) Number of women trained on entrepreneurship / business management (8) Number of FFS with women majority assisted (9) Number of micro projects on agro-processing created and assisted | 0 100 676 972 145 170 ‘2 4 | Activity 2.1 Train key partners on business management methodologies and toolkits (GET AHEAD, CDSN), Technical-vocational and life skills, associativism (WEA), and functional literacy; good practices on income generation, gender HR and culture | X | X | X | X | INAS, IPEME, INEFP, CTA, IPEME, DPEC, Mutauanha, INEA, MMAS, DPMAS NAFEZA, Fórum Mulher | ILO UNESCO UNFPA |  | 10,000.00 60,000.00 31,000.00 |
|  |  | Activity 2.2 Replicate the training on business management to key partners (GET AHEAD, CDSN) and associativism (WEA). |  | X | X | X | INAS, IPEME, INEFP, CTA, IPEME | ILO |  | 15,000.00 |
|  |  | Activity 2.3 Provide capacity building / expose women entrepreneurs to the business environment: ● Training / production of IEC material on entrepreneurship ● Commercial fairs ● Financial fairs ● Economic fairs ● Women entrepreneurial month |  | X | X | X | INAS, IPEME, INEFP, CTA, IPEME Fórum Mulher | ILO UNFPA UNIDO |  | 30.000,00 5,000.00 45,000.00 |
|  |  | Activity 2.4 Allocate financial resources to women entrepreneurs (kits): ● GAPI ● Financing mechanisms (Local Investment Fund - FIL and FDD) ● Women’s associations ● Victims of domestic violence ● Patients with HIV and AIDS | x | X | X | X | INAS, IPEME, INEFP, CTA, IPEME Fórum Mulher MMAS | ILO UNESCO UNDP UNFPA |  | 10,000.00 100,000.00 30,000.00 10,000.00 |
|  |  | Activity 2.5 Within the Farm Field Schools (FFSs), train new facilitators on production methodologies and storage of agricultural products | X |  | X |  | DPAs of Maputo and Sofala, and DNEA | FAO |  | 38,662.00 |
|  |  | Activity 2.6 Carry out “master’s” courses on FFSs. | X |  |  |  | DNEA | FAO |  | 110,000.00 |
|  |  | Activity 2.7 Carry out district meetings, workshops and recycling courses on: ● Land Act (including experience exchanging among organizations) ● Training of trainers on gender, human rights and HIV/AIDS ● Micro-projects on small production units (agro-business) | X | X | X | X | SPER/DNEA Fórum Mulher | FAO UNIDO |  | 20,240.00 120,000.00 |
|  |  | Activity 2.8 Form new EMCs, provide assistance to the existing ones, and provide working material and financing for their activities | X | X | X | X | SDAE/SPER | FAO |  | 32,400.00 |
|  |  | Activity 2.9 Acquire bicycles and kits (rain coats and boots) for the network of EMC’s facilitators | X |  |  | X | SPER | FAO |  | 11,366.00 |
|  |  | Activity 2.10 Carry out “dias de campo” at EMCs (districts, and province levels) | X | X | X | X | SDAE/ SPER | FAO |  | 13,428.00 |
|  |  | Activity 2.11 Carry out monitoring and technical follow up visits to FFSs | X | X | X | X | SDAE/ SPER | FAO |  | 56,029.00 |
|  |  | Activity 2.12 Undertake evaluations and graduations of the FFSs |  | X | X | X | SDAE/ SPER | FAO |  | 5,278.00 |
|  |  | Activity 2.13 Undertake seminars, exchange of experiences and other training / harmonization | X | X | X | X | SDAE/ SPER | FAO |  | 59,331.00 |
|  |  | Activity 2.14 Produce / document communication material on FFSs and related activities | X | X | X |  | DNEA /SPER | FAO |  | 35,701.00 |
|  |  | Activity 2.15 Undertake workshops on mechanisms for women’s access to the Local Initiative Funds and DUATs and produce IEC materials on procedures to acquire land titles in 3 local languages |  | X | X | X | Fórum Mulher | UNFPA |  | 9.000,00 |
|  |  | Activity 2.16 Recruit national and international consultants on food processing | X | X |  |  | IPEME, SDAEs | UNIDO |  | 55,000.00 |
|  |  | Activity 2.17 Undertake local trips to coordinate activities at district level and monitor actions (national consultant / project manager / partners) | X | X | X | X | IPEME, SDAEs, DPMAS | UNIDO |  | 18,000.00 |
|  |  | Activity 2.18 Renew and equip the fruit and cassava processing installations | X | X |  |  | IPEME, SDAEs, DPMAS | UNIDO |  | 100,000.00 |
|  |  | Activity 2.19 Organize training on cassava processing for local producers |  | X | X |  | IPEME, SDAEs | UNIDO |  | 25,000.00 |
|  |  | Activity 2.20 Undertake study tours for the establishment of demonstration centers |  | X | X |  | IPEME, SDAEs, DPMAS | UNIDO |  | 35,000.00 |
|  |  | Activity 2.21 Operationalize Boane’s agro-industry for cassava and cereal processing |  | X | X | X | IPEME, SDAEs, DPMAS | UNIDO |  | 70,000.00 |
|  |  | Activity 2.22 Develop modules and curricula on applying socio-cultural approach to gender, human rights and culture in the Faculty of Law at the Eduardo Mondlane University | X |  |  |  | Faculty of Law/UEM | UNESCO |  | 10.000,00 |
|  |  | Activity 2.23 Train teachers on applying socio-cultural approach to gender, human rights and culture in the Faculty of Law atf the Eduardo Mondlane University. | X | X |  |  | Faculty of Law/UEM | UNESCO |  | 20.000,00 |
|  |  | Activity 2.24 Support the Faculty of Law on the implementation, monitoring and evaluation of the projects that have been initiated | X | X | X | X | Faculty of Law/UEM | UNESCO |  | 30.000,00 |
|  |  | Activity 2.25 Disseminate the results and recommendations of the monitoring & evaluation undertaken in (2.24) |  |  |  | X | Faculty of Law/UEM | UNESCO |  | 5.000,00 |
|  |  | Divulgar os resultados e recomendações |  |  |  | x | UNESCO | 5,000 | 5,000 (One fund) |
| MONITORING INDICATORS | BASE TARGET | PLANNED ACTIVITIES | TIMEFRAME | Implementing partners | PLANNED BUDGET |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Financial Source | Budget/ Contributions/ Description | Amount in US |
| OUTCOME 3: Rule of law, access to justice and penal reforms improved, within the domain of violence against women, with an emphasis on public and human security Output 3: National capacity of local authorities and civil society organizations to effectively address the issues of public security, including gender based violence, strengthened |
| (10) Mechanism for victims of violence integrated care approved (11) Communication strategy for dissemination of the Law on Domestic Violence approved (12) Number of police officers trained on domestic violence (13) Number of violence against women cases attended / solved by the Ministry of Interior (Domestic Violence Section in the Police stations and Gabinetes de Atendimento) (14) Number of persons trained on the Law Against Domestic Violence (15) Number of female victims implementing income generation activities (16) Number of men trained and sensitized in gender and violence issues. | 1 1 120 13,583 10,000 (2009) 900 115 70 150 | Activity 3.1 Strengthen ministerial capacity to operationalize the gender strategy with an emphasis on prevention and combating violence against women (including child abuse): ● MINED ● MMAS ● MISAU | X | X | X | X | MINED MMAS Civil Society MISAU | UNICEF WHO |  | 45.000,00 35,000.00 |
|  |  | Activity 3.2 Provide capacity building on the use of gender appropriate legislation toolkit for institutions dealing with customary law in relation to violence. | X | X |  |  | WILSA | UNESCO |  | 35,000.00 |
|  |  | Activity 3.3 Provide support to journalists in community radios on the adaptation of the legislative package and its use for dissemination purposes | X | X | X | X | MULEIDE, AMCJ (Nampula), community leaders | UNESCO |  | 35,000.00 |
|  |  | Activity 3.4 Strengthen the interventions on advocacy and dissemination for the end of violence against women and children: ● Advocacy by radio ● Strategy for religious groups ● Campaign through the media on “Zero Tolerance” against violence and sexual abuse against girls ● Campaign on “Africa Unite” for the end of violence against women and girls ● Production of modules on the PNPCVM and the Law and train the provincial and district dissemination team ● Operationalize the course on gender based violence ● Dissemination of the Law against Domestic Violence and PNPCVM according to the Communication Strategy and train MINT on its monitoring role (policy officers and material) ● Undertake the campaign on “16 days against violence perpetrated on women” ● Men to men campaign against violence perpetrated on women – Support the process of providing men to men advice to the perpetrators of this violence ● Production of TV and radio spots suitable for handicapped women | X | X | X | X | MINED MINT MIJUS FORCOM Mozambique Radio ICS, Conselho Cristão and Islâmico, Fórum Mulher, MINDEF, NAFEZA, Dept of Sociology, FORCOM, CMCs | UNICEF UNIFEM UNFPA PNUD UNESCO |  | 125.000,00 85,000.00 80,000.00 25,000.00 30,000.00 |
|  |  | Activity 3.5 Evaluate and disseminate the results of the pilots (act.3.2 and 3.3) on the application of the socio cultural approach in solving the problems of gender based violence | X | X | X |  | Consultant / UNESCO | UNESCO |  | 40,000.00 |
|  |  | Activity 3.6 Advocate for the inclusion of the course on Customary Law in the faculty of Law | X | X | X |  | Faculty of Law at UEM | UNESCO |  | 30,000.00 |
|  |  | Activity 3.7 Define the flowchart for the multi-lateral “Integrated Assistance” for children victims of violence, sexual abuse, and exploitation | X | X | X | X | MMAS MINT MIJUS MISAU MINED | UNICEF / WHO |  | 5.000,00 |
|  |  | Activity 3.8 Support the functioning of more than 200 police assistance centersforo women and children victims of violence to ensure assistance in cases of abuse, violence and exploitation through: Construction / rehabilitation of centres from 3 provinces (Pemba, Inhambane and Nampula), and in 1 Child Friendly District (Angoche) Inclusion of a module on “Assisting women and children victims of violence” in the Escola Prática de Matalane - 2,400 police officers per year and training other focus groups within the PRM Expansion of statistical data collection and analysis | X | X | X | X | MINT MMAS | UNICEF UNDP |  | 100.000,00 20,000.00 |
|  |  | Activity 3.9 Develop the mechanisms to establish “free charge” legal assistance services for women and children victims of violence in the “Gabinetes de Atendimento” of the police offices and in women’s associations: Specific training on child’s rights and violence against children Disseminate and promote the services of the IPAJ Allocate IPAJ volunteers to the PRM’s services of women and child assistance (police stations, “Gabinetes de Atendimento, central hospitals) Support women’s associations working on legal assistance to women, including psychological support Recycle paralegals and train activists Build capacity of forensic doctors in their legal and judicial support to women and children victims of violence at hospital level Define the mechanisms to follow up the victims | X | X | X | X | MINT Instituto de Patrocínio e Assistência Jurídica (IPAJ) Faculdades de Direito Fórum Mulher, ASOMUDE, MULEIDE, AMUDEIA, NAFEZA, DPMAS MISAU, HCM, DPS | UNICEF UNFPA WHO |  | 100.000,00 15,000.00 55,000.00 |
|  |  | Activity 3.10 Strengthen the capacity of the Ministry of Health to respond to cases of violence and sexual abuse against women and children, including screening, legal medicine expertise, and clinical care (physical and mental): Print and disseminate the Strategic Plan on Trauma & Violence Prevention and Control 2011-2015 Train “occasional experts” in legal medicine, accredited by MIJUS ( 3 months Feb.- April 2011); Strengthen the Center for Child Psychological Rehabilitation - CERPIJ Provide capacity building to the basic health staff in identifying and providing medical support to the victims Strengthen the community psycho-therapy programmes Print information forms and do the follow up of cases in gynecology and pediatric urgency services | X | X | X | X | MISAU Faculty of Medicine (UEM) | UNICEF WHO |  | 190.000,00 70,000.00 |
|  |  | Activity 3.11 Support the Trauma / Violence Research and Training Unit of the Faculty of Medicine in strengthening the “Teach VIP on MPH” and doing community research on violence against women | X | X | X | X | Faculty of medicine | OMS |  | 50.000,00 |
|  |  | Activity 3.12 Carry out the evaluation and mapping of the interventions and support services on women victims of violence available in the country |  | X | X | X | DNM/DPMAS | UNIFEM UNDP |  | 15.000,00 30,000.00 |
|  |  | Activity 3.13 Support Women Victims Assistance Centers , ensuring experience exchange among them | X |  |  |  | NHAMAI / LeMusica | UNIFEM |  | 70.000,00 |
|  |  | Activity 3.14 Finalize the annotation and publication of the Law on Domestic Violence Against Women and the Family Law | X | X | X | X | Fórum Mulher | FNUAP |  | 5,000.00 |
|  |  | Activity 3.15 Strengthen institutionally the services of legal medicine to respond to the victims integrated assistance services in Beira and Nampula |  | X | X | X | MISAU HCM | WHO |  | 55.000,00 |
|  |  | Activity 3.16 Develop a module on identification, diagnosis treatment, and follow up of the victims of violence in the ISCISA curricula |  | X | X |  | MISAU ISCISA | WHO |  | 25.000,00 |
|  |  | Activity 3.17 Undertake the annual trainer’s meeting on the Law on Domestic Violence Against Women |  |  | X |  | DNM | UNDP |  | 15.000,00 |
|  |  | Activity 3.18 Undertake actions of joint coordination, monitoring and evaluation | X | X | X | X | UNFPA PNUD | UNFPA UNDP |  | *10.000,00 **60,000.00 |
|  |  | Activity 3.19 Publish the announcement and contract the consultant to undertake the evaluation of the project |  | X |  |  |  | UNDP |  |  |
| TOTAL PLANNNED | Source A: Agency and other resource contributions | US$2,284,509.3 |
|  | Source B: Deficit | US$1,349,226.7 |
|  | Total Planned: US | US$3,781,435.0 |

Abbreviations

| ASSOTSI – Association of the Informal Sector’s Operators & Employees CBO – Community based organization CCT – Consultative Commission on Labor CDSN – Start & Develop Your Business (business management tool) CDAM – District Councils for Women Advancement CeCaGe – Center of Gender Studies and Coordination (at the Eduardo Mondlane University) CEDARTE – Center for Art Craft Research and Development CEDAW – Convention on Elimination of All Forms of Discrimination Against Women CNAM- National Council for Women Advancement CPAM – Province Council for Women Advancement COMUTRA – National Committee of Female Workers Consilmo – National Confederation of Free and Independent Trade Unions of Mozambique CSOs – Civil Society Organizations CSW – Commission on the Status of Women CTA – Mozambique’s Confederation of the Economic Associations CTNAM – Technical Council for Women’s Advancement DINEA- National Directorate of Agricultural Extension DNM – National Directorate of Women DPA- Provincial Directorate of Agriculture DPMAS- Provincial Directorate of Women & Social Affairs DUAT – Rights on Land Use FAMOs – Verification and methods for small enterprises managed by women and men FM- Fórum Mulher (Women Fora) FFS – Farmer Field Schools GB – Gender Budget GBV – Gender Based Violence Get Ahead – Women and Entrepreneurship (business management tool) | IEC – Information, Education & Communication INEFP – National Institute of Employment and Professional Training INSS – National Institute for Social Security IOM – International Organization for Migration ISAP- Higher Institute on Public Administration IPEME – Institute for Small & Medium Scale Enterprise’s Promotion JP – Joint Programme MDG – Millennium Development Goals MIJUS- Ministry of Justice MINED- Ministry of Education MINT- Ministry of Interior MISAU- Ministry of Health MMAS- Ministry of Women & Social Affairs MTC – Ministry of Transport & Communication MULEIDE – Women, Law and Development (NGO) OTM – Mozambican Worker’s Organization PNPCVM – National Plan on Prevention & Combat of Violence Against Women PSRE – Provincial Services of Rural extension PRSP – Poverty Reduction Strategy Paper RM- Mozambique Radio SDAE – District Services of Economic Activities SDSMAS- District Services of Health, Women and Social Affairs TVET/NFE – Technical Vocational Education Training – Non Formal Education TECH VIP on MPH - Technical Vocational Education Training – Non Formal Education VAW – Violence Against Women WEA - Women Entrepreneurship Association WFP – World Food Programme |
| --- | --- |

2011 Annual Plan Budget

|  | Planned Budget | Agency Resources (2011) | One Fund Balance 2010 | Final Deficit |
| --- | --- | --- | --- | --- |
| UNDP | 630,000.0 | 100,000.0 | 150,000.0 | 342,000.0 |
| UNIFEM | 270,000.0 | 100,000.00 | 248,845.9 | *** |
| UNFPA | 506,000.0 | 200,000.0 | 40,000.0 | 239,400.0 |
| UNESCO | 445,000.0 | 90,000.0 | 274,353.9 | 38,646.1 |
| UNICEF | 565,000.0 | 425,000.0 | 24,257.0 | 104,043.0 |
| ILO | 190,000.0 | 90,000.0 |  | 100,000.0 |
| FAO | 382,435.0 |  | 218,536.0 | 165,000.0 |
| UNIDO | 468,000.0 |  | 295,962.0 | 172,038.0 |
| WHO | 325,000.0 | 30,000.0 | 76,400.5 | 188,099.5 |
| Total | 3,781,435.0 | 1,035,000.0 | 1,328,355.3 | 1,349,226.7 |

*10.000 USD correspond to Programme coordination activities

** 60.000 USD correspond to the Coordinator of the Programme                                                               *** Additional Funds to be mobilized by the Agency (2011 Agency resources)