### Future Work Plan

In 2011 activities under the Civil Society Joint Programme will continue to strengthen the capacity of civil society organisations through a number of training initiatives. The aim of these initiatives will be to enhance civil society participation in the socio-economic development of the country in the following areas:

- Advocacy;

- Monitoring and Evaluation;

- Knowledge Management;

- Participation; and

- Result Based Management.

These will be complemented by agency specific training activities.

The Joint Civil Society Programme will provide the necessary technical and financial support to carry out various advocacy and mobilization initiatives for children, young people, workers and women and increasingly include them in national policy discussions. At the coordination level, the Joint Programme will strive to coordinate more effectively at the implementation level and conduct peer monitoring visits to collect and share lessons learned and experiences.

# UN Mozambique

Building Capacity of Civil Society Organizations, Including Communication for Empowerment

Joint Programme

2011 Annual Work Plan

UNDAF CP Outcome(s): UNDAF OUTCOME 1.6 Civil society organizations and structures (including traditional authorities) strengthened and involved in the development agenda at national and decentralised level

UNDAF CP Output(s): UNDAF OUTPUT 1.6.2 Capacity of CSOs, CBOs, volunteer organisations, and particularly women-led organizations, strengthened to implement, manage and report on project execution, to build partnerships and to become fully-fledged development agents (UNDP, FAO, UNICEF, UNESCO, ILO) Indicator: Number of capacity development programmes developed and implemented for selected CSOs (Target: at least 1 CD programme implemented in Nampula, Cabo Delgado and Gaza) Number of communities with bank accounts (Target: 30 communities in at least three provinces) Baseline: No comprehensive capacity development programme for CSOs being implemented Means of verification: Evaluation Report of the CD programme for CSOs Risks and assumptions: Willingness of NGOs and continuing commitment & support at national & provincial levels

| Specific Outputs | Planned Activities | TIMEFRAME (Quarter) | Imple-menting Partners |  | PLANNED BUDGET |
| --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Planned Amount | Allocated Amount | Funding Gap | Source of Funds |
| JP Outcome 1: ENHANCED ADVOCACY, POLICY ANALYSIS AND PARTNERSHIPS |
| JP Output 1.1. Advocacy approaches seek to leverage knowledge and resources for women and children and quality education for all as a human right | 1.1.1. Strengthen provincial CSO networks in at least 6 provinces to monitor the effective implementation of the CRC recommendations and the Children's Act | x | x | x | x | UNICEF FDC | 50,000 | 12,000 | 38,000 | One Fund |
|  | 1.1.2 support to catalytic CSO projects on social mobilization and communication for empowerment efforts to advocate for and raise community awareness of women’s rights | x | x | x | x | UN WOMEN | 60.000 | 10.000 | 50.000 | RR |
|  | 1.1.3 Advocacy and awareness raising on social issues and child rights through outreach activities, dissemination of information and participation in public fora | x | x | x | x | UNICEF MISA | 21,250 | 0 | 21,250 |  |
|  | 1.1.4 Monitoring and analysis of the news coverage on children’s issues, and publication and dissemination of one annual report | x | x | x | x | UNICEF MISA | 21,250 | 0 | 21,250 |  |
|  | 1.1.5 Support advocacy activities for increased government support for foster caregivers / substitute families ( eg. financial, medical and educational support). | x | x | x | x | UNICEF Kubatsirana | 25,000 | 0 | 25,000 |  |
|  | 1.1.6 Organize consultations for discussions and validation of the radio/TV broadcasting law | x | x | x | x | UNESCO UNDP MISA FORCOM ICS GAB INFO | 60,000 | 60,000 | 0000 | One fund |
|  | 1.1.7 Design and dissemination of child friendly games for learning and practicing child rights in schools | x | x | x | x | UNESCO MEPT | 80,000 | 50,000 | 30,000 | One Fund |
|  | 1.1.8 Production of a guide for orientation and counselling of the girl child to be used by teachers, and in particular women teachers, for the protection of the rights of girls in schools | x | x | x | x | UNESCO ONP MEPT | 80,000 | 50,000 | 30,000 | One Fund |
|  | 1.1.9 Provide technical and financial support for the institutional capacity building of UEM Research Centres and the development and publication of a national Scientific Research Journal. | x | x | x | x | UNDP UEM | 165,000 | 50,000 | 115,000 |  |
|  | 1.1.10 Support to the Moot Court at the Faculty of Law of UEM | x | x | x | x | UNDP UEM | 45,000 | 0,00 | 45,000 |  |
|  | 1.1.11 Training and advocacy on gender issues, gender sensitive reporting and women’s rights with media houses, journalism students and community media | x | x | x | x | UN WOMEN FORCOM Women’s Media Association Genderlinks UEM | 129.837 | 75.757 4.785 | 49.295 | One Fund RR |
| JP Output 1.2. Child-friendly media networks are established and functioning and education sector annual award for outstanding articles in newspapers, radio and TV attributed to the best media professional | 1.2.1. At least 40% of national and provincial journalists in all provinces have basic understanding of and are publishing articles on child rights | x | x | x | x | UNICEF MISA | 127,000 | 89,000 21,250 | 16,740 | RR One Fund |
|  | 1.2.2 Support Radio Mozambique children’s clubs and weekly production and dissemination of child-to-child radio programmes through 11 RM delegations, including on the job training of 100 new producers in 11 provinces . | x | x | x | x | UNICEF RM: | 80,000,000 | 80,000 | 0 | RR |
|  | 1.2.3 Support the production of weekly child-to-child TV programmes on key themes, involving duty bearers and service providers in inter-generational debates, focusing on 4 TVM delegations in Maputo City, Sofala, Zambézia and Nampula provinces. | x | x | x | x | UNICEF TVM: | 65,000 | 65,000 | 0 | RR |
|  | 1.2.4 70 community radios and 11 radio stations in all provinces producing and broadcasting programmes and debates on child rights | x | x | x | x | UNICEF RM: UNICEF:DN | 83,000 | 30,000000 | 53,000 | RR |
|  | 1.2.5 Organize and conduct training workshops on “education makes news” and child rights involving teachers and journalists from the central and northern regions | x | x | x | x | UNESCO MPET ONP | 75,000 | 75,000 | 0 | One Fund |
|  | 1.2.6 Award an annual prize to recognise the best work on “education makes news” in support of the EFA activities and MDGs | x | x | x | x | UNESCO MEPT MISA | 5,000 | 5,000 | 0000 | One Fund |
|  | 1.2.7 Build the capacity of CMCs to report on Child Rights | x | x | x | x | UNESCO CMCs AFRICARE | 130,000 | 40,000 | 90,000 | One Fund |
| JP Output 1.3 Institutional linkages and networks involving workers and employers’ organizations strengthened and workers’ rights respected in the workplace | 1.3.1 Reinforce the efforts of civil society organizations for people with disabilities to promote the rights of children and women with disabilities | x | x | x | x | ILO GAMA ADEMO | 30,000 | 10,000 | 20,000 | RR |
|  | 1.3.2. Work with domestic workers’ organizations by reinforcing their capability on the ground to promote their rights and guarantee work place hygiene | x | x | x | x | ILO OTM & AMUEDO | 60.000 | 20,000 | 40,000 | RR |
|  | 1.3.3 Support for the dissemination of international conventions on work related issues ( hygiene at the work place, maternity conventions ) | x | x | x | x | ILO AMAJOR, Aro Mocambique, COMUT, COMUTRA & ASSOTSI | 80,000 | 10,000 | 70,000 | RR |
| JP Output 1.4 Employment opportunities for youth, women and persons with disabilities created. | 1.4.1. Build the capacity of youth organizations to advocate for a more enabling business environment that respects the rights of employers and workers Further the consolidation of innovative ways for the associations to implement solution-focused approaches | x | x | x | x | ILO CTA UEM- Centro de Estudos, NUMASECOSIDA | 60,000 | 20,000 | 40,000 | RR |
| JP Output 1.5 Research, information and monitoring systems that facilitate improved targeting and support to children, women, young people and PWDs are in place and functioning | 1.5.1 Produce and disseminate budget briefs related to 2011 State Budget Proposal highlighting the correlation between the allocation of resources per province and population size, and the levels of women and child poverty and disparities | x | x | x | x | UNICEF FDC/ Policy Forum | 40,000 | 0.00 | 0 |  |
|  | 1.5.2 Monitoring learning achievements on skills and competencies related to child rights in schools | x | x | x | x | UNESCO ONP | 120,000 | 40,000 | 80,000 | One fund |
| JP Output 1.6 Regulatory framework for civil society reviewed | 1.6.1 Draft a Code of Conduct for CSOs and disseminate | X | x | X |  | UNDP DFC + CSOs | 5,000 | 0,00 | 5,000 |  |
|  | 1.6.2 Establish 3 CSO Platforms at administrative post level in Ancuabe | x | x | x |  | UNDP FDC + CSOs | 5,000 | 0,00 | 5,000 |  |
|  | 1.6.3 Training for 25 members of CSO Platform in Ancuabe. | x | x | x |  | UNDP FDC + CSOs | 5,000 | 0,00 | 5,000 |  |
|  | 1.6.4 Monitor District Budget at District level (Ancuabe) | x | x | x |  | UNDP FDC + CSOs UNICEF | 5,000 | 0,00 | 5,000 |  |
| Sub-total |  |  |  |  |  |  | 1,582,500 | 707,250 | 815,250 |  |
| JP outcome 2: STRENGTHENED TECHNICAL AND MANAGERIAL CAPACITIES OF CSOs |
| JP Output 2.1 Planning, implementing and monitoring skills of CSOs enhanced for managing their projects / programmes | 2.1.1 Enhance the institutional capacity of 250 Civil Society Organizations to actively engage in the promotion and protection of child rights, including HIV prevention (HRBAP, RBM, M&E and Knowledge Management) | x | x | x | x | UNICEF FDC | 100,000 | 20,000 | 80,000 | One Fund |
|  | 2.1.2 Strengthen thecapacity of CSOs at national level on Gender Sensitive Results Based Management and Programming including Gender Sensitive M&E | x | x | x | x | UN WOMEN | 50.000 | 50.000 | 0 | One Fund |
|  | 2.1.3 Strengthen the capacity of FORCOM and its three regional nuclei to train staff from 30 community radios,on priority themes addressing Child Rights, ACSD, Prevention of Violence Against Children and HIV prevention, and associated radio production skills, including regular monitoring of the activities | x | x | x | x | UNICEF FORCOM: | 280,000 | 141,000 26,100 | 112,900 | RR One fund |
|  | 2.1.4 Strengthen the capacities of CSOs at provincial and district level to support communities to identify OVC and ensure their access to quality basic services, through the establishment of referral systems in 7 provinces | x | x | x | x | UNICEF: Nivenyee Kaeria Kewa ChigwirizianKhulupira Rudo-Kubatana Kuvumbana | 175,000 | 140,000 | 35,000 | RR |
|  | 2.1.5 Strengthen the nstitutional capacity of education CSOs on monitoring learning achievements, design and use of learning assessment tools | x | x | x | x | UNESCO MPET, PROMUGE, ONP, AMJE | 108,322 | 103.300 | 5,022 | One Fund |
|  | 2.1.6 Capacity building for communities in three districts and civil society representatives in Consultative Councils in: planning, monitoring and evaluating public programs and policies budget monitoring advocacy organization for participation by various interest groups | x | x | x | x | UNDPFDC, FONGA | 10,000 | 5,000 | 5,000 | RR |
|  | Is 2.1.7 missing?? |  |  |  |  |  |  |  |  |  |
|  | 2.1.7 Organize training for key CSOs partners in gender advocacy related policy issues at local level | x | x | x | x | UN WOMEN AMOPROC | 9,822.00 | 9,822.00 | 0 | One Fund |
|  | 2.1.8 Support training of one member of SDEJT and new teachers and students in interactive community theatre techniques at ZIP level and strengthen theatre activities in all 7 CFS districts, including support to radio drama production for radio stations | x | x | x | x | UNICEF GTO: Alvim Cossa UNICEF: MCM | 37,000 | 0 | 37,000 |  |
|  | 2.1.9 Strengthen the capacity of FORCOM and its three regional nuclei to train staff from 30 community radios on priority themes addressing Child Rights, ACSD, Prevention of Violence Against Children and HIV prevention, and associated radio production skills, including regular monitoring of the activities | x | x | x | x | UNICEF FORCOM: Luísa Banze UNICEF: DN | 83,000 | 30,000 | 53,000 | RR |
|  | 2.1.10 Organize training on M&E for CSOs at district level (Citizen Report Cards and PETs) | x | x | x | x | UNDP GMD G20 | 13,000 | 0,00 | 13,000 |  |
|  | 2.1.11 Support 2 provincial CPJ PARPA briefings for 75 youth associations, and ensure and monitor their effective participation in development observatories, consultative committees and school councils in 8 provinces. | x | x | x | x | UNICEF CNJ: | 90,000 | 70,000 | 10,000 | RR |
|  | 2.1.12 Undertake an assessment of ICS capacity (HR, equipment and capacity of production of audiovisual material) | x | x | x | x | UNICEF ICS: | 30,000 | 0 | 30,000 |  |
|  | 2.1.13 Court officers trained on child appropriate justice services for child victims, witnesses and offenders in 4 children’s sections and 7 civil sections as stated in international Conventions | x | x | x | x | UNICEF CFJJ Faculty of Law - UEMCarla | 50,000 | 0 | 50,000 |  |
|  | 2.1.14 Support for dissemination of international conventions on work related issues | x | x | x | x | ILO CONSILMO, OTM, ADEMO, ACTIVA, AMEM & FEMME | 80,000 | 20,000 | 60,000 | RR |
| Sub-total |  |  |  |  |  |  | 1,259,779 | 710,214 | 549,565 |  |
| JP Outcome 3: ENHANCED CAPACITY OF CSOs AT LOCAL LEVEL TO PARTICIPATE IN DEVELOPMENT PROCESSES |
| JP Output 3.1 Communities, the private sector and CSOs have increased awareness of the right to participate in development processes and increased capacity to actively participate in and contribute to the development planning, implementation, monitoring and evaluation processes at the local and provincial levels through recognized mechanisms like PO/IPCC. | 3.1.1 Provincial Child Parliament functioning and reporting to the National Parliament and Provincial Council for Children’s Rights | x | x | x | x | UNICEF CNAC PNAC | 20,000 | 0 | 20,000 |  |
|  | 3.1.3 Enhance the capacity of civil society organisations and communities in three districts to conduct budget tracking and monitoring (through community score cards) in thematic areas relevant to child rights and gender equality, such aseducation and child health | x | x | x | x | UNICEF CESC: | 100,000. | 45,000.00 | 55,000 | One Fund |
|  | 3.1.4 70 community radios and 11 radio stations in all provinces producing and broadcasting programmes and debates on child rights | x | x | x | x | UNICEF FORCOM N’weti RM | 330,000 | 180,000 25,000 | 125,000 | RR One Fund |
|  | 3.1.5 Training of at least 1,200 children and young people on child-to-child broadcasting in CMCs in 11 provinces | x | x | x | x | UNESCO AFRICARE Moçambique | 80,000 | 00000 | 80,000 |  |
|  | 3.1.6 At least 200 children and young people in all provinces participating in local decision-making fora (school councils, community committees and poverty observatories) | x | x | x | x | UNICEF | 35,000 | 20,000 | 15,000 | RR |
|  | 3.1.7 Support the production and dissemination of bi-monthly child-to-child radio programmes through 50 community radios within the 75 priority districts, including intensified programming in the 7 CFS districts | x | x | x | x | UNICEF FORCOM: | 85,000 | 50,000 | 35,000 | One Fund |
|  | 3.1.8 Provide ad hoc technical assistance for CSOs / GMD Provincial Nuclei; Participate in 9 PO/DO and IPCCS; Provide Logistics support to Provincial Nuclei; (UNICEF is also supporting the PO/DO - there is room for collaboration) | x | x | x | x | UNDP GMD SNV G20 | 85,000 | 0,00 | 85,000 |  |
|  | 3.1.9 Support publication of critical policy analysis documents: public plans and development policies, including aid effectiveness (follow-up to Accra); external assistance and public debt and audiovisual materials | x | x | x | x | UNDP GMD SNV G20 | 20,000 | 0,00 | 20,000 |  |
|  | 3.1.10 Organize 4 dialogue sessions with inter-parliamentary provincial commissions (Gaza, Inhambane, Nampula, Tete and Niassa) | X | X | X |  | UNDP GMD G20 | 42,967 | 0,00 | 42,967 |  |
|  | 3.1. 11 Establish a system of data collection and processing | X | X |  |  | UNDP GMD G20 | 13,731 | 0,00 | 13,731 |  |
|  | 3.1.12 Implement a pilot project in 3 districts on M&E (Monitoring Score cards) |  | X | X | X | UNDP GMD G20 | 13,000 | 0,00 | 13,000 |  |
|  | 3.1.13 Support the development of the National Governance Report | x | x | x | x | UNDP GMD G20 | 5,000 | 0,00 | 5,000 |  |
| JP Output 3.2 Effectiveness of communication for empowerment and social mobilization / community participation for the realization of the rights of the most vulnerable enhanced. | 3.2.1 Support bi-annual mobile unit activities in 221 localities in selected priority districts and strengthen counselling and testing services. | x | x | x | x | UNICEF ICS: | 385,000 | 385,000 |  | RR |
|  | 3.2.2 Support roll out of the single, harmonized framework and curriculum for ONE CLUB (school and radio), harmonizing the Os Bradas approach with Pacote Basico’s life skills content through three Regional TOT (PLWHAs, PB and MINED Gender focal points), and regular support for scaling club interventions up to 400 schools in 7 CFS districts (in collaboration with Education and Child Protection). | x | x | x | x | UNICEF N’weti: RENSIDA: MEC: RM: FORCOM: UNICEF: OB / MCM | 50,000 | 0 | 50,000 |  |
|  | 3.2.3 Support the functioning of 1,100 listeners groups, with focused attention on 7 CFS, to reinforce the link between school and radio clubs and ensure regular cross-fertilization and expansion of radio programme impact. | x | x | x | x | UNICEF N’weti: RENSIDA: MINED: RM: FORCOM: UNICEF: OB | 50,000 | 0 | 50,000 |  |
|  | 3.2.4 Capacity building of the CBOs linked to CMCs in communication for child rights, particularly on planning aspects | x | x | x | x | UNESCO AMJE , PROMUGE FORCOM AMUDEIA | 60,000 | 60,000 | 0 | One Fund |
| JP Output 3.3. Community-based surveillance systems to prevent violence, abuse and exploitation are established and functioning | 3.3.1 Support intensification of the Zero Tolerance on Violence and Sexual Abuse Against children community and school-level C4D activities through existing social mobilisation partners (activists, radio, theatre, clubs) and school councils in 75 districts focusing on sexual abuse against children, including the provision of necessary IEC materials (eg. radio content targeting youth; developing community discussion guidelines for use by mobile units and theatre groups etc) | x | x | x | x | UNICEF MINED: RM: ICS: FORCOM: | 90,000 | 0 | 90,000 |  |
|  | 2.3.2 Use of community networks on alternative measures for children in conflict with the law through establishment of community service management system | x | x | x | x | UNICEF AMMCJ OREC | 70,000 | 0 | 70,000 |  |
|  | 3.3.3 Support the production of youth-to-youth radio programmes and weekly debates on 11 RM stations, with focused attention on Violence Against Children and Stigma & Discrimination and the participation of CSOs and service providers (MINT, MINED, MMAS, MINJUS) | x | x | x | x | UNICEF RM: | 20,000 | 0 | 20,000 |  |
|  | 3.3.4 Support the production of community radio programmes and weekly debates on ACSD, Prevention of Violence Against Children, and HIV prevention(early pregnancy, early debut, inter-generational sex, MCP & stigma), with the participation of local decision-makers and community members in 40 community radios stations, in 75 priority districts (6750*20 radio*12 months; 6750*20 radios * 10 months) | x | x | x | x | UNICEF FORCOM: | 50,000 | 0 | 50,000 |  |
|  | 3.3.5 Support tri-annual community theatre activities in 190 localities, including production of radio drama for community radios, with special attention to improving coordination with Health sectors. | x | x | x | x | UNICEF GTO: | 123,000 | 71,000 10,000 | 42,000 | RR One Fund |
|  | 3.3.6. Establish community level reference groups where members of government sectors, local associations and organisations, students, teachers, school directors, parents and community leaders are given the capacity and come together for the monitoring and prevention of violence, abuse and exploitation and for assisting women and children victims of violence | x | x | x | x | UN WOMEN ICS MEC |  |  |  |  |
| Sub-total |  |  |  |  |  |  | 1,777,698 | 846,000 | 931,698 |  |
| GRAND TOTAL |  |  |  |  |  |  | 4,619,977 | 2,263,464 | 2,296,513 | RR/One fund |

Summary of the programme budget per Agency showing the respective  funding gaps

|  | Planned | Allocated | Gap | Comment |
| --- | --- | --- | --- | --- |
| UNICEF | 2,815,500.00 | 1,510,350.00 | 1,305,150.00 | All one fund allocations referred to in the table are the carry-over of one fund from 2010 |
| UNDP | 432,698.00 | 55,000.00 | 377,698.00 |  |
| UNESCO | 798,322.00 | 513,300.00 | 285,022.00 |  |
| UN WOMEN | 263,457.00 | 164,814.00 | 98,643.00 |  |
| ILO | 310,000.00 | 80,000.00 | 230,000.00 |  |
| Total | 4,619,977.00 | 2,323,464.00 | 2,296,513.00 |  |