**Angola**

|  |  |  |
| --- | --- | --- |
| **Programme Title:** | Children, Food Security and (Mal)Nutrition in Angola | |
| **Programme number & MDTF ref:** | MDGF-1997-I-AGO (67239) | |
| **Window:** | Children, Food Security & Nutrition | |
| **Approved Budget by NSC (US$):** | 4 million | |
| **Participating Organizations:** | UNICEF, WHO, IOM, FAO, UNDP | |
| **First Tranche transferred on:** | 14-Dec-2009 | |
| **ACTIVITIES Reported:** | |
| **Main Substantive Activities:** | |
| * Food security and nutrition strategy prepared and disseminated. * 88% children under 5 received one dose of vitamin A and 82 % children received albendazole. * More than 80% of the population have the access to full high impact interventions in 9 selected municipalities of Bie, Moxico and Cunene for revitalization. * Total of 4,166 severely acute malnourished children have been treated in 2010 both at community and facility based care unit using therapeutic feeding protocol in Bie, Moxico and Cunene. * 20 % vulnerable families assisted for food security. * Essential supplies distributed to municipal governments. * Training of trainers on food security and nutrition ongoing. | |
| **Problems and lessons learned:** | |
| * Ensuring a good understanding of the JP and promoting strong National and provincial ownership * High mortality rate of Severely malnourished children at Facility based care unit * Rapidly building the skills of providers for scaling up of planned interventions at the municipality level * Sustaining the commitments of the Provincial and municipality authorities * Promoting Community involvement and full participation * Building an effective health management information system to monitor and measure progress linked to the existing system * Coordination with government and Coordination within government | |
| **The programme reports relevant linkage to the UNDAF:** Yes | |
| **The programme has communications strategy in place**: No (There are several communication activities embedded on the programme) | |

CHARTS & FIGURES

As of 31 December 2010

