## all agencies
Annex A: Work Plan (Year II) - MDG Achievement Fund Culture - Bosnia and Herzegovina
|  |  | Expected BiH UNDAF Outcome 1: | Strengthened accountability and responsiveness of governments to pro-active citizens.
|  |  | Outcome 2: | Improved access to and quality of education, health and social protection services.
JP Outcome 1: Developed and implemented cultural policies and legal frameworks
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Source of Funds | Budget Description (Expenditure Account) |  | Remaining funds from Year I | Planned Budget Y II
[13 empty] | Total Amount | Total Amount
(List of Output & Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
1.1 | Improved policies & legal frameworks in culture and education sectors | [11 empty] | 216282.84 | 816454.9188
| Culture sector review in BiH (legislative, financial, infrastructure and human resource analysis) prepared. | 1.1.1. | Complete mapping of the culture sector and related industries using gender-sensitive approach to identify economic and social potentials and complete Culture Portal implementation by line ministries. |  |  |  |  | UNDP | MoCA | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 10497.12 | 18000
[9 empty] | MoCs |  | 1.2 | Personnel (staff, consultants, travel and training) | -23763.91 | 46189.98
| Publication on culture sector review prepared and printed. | [7 empty] | Statistical Agencies |  | 1.3 | Training of counterparts | 8897.63 | 0
| Culture participation survey finalised. | a. | Implement activities related to culture sector and related culture industries overview using gender-sensitive approach. | [7 empty] | 1.4 | Contracts | 37040.42 | 0
| Culture sector mapping methodology prepared and distributed to state and entity ministries with accompanying capacity development workshops to key stakeholders in government sector and culture institutions. | [9 empty] | 1.5 | Other direct costs | -1846.48 | 29000
[11 empty] | 2.0 | Indirect support costs 7% | 9639.03 | 6523.2986
Directory of culture sector prepared.
| Roadmap for cultural statistics prepared and new methodology introduced for the collection of cultural statistics in BiH. | b. | Improve cultural statistics and align methodology with EUROSTAT and NACE cultural industry classification. |  |  |  |  | UNDP | MoCA | MDG-F
MoCs
Report on gap analysis in statistical tracking for culture sector prepared.
Methodology for culture statistics adopted by the BiH Agency for Statistics and in a follow up phase bz Entity institutes for statistics.
Culture statistics collected and distributed to statistical institutes, state, entity and cantonal ministries.
|  | 1.1.2 | Assist programme stakeholders in policy development. |  |  |  |  | UNDP | MoCA, MOCs | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 13693.19 | 0
| - Joint Action Plan for the BiH Culture Strategy which sets priorities and identifies clear responsibilities between the 3 ministries finalised. | a. | Facilitate the production and implementation of the Action Plan based on National Cultural Policy Strategy through a participatory process and with inclusion of all relevant institutions. | [7 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 16537.38 | 208998
[11 empty] | 1.3 | Training of counterparts | 0 | 110000
[11 empty] | 1.4 | Contracts | 45068.25 | 24500
[11 empty] | 1.5 | Other direct costs | -1681.09 | 22653
| At least two consultation processes organised for Joint Action Plan for the BiH Culture Strategy and consulted with key stakeholders active on issues of gender, youth and social inclusion. | b. | Provide technical assistance to governmental Working Groups for incorporating cross-cutting issues: gender, youth, and social inclusion in the Action Plan for implementation of the National Cultural Policy Strategy. |  |  |  |  | UNDP | MoCA/ MoCs | MDG-F | 2.0 | Indirect support costs 7% | 15712.68 | 25630.57
| Joint action plan and other policy documents widely discussed with key civil society sector partners, universities and other stakeholders (at least two larger conferences with relevant stakeholders from civil society sector organised). | c. | Hold third-party-led consultations (study visits and exchange programmes) on cultural policy priorities and reporting procedures. |  |  |  |  | UNDP | Public Servants | MDG-F
Key government partners and representatives of culture industries introduced to best practices of cultural management in Spain (though study visit).
At least two cross-entity exchange programmes of municipal cultural products (tourist products, arts, performances) within BiH organised to mainstream cultural exchange activities among cities in BiH. (target group Sarajevo and Banja Luka and their exchange of promotional activities, i.e. 'Days of Banja Luka in Sarajevo'
| At least 2 conferences organized on cultural topics related to the programmes priorities of MDGF/ Action plan and linked to Advocacy and M&E additional funds (Government to provide selection of topics) | d. | Arrange conferences on specific priorities in the cultural sector |  |  |  |  | UNDP | MoCA | MDG-F
MoCs
Technical assistance activities supported as identified in the Action plan for implementation of Culture Strategy shall be prioritised by state, entity and cantonal ministries of culture by 31st of March 2010. Current priorities include:
A) Training in culture management of key stakeholders in culture institutions delivered (at least 10 participants in 2 day training ) B) Review of legal obstacles for public-private partnership in culture sector prepared and trainings for institutionalising PPP delivered (at least 10 participants in 2day training) C) Recommendations for promotion of young talented artists prepared based on the broader culture sector analysis (111). D) Two pilot studies of culture tourism potentials in two cities prepared (Mostar and Visegad). E) Analysis and recommendations for Institutes for protection of cultural and natural heritage (trainings in management of cultural assets, capacity development of the institutions and experiences from other countries) F) Analysis and recommendations for stimulus packages (tax-breaks and incentives) in culture sector (specially for culture industries)
| At least two technical trainings on monitoring and evaluation and on strategic planning provided to the inter-ministerial working groups for up to 10 participants. | e. | Provide technical assistance to sectoral Working Groups for developing and targeted implementation of selected priority areas in the Action plan for Culture Strategy |  |  |  |  | UNDP | MoCA | MDG-F
MoCs
| Culture portal roadmap implemented and used by relevant ministries. | f. | Support Sectoral working group in continuing development of the Culture portal concept and visibility improvements for all three ministries in presentation of the culture sector. |  |  |  |  | UNDP
Information-sharing platform developed and hosted under the Ministry of Civil Affairs (MoCA) domain.
| At least two targeted trainings on gender sensitivity and gender mainstreaming in the culture sector delivered to programme partners at central and local level (municipalities). | g. | Promote gender awareness through tailored trainings with policy makers, local stakeholders and media. |  |  |  |  | UNDP | MoCA | MDG-F
MoCs
| Joint action plan for Culture sector gender-mainstreamed in line with BiH gender law. | [7 empty] | Core Localities
Media
|  | 1.1.3 | Improving policies and their implementation to ensure access to quality multi-cultural education. |  |  |  |  | UNICEF | MoE, PI, PS in Core Localities | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 9300 | 29500
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | -119204.97 | 61800
[11 empty] | 1.3 | Training of counterparts | 0 | 40000
| Curricula research report submitted to relevant MoE | a. | Conduct studies and research on curricula and school environment and assist in implementation of recommendations. | [7 empty] | 1.4 | Contracts | 135250 | 38900
| Report on mapping teachers' competences in intercultural education completed | [9 empty] | 1.5 | Other direct costs | 25920.95 | 33940.602
| Trainings for school staff of PS of 10 selected municipalities to acquire knowledge and skills in principles and practices of intercultural teaching provided | [9 empty] | 2.0 | Indirect support costs 7% | 0 | 14289.8421
| Trainings for teaching staff at Pedagogical Academies in developing appropriate pedagogies; writing learning objectives; writing learning outcomes; provided | b. | Facilitate the development of a multi-cultural ethics code for teachers, schools, pupils and parents and engage in exchange of experiences. |  |  |  |  | UNICEF | MoE, Pedagogical Academies | MDG-F
|  | 1.1.4 | Supporting the preparation of policy documents, reporting mechanisms and legal frameworks (Capacity development). |  |  |  |  | UNESCO | MoE | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 16224 | 0
| Further development of system for implementation monitoring of international conventions related to culture to which BiH is a signatory. Support to participation to all UNESCO conferences, round tables etc. related to UNESCOs conventions linked to 311a | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 0 | 9774
[11 empty] | 1.3 | Training of counterparts | 0
|  | a. | Facilitate the harmonisation of legal frameworks and methods of reporting with existing international conventions. | [7 empty] | 1.4 | Contracts | 6300 | 16000
| Finalised and distributed publication with all conventions to which BiH is a signatory produced. | [9 empty] | 1.5 | Other direct costs | 4581 | 1299.63
[11 empty] | 2.0 | Indirect support costs 7% | 1897 | 1895.15
| Joint action with UNDP / see UNDP component, section 111 a and b | b. | Provide technical support to the development of Action plan based on National Cultural Policy Strategy in BiH through a participatory process and with inclusion of all relevant institutions. |  |  |  |  | UNESCO | MoE | MDG-F
| 30 participants (local decision makers from core localities, additional selected municipalities and Ministries at state and entity level) trained in cultural diversity focusing on intercultural understanding and mediation. | c. | Train major stakeholders on cultural diversity, policies and legal frameworks |  |  |  |  | UNESCO | Policy makers | MDG-F
CSOs
1.2 | Strengthened capacities of State and Entity-level governments in monitoring and evaluation of cultural development
|  | 1.2.1 | Providing monitoring and evaluation training activities to relevant government agencies. | [7 empty] | 1.1 | Supplies, commodities, equipment and transport | 4000 | 0
| Specific cultural indicators with the M&E working group developed for the monitoring of the Culture Strategy and Action Plan. | [6 empty] | UNDP | MoCA | MDG-F | 1.2 | Personnel (staff, consultants, travel and training) | 1536.38 | 24545
|  | a. | Facilitate the harmonization of the collection of cultural data and ensure gender-sensitive collection of cultural data. | [5 empty] | MoCs |  | 1.3 | Training of counterparts |  | 12500
[11 empty] | 1.4 | Contracts |  | 0
[11 empty] | 1.5 | Other direct costs |  | 0
[11 empty] | 2.0 | Indirect support costs 7% | 684.26 | 2593.15
| Representatives of state and line entity ministries trained in M&E and participated in on site monitoring of local level MDG-F projects - at least 1 visit per each of selected core localities and at least 1 visit per each NGO grantee per M&E working group member. | b. | Technical assistance to establishment of functioning Working Groups for improved Monitoring and Evaluation mechanisms in the key government counterpart ministries (state and entity level). |  |  |  |  | UNDP | MoCA | MDG-F
MoCs
Harmonised monitoring forms prepared for line ministries (1 set for municipalities, 1 set for NGOs and 1 set of reports from municipalities to Ministry-M&E Units.
Joint Manual on monitoring Standard Operating Procedures prepared for line ministries.
| - Cultural indicators for monitoring childhood cultural education performance versus international achievements developed | 1.2.2 | Developing a system to monitor implementation of improved educational policies |  |  |  |  | UNICEF |  |  | 1.1 | Supplies, commodities, equipment and transport | 0 | 0
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 0 | 0
|  | a. | Technical assistance to the Agency for Pre-primary, Primary and Secondary Education to gauge childhood education performance versus international achievements | [7 empty] | 1.3 | Training of counterparts | 0 | 0
[11 empty] | 1.4 | Contracts | 0 | 35400
[11 empty] | 1.5 | Other direct costs | 0 | 41.772
[11 empty] | 2.0 | Indirect support costs 7% | 0 | 2480.924
JP Outcome 2: Improved cross-cultural understanding at a community level | [12 empty] | 185405.84 | 961517.1594
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Planned Budget
[10 empty] | Source of Funds | Budget Description (Expenditure Account) |  |  | Total Amount
(List of Output Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
2.1 | Promoted models of social inclusion in primary schools of project target communities.
|  | 2.1.1 | Developing community level educational approaches to address ethnically-based inequalities. |  |  |  |  | UNICEF | MoCA, MoE, PI, PS in Core Localities | MDG-F | 1.1 | Supplies, commodities, equipment and transport | -6182.52 | 0
| Teachers' manual printed and disseminated to MoE, Agency for preprimary, primary and secondary education and to PS in 10 core municipalities | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 12414.54 | 42838
| Students' manual printed and disseminated to MoE, Agency for preprimary, primary and secondary education and to PS in 10 core municipalities | [9 empty] | 1.3 | Training of counterparts | 95000 | 50500
|  | a. | Develop educational models for joint interventions promoting social inclusion in formal and non-formal environments. | [7 empty] | 1.4 | Contracts | -102268.96 | 217000
| Parents' manual printed and disseminated to MoE, Agency for preprimary, primary and secondary education and to PS in 10 core municipalities | [9 empty] | 1.5 | Other direct costs | -5922.3 | 1567.6148
[11 empty] | 2.0 | Indirect support costs 7% | 0 | 21833.393
| At least one meeting with PCWG to develop an outline of public call and criteria for selection of primary schools to receive an infrastructure grants for projects that encourage intercultural encounter held | b. | Provide small infrastructure grants to create spaces for multicultural interactions among students. |  |  |  |  | UNICEF | MoCA, MoE, PI, PS in Core Localities | MDG-F
Public call for primary schools in 10 core municipalities to submit project proposals for enhancing intercultural teaching published
10 schools started with implementation of grants
| 20 workshops for teachers training implemented | c. | Provide teacher training programmes on interculturalism, equality and social justice. |  |  |  |  | UNICEF | PS in Core Localities | MDG-F
Conference for teachers in 10 municipalities to share experiences held
| Child-Friendly School 'tool kit' printed and distributed | d. | Prepare the consolidated and standardised Child-friendly School "tool kit" to 1,000 schools. |  |  |  |  | UNICEF | MoE, PI, PS | MDG-F
Public promotion of the Child Friendly tool kit to all primary schools in 10 selected municipalities, education authorities and other educational institutions (500 tool kits)
Publication "Learning to Live Together" printed and distributed 1,000 schools
| Roma Regional Conference held - with inclusion of Roma population in core localities | e. | Support local civil society organizations for multicultural activities outside traditional school settings. |  |  |  |  | UNICEF | NGOs, CSOs | MDG-F
Call for project proposal to NGOs and CSOs published
Grants to NGOs and CSOs based on project proposals provided
|  | 2.1.2 | Analysing and addressing barriers to cross-cultural tolerance. |  |  |  |  | UNICEF | Core Localities | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 0 | 15200
| KAP study finalised | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | -29810.73 | 0
[11 empty] | 1.3 | Training of counterparts | 0 | 0
| Attitudes about interculturalism identified and analysed. | a. | Conduct a gender-sensitive KAP (Knowledge, Practices, Attitudes) study on behavioural attitudes about interculturalism. | [7 empty] | 1.4 | Contracts | 25250 | 0
[11 empty] | 1.5 | Other direct costs | 29.8 | 17.936
[11 empty] | 2.0 | Indirect support costs 7% | 0 | 1065.2555
2.2 | Enhanced local initiatives delivering positive cross-cultural messages.
| Note references to municipalities under2.2.1 and 3.1.2 activities are product of approved prioritised projects in selected 10 core localities | 2.2.1 | Supporting community-based creative initiatives that improve cross-cultural understanding. |  |  |  |  | UNDP |  | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 0 | 6000
| Oral history project for Eminagica house and Ethno house in gymnasium respectively (Tesanj and Jajce) prepared. | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 22946.37 | 117800
| - Library infrastructure improved and adapted to modern technological standards: digitalisation of library funds in Bijeljina, Ugljevik, Lopare and Tesanj; creation of special children’s sections in municipal libraries; establishment of internet access in public libraries'; 70% achieved in 2010 | [9 empty] | 1.3 | Training of counterparts | 0 | 0
|  | a. | Building on Cultural Memory for improving understanding | [7 empty] | 1.4 | Contracts | 103020.75 | 400000
| -Support to BiH cinematography through preservation and revitalisation of existing endangered archives. | [9 empty] | 1.5 | Other direct costs | 95.89 | 1000
[11 empty] | 2.0 | Indirect support costs 7% | 12218 | 36736
|  | b. | Supporting building Social Capital through culture and performing arts |  |  |  |  | UNDP |  | MDG-F
At least three local communities received trainings and workshops conducted in core localities on cultural identity and belonging - cooperation with British Council ( up to 10 participants per local community).
Youth Camp in Rudo organised for over 5,000 children; Elementary school restored and put in function for summer activities.
At least 5 travelling theatre and music performances and festivals organized in local communities (culture centres) in both entities.
Open-air public space transformed in summer cultural activities in N. Sarajevo
At least 5 projects supported through second public call for NGOS (based on criteria for increased cross-cultural messages)
| At least two projects selected in core localities of Bijeljina, Derventa and Srebrenik implemented by CSOs that support people with disabilities | c. | Ensuring inclusion of minorities or socially excluded categories through implementation of culture projects |  |  |  |  | UNDP |  | MDG-F
Culture center created in minority returnee area (Ripac) of municipality of Bihac.
|  | 2.2.2 | Reinforcing stakeholder capacities in the field of intercuturalism. |  |  |  |  | UNESCO | Policy makers | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 1000 | 1000
| 20 participants (local decision makers) from selected municipalities and trained in cultural diversity focusing on intercultural understanding and mediation. | [7 empty] | CSOs |  | 1.2 | Personnel (staff, consultants, travel and training) | 22624 | 22624
[11 empty] | 1.3 | Training of counterparts | 0
|  | a. | Build capacity of local level decision-makers to manage cultural diversity in their communities focusing on intercultural education and mediation skills using a gender-sensitive approach. | [7 empty] | 1.4 | Contracts | 28200 | 20200
[11 empty] | 1.5 | Other direct costs | 2956 | 2866.61
[11 empty] | 2.0 | Indirect support costs 7% | 3835 | 3268.35
|  | b. | Build capacity of community-based organisations in approaches to cultural sensitivity (focus on intercultural mediation). |  |  |  |  | UNESCO |  | MDG-F
20 participants (NGOs) from selected municipalities trained in cultural diversity focusing on intercultural understanding and mediation.
| 2 debates in selected municipalities organised | c. | Organise in partnership with universities and civil society, workshops and public debates about cultural diversity. |  |  |  |  | UNESCO |  | MDG-F
| 20 participants from selected municipalities trained | d. | Engage civil society in European and regional cooperation projects and networks. |  |  |  |  | UNESCO |  | MDG-F
JP Outcome 3: Strengthened cultural industries | [12 empty] | 197405.09 | 835062.06
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Planned Budget
[10 empty] | Source of Funds | Budget Description (Expenditure Account) |  |  | Total Amount
(List of Output Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
3.1 | Increased employment and profitability levels within the cultural industries.
| Guidelines for Directory developed and the tentative list of ITH defined. | 3.1.1 | Supporting artistic-entrepreneurs through strategising, marketing and vocational training. |  |  |  |  | UNESCO |  | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 1000 | 1000
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 19273 | 24180
[11 empty] | 1.3 | Training of counterparts | 0 | 0
|  | a. | Create a directory of intangible cultural heritage of Bosnia and Herzegovina and provide trainings to relevant stakeholders. | [7 empty] | 1.4 | Contracts | 34350 | 61500
[11 empty] | 1.5 | Other direct costs | 2786 | 5191.83
[11 empty] | 2.0 | Indirect support costs 7% | 4018.35 | 6431.03
| Guidelines for preparation of applications for the Community Programme Culture | b. | Assist cultural organisations in targeting local and international markets and obtaining financial sustainability. |  |  |  |  | UNESCO |  | MDG-F
30 participants trained from 10 core localities and additional 13 municipalities
| 30 participants trained from 10 selected municipalities and additional 13 municipalities | c. | Provide training for artists on quality standards, labelling, regulatory frameworks and copy-rights. |  |  |  |  | UNESCO |  | MDG-F
| Restored and furnished monument in Tesanj (Eminagica kuca) and environment for summer festival and income generation activities on medieval fortress created | 3.1.2 | Promoting cultural industries and cultural tourism. |  |  |  |  | UNDP |  | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 8523.31 | 4500
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 16890.9 | 163060
[11 empty] | 1.3 | Training of counterparts | 0 | 50000
| At least 20 representatives from Municipalities, CSOs and SMEs trained to manage and promote cultural tourism. | a. | Run professional courses for culture workers and tourism providers. | [7 empty] | 1.4 | Contracts | 96904.59 | 450000
[11 empty] | 1.5 | Other direct costs | 118.3 | 21000
[11 empty] | 2.0 | Indirect support costs 7% | 13540.64 | 48199.2
| Open -air stage prepared and culture content in Municipality of Prijedor improved by engaging music performances , interactive workshops and work with youth. | b. | Improving the economic role of cultural industries |  |  |  |  | UNDP |  | MDG-F
Culture centre restored and at least five workshops and interactive trainings in arts, music, literature prepared in municipality of Sokolac.
Culture centre in Gradiska equipped with adequate technical equipment and at least 10 musical concerts prepared by the municipality of Gradiska.
Old school in Jajce restored and converted into Ethno museum with valuable local artefacts and handicrafts displayed.
Medieval fortresses restored and innovative cultural products developed in line with market demands in core localities of Srebrenik and Tesanj.
| Cultural Tourism Promotion through printed and web-based promotion materials- to be distributed to key local stakeholders, tourist organisations, municipalities and national and entity line ministries. | c. | Development of sustainable cultural tourism products in BiH and branding cultural products in BiH. |  |  |  |  | UNDP |  | MDG-F
10 medieval Bosnian fortresses supported (among which Tesanj, Srebrenik and Jajce) developed as cultural tourism product for the country – pilot destination management in BiH.
At least 5 projects supported through second public call for NGOs (based on increased income-generation and job-creation criteria )
| At least five of selected museums and major tourist sites in BiH accessible for disabled persons. | d. | Support to the museum sector and cultural institutions in BiH |  |  |  |  | UNDP |  | MDG-F
JP Outcome 4: Improved tolerance towards diversity | [12 empty] | 83223.43 | 965724.255
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Planned Budget
[10 empty] | Source of Funds | Budget Description (Expenditure Account) |  |  | Total Amount
(List of Output Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
4.1 | Increased number of positive public discourses on interculturalism.
| Report on cultural sensitivity of media reporting in BiH prepared for 2009 and used as baseline. | 4.1.1 | Promoting intercultural awareness and sensitivity through media and stakeholder partnerships. |  |  |  |  | UNDP |  |  | 1.1 | Supplies, commodities, equipment and transport | 0 | 0
| Media monitoring on cultural sensitivity of media reporting prepared for 2010 throughout the year. At least bi-annual meetings with government conducted for analysis of the report. | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 1275.66 | 31108
|  | a. | Analyse the degree to which messages in the media are delivered in a culturally-sensitive and gender-sensitive manner and present findings. | [7 empty] | 1.3 | Training of counterparts | 0 | 30000
[11 empty] | 1.4 | Contracts | 31365.17 | 75000
| At least 20 journalists and media professionals in BiH trained on culturally (and gender) sensitive reporting Trainings prepared based on the gap analysis of the media monitoring reports. | [7 empty] | Media | MDG-F | 1.5 | Other direct costs | 33.81 | 100
[11 empty] | 2.0 | Indirect support costs 7% | 3440.47 | 9534.525
| - MDG-F Joint Culture Communications strategy implemented - At least 20 Promotional events organised in core localities and at the national level; MDGF promoted through joint events; | b. | Undertake gender-sensitive information campaign and support media production of cultural diversity, tolerance and understanding. | [5 empty] | Media | MDG-F
At least three documentaries and/or feature films on intercultural understanding produced, distributed and discussions organized, including collaboration with TV and film festivals in BiH.
| Young talent supported for the production of short feature films aiming at enhancing understanding and raising awareness on the MDGs and Gender equality. | c. | Production of documentaries and feature films on intercultural understanding and support of young talent for cinematography | [5 empty] | Media | MDG-F
| - Web-based BiH Culture Identify forum created and internet-based culture mapping conducted for at least 10 municipalities | d. | Development of interactive culture mapping and cultural ID forum for BiH | [5 empty] | Core Localities | MDG-F
| Technical assistance for development of behaviour change campaign (BCC) provided. The BCC will be implemented through 4 main phases: Diagnosis, Planning, Intervention and the Evaluation. Diagnosis: KAP findings provided will serve as the baseline to identify the problems in the attitudes, practices and knowledge of the concerned target groups, through the involvement of the community. Planning: Based on the KAP, the Integrated communications action Plan (ICAP) for BCC, will be developed to define the main communication needs, objectives and activities, tools and channels for all stakeholders . Intervention: Pre - testing the messages and dissemination of messages. Programme activities: workshops for stakeholders, puppet shows, community based activities, development of community action plans Evaluation: KAP upon the intervention phase and external communication activities | 4.1.2 | Promoting intercultural sensitivity in the education sphere. |  |  |  |  | UNICEF |  |  | 1.1 | Supplies, commodities, equipment and transport | 0 | 10000
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 17500 | 70700
|  | a. | Organise a gender-sensitive Behaviour Change Communication (BCC) campaign. | [5 empty] | Media, Core Localities | MDG-F | 1.3 | Training of counterparts | 7000 | 0
[11 empty] | 1.4 | Contracts | 20000 | 30000
[11 empty] | 1.5 | Other direct costs | 857.14 | 1181.06
[11 empty] | 2.0 | Indirect support costs 7% | 0 | 7831.67
| Workshops with parents, teachers, students, local authorities, media and public in 10 municipalities to develop multi-cultural messages for parents, teachers, pedagogues and school principles implemented | b. | Develop and disseminate specific messages at community level. | [5 empty] | Media, PS in Core Localities | MDG-F
Media campaign for dissemination of multicultural messages implemented
|  | 4.1.3 | Rehabilitating and restoring major symbols of interculturalism. |  |  |  |  | UNESCO |  | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 0 | 19000
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 37705.41 | 106864
[11 empty] | 1.3 | Training of counterparts | 0 | 0
| Restoration of 8 monuments (identified by MoCA with entity Ministries of Culture) initiated as follows: | a. | Initiate the restoration of ten (10) monuments - tangible symbols of BiH inteculturalism. Activities on restoration of monuments for culture tourism promotion. | [7 empty] | 1.4 | Contracts | -41100 | 511800
| Derventa 2, Banjac Luka, Jajce, Mostar, Tesanj, Foca-Sutjeska, Trebinje | [9 empty] | 1.5 | Other direct costs | 5031 | 16793
[11 empty] | 2.0 | Indirect support costs 7% | 114.77 | 45812
| Publication on old fortified towns in BiH prepared / linked with UNDP activity 312d | b. | Prepare a cultural tourism framework for restoration activities. |  |  |  |  | UNESCO |  | MDG-F
JP Monitoring and Evaluation | [12 empty] | 26844.58 | 57993.2011
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Planned Budget
[10 empty] | Source of Funds | Budget Description (Expenditure Account) |  |  | Total Amount
(List of Output Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
|  | M&E | Monitoring and Evaluation |  |  |  |  | UN RC | Agencies | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 10320.98 | 5333.3333
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 8491.95 | 41325.92
| Project monitored according to Implementation guidelines for MDG Achievement Fund Joint Programmes | [9 empty] | 1.3 | Training of counterparts | 0 | 0
[11 empty] | 1.4 | Contracts | 0 | 0
[11 empty] | 1.5 | Other direct costs | 5396.75 | 7540
[11 empty] | 2.0 | Indirect support costs 7% | 2634.9 | 3793.9477
Total | [12 empty] | 709161.78 | 3636751.5942
Note: Remaining funds from year 1 are reflecting the unspent amounts in 2009 under specific outputs while annual targets have been reformulated for 2010.

## Sheet1
JP output: 1.1 Please highlight the rate of delivery for each joint programme’s output:
a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80%
Programme | Activity | YEAR |  | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress
Outputs
|  | Y1 | Y2 |  | NATIONAL/LOCAL | Source of Funding | Budget description | Total amount planned | Estimated Total amount | Estimated Total Amount Disbursed | Total (disbursed + commited) | Estimated
[9 empty] | Committed |  |  | % Delivery rate of budget
Improved policies & legal frameworks in culture and education sectors. | 1.1.1 Providing the evidence-base for strategy implementation in the culture sector. | X |  | UNDP | MoCA, Entity, MoCs | MDG-F | 1.1 Supplies, commodities, equipment and transport | 50950 | 0 | 39659.8 | 39659.8 |  | 11290.2
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 40440 | 22000 | 42203.91 | 64203.91 |  | -23763.91
[7 empty] | 1.3 Training of counterparts | 10000 | 0 | 1102.37 | 1102.37 |  | 8897.63
[7 empty] | 1. 4 Contracts | 82647 | 40991.3 | 4112.93 | 45104.23 |  | 37542.77
[7 empty] | 1.5 Other direct costs | 41200 | 0 | 41108.21 | 41108.21 |  | 91.79
[7 empty] | 2.0 Indirect support costs 7% | 15767 | 0 | 6127.97 | 6127.97 |  | 9639.03
0
[7 empty] | TOTAL ACTIVITY | 241004 | 62991.3 | 134315.19 | 197306.49 | More than 80 %
| 1.1.2 Assist programme stakeholders in policy development. | X |  | UNDP | MoCA, Entity, MoCs, Public Servants, Culture & Tourism Organisations | MDG-F | 1.1 Supplies, commodities, equipment and transport | 37750 | 0 | 24056.81 | 24056.81 |  | 13693.19
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 303180 | 22742.65 | 258508.44 | 281251.09 |  | 21928.91
[7 empty] | 1.3 Training of counterparts | 10000 | 0 | 10000 | 10000 |  | 0
[7 empty] | 1. 4 Contracts | 53000 | 0 | 7394.04 | 7394.04 |  | 45605.96
[7 empty] | 1.5 Other direct costs | 32083 | 0 | 31906.6 | 31906.6 |  | 176.4
[7 empty] | 2.0 Indirect support costs 7% | 30521 | 0 | 14808.32 | 14808.32 |  | 15712.68
0
[7 empty] | TOTAL ACTIVITY | 466534 | 22742.65 | 346674.21 | 369416.86 | between 71%-80
| 1.1.3 Improving policies and their implementation to ensure access to quality multi-cultural education | X |  | UNICEF | National | MDG-F | 1.1 Supplies, commodities, equipment and transport | 9300 | 0 | 0 | 0 |  | 9300
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 143300 | 262504.97 | 251718.24 | 262504.97 |  | -119204.97
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 135250 | 0 | 0 | 0 |  | 135250
[7 empty] | 1.5 Other direct costs | 35781.44 | 9860.49 | 9860.49 | 9860.49 |  | 25920.95
[7 empty] | 2.0 Indirect support costs 7%* | 22654.2 | 22654.2 | 22654.2 | 22654.2 |  | 0
0
[7 empty] | TOTAL ACTIVITY | 346285.64 | 295019.66 | 284232.93 | 295019.66 | More than 80 %
| 1.1.4 Supporting the preparation of policy documents, reporting mechanisms and legal framework (Capacity development). | X |  | UNESCO | MoCA, Culture & Tourism Organisations | MDG-F | 1.1 Supplies, commodities, equipment and transport | 16224 | 0 | 0 | 0 |  | 16224
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 26300 | 20000 | 15000 | 20000 |  | 6300
[7 empty] | 1.5 Other direct costs | 4581 | 0 | 0 | 0 |  | 4581
[7 empty] | 2.0 Indirect support costs 7% | 3297 | 1400 | 0 | 1400 |  | 1897
[7 empty] | TOTAL ACTIVITY | 50402 | 21400 | 15000 | 21400 | between 31%-50%
Strengthened capacities of State and Entity-level Governments in monitoring and evaluation of cultural development. | 1.2.1. Providing monitoring and evaluation training activities to relevant government agencies. | X |  | UNDP | MoCA | MDG-F | 1.1 Supplies, commodities, equipment and transport | 4000 | 0 | 0 | 0 |  | 4000
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 18000 | 0 | 16463.62 | 16463.62 |  | 1536.38
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1.5 Other direct costs | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 2.0 Indirect support costs 7% | 1540 | 0 | 855.74 | 855.74 |  | 684.26
0
[7 empty] | TOTAL ACTIVITY | 23540 | 0 | 17319.36 | 17319.36 | between 71%-80 %
| 1.2.2 Developing a system to monitor the implementation of improved educational policies. | X |  | UNICEF | National | MDG-F | 1.1 Supplies, commodities, equipment and transport | 0 | 0 | 0 | 0
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 0 | 0 | 0 | 0
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0
[7 empty] | 1. 4 Contracts | 0 | 0 | 0 | 0
[7 empty] | 1.5 Other direct costs | 0 | 0 | 0 | 0
[7 empty] | 2.0 Indirect support costs 7%* | 0 | 0 | 0 | 0
[7 empty] | TOTAL ACTIVITY | 0 | 0 | 0 | 0
| 2.1.1. Developing community level educational approaches to address ethnically-based inequalities | X |  | UNICEF | Local | MDG-F | 1.1 Supplies, commodities, equipment and transport | 0 | 6182.52 | 6182.52 | 6182.52 |  | -6182.52
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 45800.66 | 33386.12 | 33386.12 | 33386.12 |  | 12414.54
[7 empty] | 1.3 Training of counterparts | 95000 | 0 | 0 | 0 |  | 95000
[7 empty] | 1. 4 Contracts | 0 | 102268.96 | 71463.97 | 102268.96 |  | -102268.96
[7 empty] | 1.5 Other direct costs | 766.86 | 6689.16 | 6689.16 | 6689.16 |  | -5922.3
[7 empty] | 2.0 Indirect support costs 7% | 9909.73 | 9909.73 | 9909.73 | 9909.73 |  | 0
[7 empty] | TOTAL ACTIVITY | 151477.25 | 158436.49 | 127631.5 | 158436.49 | More than 80 %
| 2.1.2 Analyzing and addressing barriers to cross-cultural tolerance | X |  | UNICEF | Local | MDG-F | 1.1 Supplies, commodities, equipment and transport | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 0 | 29810.73 | 10966.19 | 29810.73 |  | -29810.73
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 25250 | 0 | 0 | 0 |  | 25250
[7 empty] | 1.5 Other direct costs | 29.8 | 0 | 0 | 0 |  | 29.8
[7 empty] | 2.0 Indirect support costs 7%* | 1769.59 | 1769.59 | 1769.59 | 1769.59 |  | 0
[7 empty] | TOTAL ACTIVITY | 27049.39 | 31580.32 | 12735.78 | 31580.32 | between 31%-50%
Promoted models of social inclusion in primary schools of project target communities. | 2.2.1. Supporting community-based creative initiatives that improve cross-cultural understanding. | X |  | UNDP | MoCA, MUNICIPALITIES | MDG-F | 1.1 Supplies, commodities, equipment and transport | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 24040 | 0 | 1004.97 | 1004.97 |  | 23035.03
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 150000 | 0 | 0 | 0 |  | 150000
[7 empty] | 1.5 Other direct costs | 500 | 0 | 404.11 | 404.11 |  | 95.89
[7 empty] | 2.0 Indirect support costs 7% | 12218 | 0 | 0 | 0 |  | 12218
[7 empty] | TOTAL ACTIVITY | 186758 | 0 | 1409.08 | 1409.08 | Less than 30%
Enhanced local initiatives delivering positive cross-cultural messages. | 2.2.2 Reinforcing stakeholder capacities in the field of intercuturalism. | X |  | UNESCO | Policy-makers, CSOs | MDG-F | 1.1 Supplies, commodities, equipment and transport | 1000 | 0 | 0 | 0 |  | 1000
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 22624 | 0 | 0 | 0 |  | 22624
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 28200 | 0 | 0 | 0 |  | 28200
[7 empty] | 1.5 Other direct costs | 2956 | 0 | 0 | 0 |  | 2956
[7 empty] | 2.0 Indirect support costs 7% | 3835 | 0 | 0 | 0 |  | 3835
[7 empty] | TOTAL ACTIVITY | 58615 | 0 | 0 | 0
Increased employment and profitability levels within the cultural industries. | 3.1.1 Supporting artistic-entrepreneurs through strategising, marketing and vocational training. | X |  | UNESCO | Universities, Private Sector | MDG-F | 1.1 Supplies, commodities, equipment and transport | 1000 | 0 | 0 | 0 |  | 1000
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 32868 | 13595 | 13595 | 13595 |  | 19273
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 34350 | 0 | 0 | 0 |  | 34350
[7 empty] | 1.5 Other direct costs | 2786 | 0 | 0 | 0 |  | 2786
[7 empty] | 2.0 Indirect support costs 7% | 4970 | 951.65 | 951.65 | 951.65 |  | 4018.35
[7 empty] | TOTAL ACTIVITY | 75974 | 14546.65 | 14546.65 | 14546.65 | Less than 30%
| 3.1.2 Promoting cultural industries and culture tourism. |  |  | UNDP | NGOs, CSOs, Municipalities, Public Institutions | MDG-F | 1.1 Supplies, commodities, equipment and transport | 28700 | 0 | 20176.69 | 20176.69 |  | 8523.31
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 40920 | 1046.46 | 21967.93 | 23014.39 |  | 17905.61
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 150000 | 0 | 0 | 0 |  | 150000
[7 empty] | 1.5 Other direct costs | 400 | 0 | 281.7 | 281.7 |  | 118.3
[7 empty] | 2.0 Indirect support costs 7% | 15401 | 0 | 1860.36 | 1860.36 |  | 13540.64
[7 empty] | TOTAL ACTIVITY | 235421 | 1046.46 | 44286.68 | 45333.14 | Less than 30%
Increased number of positive public discourses on interculturalism. | 4.1.1 Promoting intercultural awareness and sensitivity through media and stakeholder partnerships. |  |  | UNDP | Universities, Media | MDG-F | 1.1 Supplies, commodities, equipment and transport | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 32708 | 6000 | 25432.34 | 31432.34 |  | 1275.66
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 45000 | 13280.28 | 354.55 | 13634.83 |  | 31365.17
[7 empty] | 1.5 Other direct costs | 6100 | 0 | 5609.99 | 5609.99 |  | 490.01
[7 empty] | 2.0 Indirect support costs 7% | 5867 | 0 | 2426.53 | 2426.53 |  | 3440.47
[7 empty] | TOTAL ACTIVITY | 89675 | 19280.28 | 33823.41 | 53103.69 | between 51 %-60 %
| 4.1.2 Promoting intercultural sensitivity in the education sphere |  |  | UNICEF | Local | MDG-F | 1.1 Supplies, commodities, equipment and transport | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 17500 | 0 | 0 | 0 |  | 17500
[7 empty] | 1.3 Training of counterparts | 7000 | 0 | 0 | 0 |  | 7000
[7 empty] | 1. 4 Contracts | 20000 | 0 | 0 | 0 |  | 20000
[7 empty] | 1.5 Other direct costs | 857.14 | 0 | 0 | 0 |  | 857.14
[7 empty] | 2.0 Indirect support costs 7%* | 3175 | 3175 | 3175 | 3175 |  | 0
[7 empty] | TOTAL ACTIVITY | 48532.14 | 3175 | 3175 | 3175 | Less than 30%
| 4.1.3 Rehabilitating and restoring major symbols of interculturalism. | X |  | UNESCO | MoCA, Private Sector | MDG-F | 1.1 Supplies, commodities, equipment and transport | 22350 | 22350 | 22350 | 22350 |  | 0
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 109208 | 71502.59 | 71502.59 | 71502.59 |  | 37705.41
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 251900 | 293000 | 213688 | 293000 |  | -41100
[7 empty] | 1.5 Other direct costs | 14096 | 9065 | 0 | 9065 |  | 5031
[7 empty] | 2.0 Indirect support costs 7% | 27829 | 27714.23 | 21527.84 | 27714.23 |  | 114.77
[7 empty] | TOTAL ACTIVITY | 425383 | 423631.82 | 329068.43 | 423631.82 | More than 80 %
| MONITORING&EVALUATION |  |  | RC | Agencies | MDG-F | 1.1 Supplies, commodities, equipment and transport | 13588 | 0 | 3267.02 | 3267.02 |  | 10320.98
[7 empty] | 1.2 Personnel (staff, consultants, travel and training) | 41326 | 0 | 32834.05 | 32834.05 |  | 8491.95
[7 empty] | 1.3 Training of counterparts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1. 4 Contracts | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 1.5 Other direct costs | 13945 | 0 | 7538.38 | 7538.38 |  | 6406.62
[7 empty] | 2.0 Indirect support costs 7% | 4820 | 0 | 2185.1 | 2185.1 |  | 2634.9
[7 empty] | TOTAL ACTIVITY | 73679 | 0 | 45824.55 | 45824.55 | between 61%-70%
Total | [7 empty] | 2500329.42 | 1053850.63 | 1410042.77 | 1677503.11 | 67.09%