Color-Coded Annual Work Plan for Year 2 of China Culture and Development Partnership Framework (CDPF)

Green = done, yellow = ongoing, and red = not started

| Annual targets | Activity | TIME FRAME 2010 | UN AGENCY | RESPONSIBLE PARTY | Planned Budget |
| --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Source of Funding | Budget description | Total amount |
| Outcome 1: The inclusion of ethnic minorities in cultural, socio-economic and political life strengthened through improved public policies and services |
| Output 1.1: Governance processes made more inclusive of ethnic minorities and sensitive to culturally based development strategies |
| Cultural Diversity Lens Toolkit tested at training workshops and feedback collected to draft adapted handbook; Monitoring strengthened | 1.1.2 Feedback and real cases collected on the translated Cultural Diversity Programming Lens Toolkit for the adaptation of the Toolkit to the local situation through training workshops | x | x | x | x | UNESCO | State Ethnic Affairs Commission (SEAC) | MDG-F | Personnel | 15,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 25,000 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |
|  | 1.1.5. Monitoring, evaluation and reporting | x | x | X | x | UNESCO | SEAC | MDG-F | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 7,000 |
| Governance processes made more inclusive of ethnic minorities and sensitive to culturally based development strategies | 1.1.6 Partnership building and communication | x | x | X | x | UNDP | SEAC, China International Center for Economic and Technical Exchange (CICETE) | MGD-F | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 3,000 |
|  | 1.1.7 Carry out training activities for communities and civil society representatives on (i) participatory processes, and (ii) the role of civil society in making inclusive policies Carry out an international training activity for government representatives on (i) social and economic gains from increased participation and information by minority communities in policy making, (ii) the role of CSOs in bridging the gap between local constituencies and their representatives; (iii) the intrinsic and economic value of cultural assets, and (iv) the mutually supporting role of heritage protection and economic growth | x |  | x |  | UNDP | SEAC, CICETE | MGD-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 58,740 |
|  |  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 3,000 |
|  |  |  |  |  |  |  |  |  | Total | 76,740 |
|  | 1.1.8 Design, establish and test exchange mechanism in one or two pilot counties | x | X | x | x | UNDP | SEAC, CICETE | MGD-F | Personnel | 4,260 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 8,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 2,000 |
|  |  |  |  |  |  |  |  |  | Total | 14,260 |
|  | 1.1.9 Recommendations will be drafted to facilitate the inclusion of cultural minorities in public policies and services | x | X | x | x | UNDP | SEAC, CICETE | MGD-F | Personnel | 1,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 500 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 500 |
|  |  |  |  |  |  |  |  |  | Total | 2,000 |
|  | Monitoring and evaluation |  | X |  |  | UNDP | SEAC, CICETE | MGD-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 5,000 |
| Output 1.2: Strengthened policy and institutional capacities in developing and implementing culturally sensitive and quality basic education for ethnic minority children |  |  |  |  |  |  |  |  |
| Project progress on teaching and learning status for ethnic minority teachers and children monitored | 1.2.1 Field monitoring by UNICEF and implementing partners |  | x | x |  | UNICEF | Ministry of Education (MOE), Provincial Education Bureaus, Beijing Normal University (BNU) | MGD-F | Personnel | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
| Ethnic minority teachers informed on child friendly and culture-sensitive teaching and management | 1.2.2 Training workshops on children’s participation, culturally sensitive teaching, participatory school management and peer support for local teacher trainers, school teachers and administrators |  | x | x | x | UNICEF | MOE, Provincial Education Bureaus, BNU | MGD-F | Personnel | 24,946 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 48,000 |
|  |  |  |  |  |  |  |  |  | Total | 72,946 |
| Local curriculum guidelines/ training/teaching/learning materials developed | 1.2.3 Material development including guidebook on project implementation (checklist, manual); at least 3 sets of local curricula in culturally appropriate languages; training facilitator kits | x | x | x | x | UNICEF | MOE, Provincial Education Bureaus, BNU | MGD-F | Personnel | 25,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 25,000 |
|  |  |  |  |  |  |  |  |  | Total | 50,000 |
| Best practice models on culturally sensitive and quality basic education identified | 1.2.5 Identification of best practice models; national workshop for experience exchange for ethnic minority teachers on quality and culture-sensitive teaching and learning | x | x | x | x | UNICEF | MOE, Provincial Education Bureaus, Technical institutions | MGD-F | Personnel | 35,000 |
|  |  |  |  |  |  |  |  |  | Total | 35,000 |
| Supplies provided to local technical institutes and pilot schools | 1.2.6 Supply provision to local training institutions and pilot schools, including materials developed for teachers and administrators, IEC materials on Water, Sanitation and Hygiene as well as learning materials for children |  | x | x | x | UNICEF | MOE, Provincial Education Bureaus, Technical institutions | MGD-F | Supplies | 47,000 |
|  |  |  |  |  |  |  |  |  | Total | 47,000 |
| Review of national and provincial policy on education for ethnic minorities | 1.2.7 Collection of national and provincial policy documents -Analysis from the minority perspective - Data processing | × |  |  |  | UNESCO | NatCom, MoE, College of Education of Central University for Nationalities | MDG-F | Personnel | 18,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 22,000 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |
| Implementation of education policies examined and best practices and gaps in education for ethnic children identified | 1.2.8 On the basis of policy review and field survey conducted in Year 1, select schools and communities for case studies with certain criteria; Design and pretest case study instruments and train researchers; Conduct at least 12 case studies in Guizhou, Yunnan and Qinghai | x | x | x |  | UNESCO | MOE (National Commission for UNESCO) | MDG-F | Personnel | 18,500 |
|  |  |  |  |  |  |  |  |  | Contracts | 81,000 |
|  |  |  |  |  |  |  |  |  | Total | 99,500 |
| Policy recommendations developed and specific actions for effective implementation identified Report on education for ethnic minority children developed Training materials on improved and culturally sensitive policy planning, implementation and monitoring for education administrators developed | 1.2.9 Analyze case study data and findings to draw policy recommendations and identify specific actions for effective policy implementation; Develop a synthesis report with the findings from the Year 1 policy review, case studies and policy recommendations; Develop materials for the training of education administrators from the project sites to be conducted in Year 3 |  |  | × | × | UNESCO | MOE (National Commission for UNESCO) | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 40,000 |
|  |  |  |  |  |  |  |  |  | Other Direct Costs | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 50,000 |
| Output 1.3: Improved access to, participation in, quality of and knowledge and uptake of an essential package of evidence-based Maternity and Child Health (MCH) and Family Planning (FP) services and associated practices in ethnic minority areas, acknowledging culture and traditional beliefs as key influences on service strategies and uptake, prioritized by local administrators, and incorporating improvements in human and financial resources, health systems management, and monitoring and evaluation systems that specifically focus on the ethnicity of the providers and beneficiaries |
| Prepare and introduce culturally appropriate adaptations of national guidelines for training of MCH/FP service providers (UNFPA), and for counseling on MCH/FP choices National MCH guidelines adapted to local context | 1.3.3. Adaptation of national MCH guidelines and print and distribute the MCH technical guidelines | x | × | × | × | UNICEF | Ministry of Health (MOH), National Centre for Women’s and Children’s Health (NCWCH), Provincial Health Bureaus | MDG-F | Contracts | 18,000 |
|  |  |  |  |  |  |  |  |  | Supplies | 3,000 |
|  |  |  |  |  |  |  |  |  | Total | 21,000 |
| Prepare and introduce culturally appropriate adaptations of national guidelines for training of FP service providers (informed choice component), and for counselling on FP choices | 1.3.4. Adaptation of national FP guidelines (informed choice component), print and distribute the FP technical guidelines (informed choice component); training workshops with culturally sensitive materials on promotion of informed choice and provision of MCH information for FP staff |  | × | × | × | UNFPA | China Population Development and Research Centre (CPDRC), National Population and Family Planning Commission (NPFPC) | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 11,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 21,000 |
| Training of provincial, county and township level health providers on MCH and health communication strategies, using community-based traditional leaders and health providers, and rollout an essential package of services (UNICEF) and monitoring and evaluation to project sites | 1.3.5. Training service providers on MCH and participatory health communication strategies and rollout the Mother-baby package of services in project counties, & monitoring and evaluation conducted |  | × |  | × | UNICEF | MOH, NCWCH, Provincial Health Bureaus | MDG-F | Personnel | 45,970 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 60,000 |
|  |  |  |  |  |  |  |  |  | Supplies | 37,000 |
|  |  |  |  |  |  |  |  |  | Total | 142,970 |
| Local decision makers and service providers (MOH/FP) sensitized on culturally sensitive issues specific to each county: need to reduce communication barriers, and/or to change negative attitudes towards clients, and/or to promote minorities participation in service design/provision, and/or to associate communities in health promotion activities, and/or to increase resources for MCH system (based on findings of cultural study) | 1.3.7. Advocacy workshops and other advocacy activities targeting local decision makers and service providers | x | × | × |  | UNFPA | MOH, NCWCH, NPFPC, CPDRC, Minzu University | MDG-F | Personnel | 20,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 20,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 60,000 |
| Improved household practices | 1.3.8. Culturally appropriate MCH client education activities at county level conducted | × | × | × | × | UNICEF | MOH, NCWCH, Provincial Health Bureaus | MDG-F | Supplies | 6,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 18,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 8,334 |
|  |  |  |  |  |  |  |  |  | Total | 32,334 |
| Improved household practices and health awareness on issues specific to each minority: antenatal care, and/or hospital delivery, and/or breastfeeding, and/or infant feeding etc. (based on findings of baseline survey and cultural study) | 1.3.9. Culturally appropriate MCH client education activities at county level, using local media and mobilizing communities | × | × | × | × | UNFPA | MOH, NCWCH, NPFPC, CPDRC, | MDG-F | Personnel | 30,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 42,400 |
|  |  |  |  |  |  |  |  |  | Total | 72,400 |
| MCH/FP essential package defined | 1.3.11 Conduct financing case studies (investment studies) in Tibet, Yunnan, Guizhou and Qinghai | x | X | x |  | WHO | MOH | MGD-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 30,000 |
| Draft integrating MCH service model in rural areas is available | 1.3.12 Workshop with experts from the fields of MCH and rural health to analyze the findings of the baseline survey and plan next steps; Support national policy-making on MCH & New Rural Medical Scheme integration in ethnic minority areas and its application in pilot counties; Establish mechanism which will influence accessibility in programme sites; Programme monitoring and evaluation |  | X | x |  | WHO | MOH, Huazhong University of Science and Technology | MGD-F | Personnel | 12,500 |
|  |  |  |  |  |  |  |  |  | Contracts | 25,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 2,500 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |
| Standardized MCH data collection | 1.3.13 To improve the quality of Reproductive Health/Child and Adolescent Health data with focus on missing and new added MDG4 and MDG5 data collection in programme areas; Training on MCH information management; Standardizing management of MCH information | x | X | x |  | WHO | MOH, National Center for MCH Surveillance | MGD-F | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 32,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 2,500 |
|  |  |  |  |  |  |  |  |  | Total | 44,500 |
| M&E framework and the indicators for MCH performance evaluation finalized | 1.3.14 Development of performance evaluation tools; Expert consultation to finalize the M&E framework and the indicators; Implementation of performance evaluation on MCH services in ethnic minority regions | X |  | x | x | WHO | MOH | MGD-F | Personnel | 9,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 30,000 |
| Output 1.4: Inclusion issues of minorities are better addressed through culture-based economic empowerment and non-discrimination |  |
| Build up the knowledge base on the employment situation of ethnic minorities in selected pilot sites; Identify capacity gaps; Develop training materials | 1.4.2 Develop training materials for key stakeholders to better implement legislation; Training conducted among relevant stakeholders | × | × | × | × | ILO | Ministry of Human Resources and Social Security (MOHRSS) | MGD-F | Personnel | 20,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 12,000 |
|  |  |  |  |  |  |  |  |  | Total | 32,000 |
| Action research on language and cultural barriers facing ethnic minorities at workplace | 1.4.3. Review and analyze policies on language barriers in China; Analyze the data collected during the field visit in the first year; Continue consultative meetings with local partners in pilot sites | × | × | × | x | UNESCO | Chinese Academy of Social Sciences (CASS) | MGD-F | Contracts | 1,500 |
|  |  |  |  |  |  |  |  |  | Personnel | 6,700 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 300 |
|  |  |  |  |  |  |  |  |  | Total | 8,500 |
|  | 1.4.4. Qualitative research conducted on language and cultural barriers facing ethnic minorities in the workplace; Produce policy recommendations, foster dialogue among governments, CSOs and individuals in labour markets | x | x | x | x | UNESCO | CASS | MDG-F | Contracts | 48,500 |
|  |  |  |  |  |  |  |  |  | Personnel | 8,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 57,500 |
| Outcome 2: Ethnic minorities empowered in the management of cultural resources and benefiting from culture-based economic development |
| Output 2.1: Improved approaches and capacity of ethnic minorities in understanding and protecting cultural (tangible and intangible) capital and ethnic awareness of cultural diversity |
| Implementation cultural mapping in pilot villages and first batch of cultural maps and village archives produced; Display enhancement in existing museums and preparation for a new exhibit; Monitoring strengthened | 2.1.2. Ethnic minority communities production of own cultural maps | x | x | x | x | UNESCO | Guizhou Administration of Cultural Heritage (GACH), Beijing Cultural Heritage Protection Centre (CHP) | MDG-F | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 50,000 |
|  |  |  |  |  |  |  |  |  | Total | 60,000 |
|  | 2.1.3. Enhancement of existing exhibits incorporating results of the cultural mapping activities in the pilot villages; plan and preparation of one new exhibit in the pilot village | x | x | x | x | UNESCO | GACH, China National Museum of Ethnology | MDG-F | Personnel | 8,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 9,000 |
|  |  |  |  |  |  |  |  |  | Total | 17,000 |
|  | 2.1.4. Monitoring and Reporting | x | x | x |  | UNESCO | GACH | MDG-F | Personnel | 7,000 |
|  |  |  |  |  |  |  |  |  | Contract | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 17,000 |
| Awareness raising of traditional agro-culture in piloted minority areas | 2.1.5. Master Plan development on the dynamic conservation of agricultural heritage systems and alternative industries development | x | x | x |  | FAO | Ministry of Agriculture (MOA), Institute of Geographic Sciences and Natural Resources Research (IGSNRR) | MDG-F | Personnel | 1,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 44,000 |
|  |  |  |  |  |  |  |  |  | Total | 45,000 |
| Dynamic conservation and adaptive management of these agro-culture systems | 2.1.6. Local workshop on dynamic conservation and development and the stakeholder training |  |  |  | x | FAO | MOA, IGSNRR | MDG-F | Personnel | 3,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 17,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
| Improvement of living standard in pilot minority areas with traditional agriculture systems | 2.1.7. Publication and propaganda on agricultural systems, such as media publication and information exchange |  | x | × |  | FAO | MOA, IGSNRR | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
| Output 2.2: Capacity built and examples piloted on using participatory processes in managing minority community resources and sustainably leveraging tourism for local livelihoods |
| Tourism handbook tested at training workshops and feedback collected to draft adapted handbook; Monitoring strengthened | 2.2.3. Feedback and real cases collected on the translated Community-Based Tourism Capacity Building Handbook for the adaptation of the Toolkit to the local situation through the training workshops | x | x | x | x | UNESCO | SEAC | MGD-F | Personnel | 11,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 36,000 |
|  |  |  |  |  |  |  |  |  | Total | 47,000 |
|  | 2.2.5. Monitoring, evaluation and reporting | x | x | x | x | UNESCO | SEAC | MGD-F | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 7,000 |
| Capacity built and examples piloted on using participatory processes in managing minority community resources, and sustainability leveraging tourism for local livelihoods | 2.2.6 Partnership building and communication | x | x | x | x | UNDP | SEAC, CICETE | MGD-F | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 3,000 |
|  | 2.2.7 Carry out a national training activity which will be focused on tourism development and resource management |  | x |  |  | UNDP | SEAC, CICETE | MGD-F | Personnel | 8,500 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 20,500 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 8,000 |
|  |  |  |  |  |  |  |  |  | Total | 37,000 |
|  | 2.2.8 Recommendations to improve the provincial and local tourism strategies will be drafted as an outcome of consultation workshops or roundtables | x | x | x | x | UNDP | SEAC, CICETE | MGD-F | Personnel | 1,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 3,500 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 2,000 |
|  |  |  |  |  |  |  |  |  | Total | 6,500 |
|  | 2.2.9 Responsible cultural tourism models at pilot villages with strong community participation will be designed and established | x | x | x | x | UNDP | SEAC, CICETE | MGD-F | Personnel | 6,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 16,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 59,000 |
|  |  |  |  |  |  |  |  |  | Total | 81,000 |
|  | 2.2.10 Monitoring and evaluation |  | x |  |  | UNDP | SEAC, CICETE | MGD-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 5,000 |
| Output 2.3: Culture-based Local Economic Development (LED) and livelihood creation through: (i) provision of entrepreneurship and business development services, and (ii) strengthening policy and institutional environment for ethnic minority arts and crafts sector |  |  |  |  |  |  |  |  |
| Potential & existing entrepreneurs in cultural industries trained on Start and Improve Your Business (SIYB) | 2.3.2 Training of trainers 2.3.3 Training of entrepreneurs | × | × × | × |  | ILO | MOHRSS | MDG-F | Personnel | 20,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 25,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 3,000 |
|  |  |  |  |  |  |  |  |  | Supplies | 2,000 |
|  |  |  |  |  |  |  |  |  | Total | 50,000 |
| Action plans developed and implemented for Value Chain Development (VCD) on creative and traditional products | 2.3.6 Pilot VCD in the selected localities 2.3.7 Review of local business environment 2.3.9 Monitoring | × | × x | × × × | × | ILO | MOHRSS | MGD-F | Personnel | 20,000 |
|  |  |  |  |  |  |  |  |  | Training | 40,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 19,720 |
|  |  |  |  |  |  |  |  |  | Other Direct Costs | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 84,720 |
| Culture-based Local Economic Development (LED) and livelihood creation through: 1. provision of entrepreneurship and business development services, and 2. strengthening policy and institutional environment for ethnic minority arts and crafts sector. | 2.3.10 Partnership building and communication | x | x | x | x | UNDP | SEAC, CICETE | MGD-F | Personnel | 3,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 4,000 |
|  | 2. 3.11 Carry out training activities to support minority crafts sector. The target trainees will include representatives from local crafts associations and artisan networks. |  |  |  | x | UNDP | SEAC, CICETE | MGD-F | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 15,750 |
|  |  |  |  |  |  |  |  |  | Contracts | 13,750 |
|  |  |  |  |  |  |  |  |  | Total | 39,500 |
|  | 2.3.12. Support/create local non-government minority crafts associations and artisan networks | x | x | x | x | UNDP | SEAC, CICETE | MGD-F | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 15,750 |
|  |  |  |  |  |  |  |  |  | Contracts | 15,750 |
|  |  |  |  |  |  |  |  |  | Total | 41,500 |
|  | 2.3.13 Design and develop marketing materials; Make plans and necessary preparation for promotional event to be held in 2011 | x | x | x |  | UNDP | SEAC, CICETE | MGD-F | Contracts | 15,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | 2.3.14 Monitoring and Evaluation |  | x |  |  | UNDP | SEAC, CICETE | MGD-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 5,000 |
| Participatory craft survey questionnaire improved, survey carried out in more villages and report published; SEAL training organized with more specific focus on crafts skills. | 2.3.17. Market assessment results | x |  |  |  | UNESCO | SEAC, China Arts and Crafts | MDG-F | Contract | 12,000 |
|  |  |  |  |  |  |  |  |  | Total | 12,000 |
|  | 2.3.18. Organize training workshops to introduce the UNESCO AWARD of Excellence programme (aka SEAL) | x | x | x | x | UNESCO | SEAC, China Arts and Crafts Association (CACA) | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 13,000 |
|  |  |  |  |  |  |  |  |  | Total | 18,000 |
|  | 2.3.19. Revise the participatory craft survey according to the local situation and organize training on the participatory craft survey methodology and content, disseminate the survey questionnaire and collect completed questionnaires for analysis | x | x | X | x | UNESCO | SEAC, CACA | MDG-F | Supplies | 2,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 12,000 |
|  |  |  |  |  |  |  |  |  | Other Direct Costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 2.3.20. Survey report drafted and published based on the participatory survey results and analysis | x | x | X | x | UNESCO | SEAC, CACA | MDG-F | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 8,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
|  | 2.3.21. Project review meeting organized to collect feedback from national, provincial and local stakeholders (government, craft-workers, craft entrepreneurs, craft associations etc.) on the project implementation and forging partnership among local stakeholders | x | x | X | x | UNESCO | SEAC, CACA | MDG-F | Supplies | 2,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 1,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 11,000 |
|  |  |  |  |  |  |  |  |  | Other Direct Costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | 2.3.22. Provide cultural expert to assist in the testing, local craft works participate in the national crafts fair | x | x | X | x | UNESCO | SEAC, CACA | MDG-F | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 7,000 |
|  | 2.3.23. Use regular communication tools (newsletter, website or magazine etc.) as exchange platform for discussion and sharing of information among stakeholders, produce advocacy materials of project activities | x | x | X | x | UNESCO | SEAC, CACA | MDG-F | Supplies | 3,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 9,000 |
|  |  |  |  |  |  |  |  |  | Total | 14,000 |
| Entrepreneurial and business development services training strategy developed and implementation initiated, need assessment completed | 2.3.25 Needs assessment and consultation at county level |  | x |  |  | UNIDO | SEAC | MGD-F | Personnel | 8,000 |
|  |  |  |  |  |  |  |  |  | Total | 8,000 |
|  | 2.3.26 Finalise market and product analysis; Dissemination workshop for the market and product analysis | x | x |  |  | UNIDO | SEAC | MDG-F | Personnel | 12,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 12,000 |
|  |  |  |  |  |  |  |  |  | Total | 24,000 |
|  | 2.3.27 Design and adaptation (including translation) including: Development plan and capacity building plan; Training design; Localize training; Translate training | × | × | x | x | UNIDO | SEAC | MGD-F | Supplies | 25,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 25,000 |
|  |  |  |  |  |  |  |  |  | Total | 50,000 |
|  | 2.3.28 Training of trainers |  | × | × | × | UNIDO | SEAC | MGD-F | Supplies | 3,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 12,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 33,000 |
|  |  |  |  |  |  |  |  |  | Other direct costs | 6,000 |
|  |  |  |  |  |  |  |  |  | Total | 54,000 |
|  | 2.3.29 Capacity building for business support services including: - Study tour for local artisans - Support to artisans for product innovation - Capacity building on Business Development Services (BDS) in cooperation with UNESCO and ILO where possible |  | x | x | x | UNIDO | SEAC | MDG_F | Supplies | 22,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 20,000 |
|  |  |  |  |  |  |  |  |  | Training | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 62,000 |
|  | 2.3.31 Monitoring and Evaluation |  | x | x | × | UNIDO | SEAC | MGD-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
| Joint Programme Coordinator (Funds to be administered by UNDP on behalf of UNRCO) | 188,529 |
| UN Resident Coordinator Office | 30,000 |
| Total Planned Budget without management fee | 2,220,399 |
| Management Fee for MDG-F (7%) | 155,428 |
| Grand-Total | 2,375,827 |