CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

31 March 2008

| Participating UN or Non-UN Organization: | UNWTO | UNCAPAHI Objective(s) covered: | 5. Public information and communication to support behaviour change 6. Continuity under pandemic conditions |
| --- | --- | --- | --- |
| Implementing Partner(s): | WHO, UNICEF, FAO, OIE, OCHA |
| Programme Number: | CFIA-A4 |
| Programme Title: | Targeted communications for travellers, the travel industry, and tourist destinations |
| Total Approved Programme Budget: | US$ 400,000 |
| Location: | Madrid, Spain |
| MC Approval Date: | 12 July 2007 |
| Programme Duration: | 12 Months | Starting Date: | August 2007 | Completion Date: | July 2008 |
| Funds Committed: | US$ 121,349.62 | Percentage of Approved: | 30.3% |
| Funds Disbursed: | US$ 19,047.00 | Percentage of Approved: | 4.8% |
| Expected Programme Duration: | 18 Months | Forecast Final Date: | January 2009 | Delay (Months): | 6 Months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Organizational set-up | Recruitment of staff completed and operational | 100% |
| Defining partner links | Campaign inception report developed, full strategic plan with details on tactical aspects on target to be completed April 2008 | 50% |
| Developing and setting up a campaign framework | Campaign inception report developed, full strategic plan with details on tactical aspects on target to be completed April 2008 | 50% |
| Defining local and national media contacts | Communication staff joined UNWTO February 2008. Evaluation of media databases underway. | 50% |
| Multiplying outreach through pro-bono work with PR companies | More suitable partners identified in order to ensure that the objectives are achieved in the most beneficial way. Consequently, this area has been delayed slightly. | 10% |
| Multiplying partner links and external network contacts | Campaign inception report developed and reviewed, full strategic plan with details on tactical aspects on target to be completed first week of April 2008 | 10% |
| Deploy instruments | Technical developments for www.sos.travel are fully underway. Microsoft handover planned for May 2008. Other instruments to be deployed according to plan. | 25% |

Qualitative achievements against outcomes and results:

Since the approval of the funds in August 2007, the focus for the remaining of 2007 was geared to the development of the planning phase with the aim of achieving the final objective in the most beneficial way. Strategies were re-identified and messages revised in order to make the best use of our external resources. Careful recruitment process began in September to identify the candidates with the most appropriate skills set and experience for implementing the project. After some minor technical issues involving visa issuance, and availability of the selected candidates, issues were resolved, and the team and resources were ready for full deployment. An ambitious timeline has been developed that covers delivery of the full scope of the project deliverables by year’s end with limited follow-up activity early in the first quarter of 2009. Therefore, in view of the above, the planning phase has been extended to 6 months to optimize the deliverables and maximizing the outputs. Project is again back on schedule.

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.