CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

as of 31 December  2008

| Participating UN or Non-UN Organization: | World Food Programme | UNCAPAHI Objective(s) covered: | Objective: Humanitarian Common Services Support |
| --- | --- | --- | --- |
| Implementing Partner(s): | NA |
| Programme Number: | CFIA-A1 |
| Programme Title: | Development of a Logistics Concept of Operations for Humanitarian Activities in a Pandemic Environment |
| Total Approved Programme Budget: | US$_400,000____ |
| Location: | Africa; Kenya & Mombassa Corridor, Southern Africa Corridor Asia: Pakistan and Afghanistan Indonesia and South East Asia Cluster |
| MC Approval Date: | 12 July 2008 |
| Programme Duration: | Initial 12 Months | Starting Date: | 14 July 2007 | Completion Date: | 26 July 2008 |
| Funds Committed: | US$ 319,566 | Percentage of Approved: | 80% |
| Funds Disbursed: | US$ 219,566 | Percentage of Approved: | 54% |
| Expected Programme Duration: | 21 Months | Forecast Final Date: | 31 March 2009 | Delay (Months): | 9 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Continuity under Pandemic Conditions Ensuring the community of essential social, economic and governance services, and effective implementation of humanitarian relief under pandemic conditions. | The Pandemic Logistics Corridor Capacity Assessment (PLCCA) of the eastern and southern African logistics corridor has been completed. The PLCCA of the North-South [Economic] Corridor in south east Asia is in progress. Joint stakeholder hazard and risk analysis for the eastern and southern African and North- South Economic Logistics corridor have been undertaken. | 85% |
| Support provided to the preparation of a response plan in Southern Africa and South East Asia | Awareness raising efforts, which have resulted in the increased involvement of Government and other key stakeholders are on going. | 90% |
| Qualitative achievements against outcomes and results: |
| WFP has completed the Pandemic Logistics Corridor Capacity Assessment ( PLCCA) of the eastern and southern African logistics corridors. The assessment provides an analysis of transport modes and the capacity of the logistic networks, including a pandemic impact analysis on the logistic networks. An PLCCA for the North-South [Economic] Corridor in south east Asia is due to be completed shortly. Following the completion of the PLCCAs, together with national planning maturing, it is envisioned that a more detailed supply chain analysis will be undertaken during the course of the next year. The project has resulted in intensified collaboration of a network of stakeholders, which includes UN agencies, NGOs, IFRC, both the national and local authorities as well as critical partners from the commercial sector in the area of pandemic preparedness. |