CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

As of 30 September 2008

| Participating UN or Non-UN Organization: | UNDP | UNCAPAHI Objective(s) covered: | Objective 4 |
| --- | --- | --- | --- |
| Implementing Partner(s): | UN Resident Coordinator’s Offices supported by UNDP Country Offices |
| Programme Number: | CFIA-A3 |
| Programme Title: | Support to Coordination of Avian and Human Influenza Activities |
| Total Approved Programme Budget: | US$400,000 |
| Location: | Selected countries on the African and Asian continents, with a special focus on Burkina Faso, Egypt, Niger and Indonesia |
| MC Approval Date: | 18 July 2007 |
| Programme Duration: | 12 months | Starting Date: | 18 July 2007 | Completion Date: | 18 July 2009 |
| Funds Committed: |  | Percentage of Approved: |  |
| Funds Disbursed: |  | Percentage of Approved: |  |
| Expected Programme Duration: | Extended to 2 years | Forecast Final Date: | 18 July 2009 | Delay (Months): |  |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| AHI Coordination Egypt | AHI specialist recruited for the RC office Inter-ministerial conference supported for Q3 2008 | 70% |
| AHI Coordination Indonesia | AHI specialist recruited for the RC office | 60% |
| AHI Coordination Nigeria | Study on the socio economic impact of HPAI on the poultry industry Strengthen the UN coordination mechanism; Community capacity for managing the epidemic (cross border collaboration with Benin); Capacity for livestock surveillance at the local government level | 40% |
| Qualitative achievements against outcomes and results: |
| The support to the inter-ministerial conference to be held in Egypt through the office of the Resident Coordinator of the UNCT in Egypt is the highlight activity of this quarter. |