CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

As of September 30, 2008

| Participating UN or Non-UN Organization: | UNWTO | UNCAPAHI Objective(s) covered: | Obj. 5: Public Information and communication to support behaviour change Obj. 6: Continuity under pandemic conditions |
| --- | --- | --- | --- |
| Implementing Partner(s): | WHO, UNICEF, FAO, OIE, OCHA |
| Programme Number: | CFIA-A4 |
| Programme Title: | Targeted Communications for travellers, the travel industry, and tourist destinations |
| Total Approved Programme Budget: | US$ 400,000 |
| Location: | Madrid, Spain |
| MC Approval Date: | 12 July 2007 |
| Programme Duration: | 12 months | Starting Date: | August 2007 | Completion Date: | July 2008 |
| Funds Committed: | US$ 158,978 | Percentage of Approved: | 39.7% |
| Funds Disbursed: | US$ 86,294 | Percentage of Approved: | 21.5% |
| Expected Programme Duration: | 18 months | Forecast Final Date: | January 2009 | Delay (Months): | 6 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Organizational set-up | Recruitment of staff completed and operational by Feb 2008 | 100% |
| Defining partner links | No major updates in this reporting period. Campaign inception report developed March 2008, Strategic/tactical plan finalized June 2008; Some plan refinement may take place in execution phase later in the year. | 80% |
| Developing and setting up a campaign framework | No major updates in this reporting period. Campaign inception report developed March 2008; Strategic/tactical plan finalized June 2008; Some plan refinement may take place in execution phase. Internal and interagency network communications active and regular, public communication will coincide with website first release later this year. | 80% |
| Defining local and national media contacts | Media database contracted and active as of July. | 90% |
| Multiplying outreach through pro-bono work with PR companies | More suitable partners identified in order to ensure that the objectives are achieved, pursuing relationships. This area continues to be slightly delayed | 20% |
| Multiplying partner links and external network contacts | Campaign inception report developed March 2008, Strategic/tactical plan finalized June 2008; Internal and interagency network communications active and regular. | 65% |
| Deploy instruments | All functional website requirements have been defined and technical consultant was identified and has initiated the development phase. Alerting function and first site release to be delivered before end of 2008. Toolkit to be launched Q1 2009. Crisis-specific communication instruments in development, and to be deployed according to plan. | 45% |
| Qualitative achievements against outcomes and results: |
| During this reporting period, UNWTO has continued with its workplan according to the strategic and tactical plan developed for the project. This plan covers, among other aspects, identification of partnerships and networks, the approach to the media, and development of communication materials. Most executional communication aspects are planned for the next reporting period (Oct-Dec) during which some plan refinement may take place. UNWTO has been continuing to provide regular targeted communication with core tourism and travel associations and its Tourism Emergency Response Network (TERN) related to the current situation of Avian and Human Influenza, guidelines and best practices. Other instruments will be deployed according to plan. On the media side, a media database was established in July 2008 and since then has been in use by our communication staff. Additionally, select network-building efforts are currently active, including the coordination of a meeting of the TERN group planned for fall and a regular project update sent via email to key project stakeholders. |

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.