CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

31 December 2008

| Participating UN or Non-UN Organization: | World Food Programme | UNCAPAHI Objective(s) covered: | Objectives 2,4,6 and 7 |
| --- | --- | --- | --- |
| Implementing Partner(s): | N/A |
| Programme Number: | CFIA- B3 |
| Programme Title: | World Food Programme Pandemic Preparedness and Planning |
| Total Approved Programme Budget: | US$ 4,205,100 |
| Location: | Corporate with focus on 9 priority countries and 2 pandemic regional logistic capacity assessments |
| MC Approval Date: | 20 February 2008 |
| Programme Duration: | 12 Months | Starting Date: | 04/03/2008* ( 01/10/2007) | Completion Date: | 31/12/2008 |
| Funds Committed: | US$ 3,447,000 | Percentage of Approved: | 82 % |
| Funds Disbursed: | US$ 2,226,784 | Percentage of Approved: | 53% |
| Expected Programme Duration: | 19 Months | Forecast Final Date: | 30/04/2009 | Delay (Months): | 7 Months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Operational contingency plans in place in 9 priority countries by the end of 2008 | Draft contingency plans developed for Ethiopia, Indonesia, Egypt, Cambodia, Laos, Kenya and Uganda. Draft contingency plans in preparation for Nigeria, Mali and Bangladesh. | 90% |
| Transport alternatives of humanitarian goods along the main delivery corridors during a pandemic properly analysed and assessed; integration of the project with other ongoing preparedness measures. | Pandemic Logistics Corridor Capacity Assessment (PLCCA) of the eastern and southern African logistics corridor have been completed. The PLCCA of the North-South [Economic] Corridor in south east Asia is in progress. | 85% |
| Logistics training programme developed and key operational staff (WFP and non WFP; WHO, UNHCR, UNICEF, IFRC and selected NGOs) trained on Standard Operating Procedures (SOPs) in immediate response for “containment / quarantined operations”. | A Pandemic Logistics and Learning Exercise (P2LX) training, with technical support of WHO took place 24-30 November 2008. The exercise resulted in the identification of gaps in pandemic-specific guidelines for logistics operations. Over 220 participants were familiarized with basic procedures for logistics response in a pandemic environment, including sea and air ports as well as surface operations. A series of thematic focus groups have been established to address recommendations ensuring from the training. A Logistic CONOPS has been drafted. | 100% |
| Improved pandemic preparedness planning across the organization. | Joint UNICEF, UNDP and WFP training within the framework of Pandemic Preparedness rolled out 100% of WFP country offices. | 100% |
| Impact of an influenza pandemic on the livelihood of vulnerable groups in priority countries analysed and programme response guidance developed. In close collaboration with sister UN agencies, the Red Cross Movement, NGOs and national authorities, the project will develop guidelines for the use of food assistance in a pandemic environment | WFP has analyzed its food security and livelihood programme and identified additional areas of collaboration with sister UN agencies, the Red Cross Movement, NGOs and national authorities in addition to its linkages with the H2P process. | 60% |
| Qualitative achievements against outcomes and results: |
| WFP has completed the Pandemic Logistics Corridor Capacity Assessment ( PLCCA) East and Southern Africa Logistics Corridors. The PLCCA for the North-South [Economic] Corridor in south east Asia is due to be completed shortly. The assessments provide an analysis of transport modes and the capacity of the logistic networks, including a pandemic impact analysis on the logistic networks. In November 2008, WFP conducted a seven-day field based simulation in Malaysia, with technical support from WHO and operational support from Mercy Malaysia. Over 220 participants, including representatives from 20 different national entities, UN agencies, Red crescent, US Centre for Disease Control, NGOs and military personnel took part in the testing process of UN system pandemic preparedness for port, airport and surface operations procedures. Other assessment and food distribution exercise were conducted, and an inter-agency lessons learned team identified gaps in procedures and areas for improvement. A series of thematic focus groups bringing together stakeholders have been established to address recommendations which were identified during the exercise. WFP continues to work in synergy with the USAID funded, Humanitarian Pandemic Preparedness (H2P) initiative. WFP is expected to incorporate, where appropriate, the December 2008 outcomes of the H2P initiative into the food security and livelihood analysis component of this project. |