CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

As of 15 January 2009

| Participating UN or Non-UN Organization: | UNITED NATIONS HIGH COMMISSIONER FOR REFUGEES UNHCR | UNCAPAHI Objective(s) covered: | Obj 3: Human Health Obj 5: Communication: Public Information & Supporting Behavior Change Obj 6: Continuity under Pandemic Conditions |
| --- | --- | --- | --- |
| Implementing Partner(s): | Association of Medical Doctors of Asia (AMDA)-Nepal; Committee for Coordination of Services to Displaced Persons in Thailand UNHCR Direct Implementation in 20 countries |
| Programme Number: | CFIA -B5 |
| Programme Title: | Avian and Human Influenza Preparedness and Response in Refugee Setting |
| Total Approved Programme Budget: | US$ 2,970,000 |
| Location: | Countries hosting refugee communities assisted in camps and in an urban situation |
| MC Approval Date: | 20 February 2008 |
| Programme Duration: | 12 months | Starting Date: | 01 April 2008 | Completion Date: | 02/04/2009 |
| Funds Committed: | US$ ____ ______________ | Percentage of Approved: |  |
| Funds Disbursed: | US$_____ ______________ | Percentage of Approved: |  |
| Expected Programme Duration: | 12 months | Forecast Final Date: | 02/04/2009 | Delay (Months): | N/a |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Inclusion of Refugees into National Contingency Plans | In all countries, except in Egypt, Burundi, Rwand and DRC, Refugees are not yet included into National Contingency Plans. | 5 % |
| Systems for surveillance of influenza-like illness through strengthening health services. Strengthen of outbreak control and response task force in the camps. Stock of drugs and medical equipment in place. | Reporting systems, coordination and surveillance mechanisms at camp level put in place during precedent exercise are reviewed and assessed during the missions of the Regional AHI Coordinators in the different refugee camps. Training on Health Information System and epidemiological surveillance continued during second mission of the Regional AHI Coordinators in the camps The distribution of medical equipment and drugs purchased in 2007 has been completed in the camps at health post level in most of the countries targeted | 85% 85% 95 % |
| Refugees and other population of concern to UNHCR are properly informed and encouraged to adopt healthy behaviour | Translation of public awareness documents into appropriate languages for refugees has been done in almost all the camps where it was necessary Training have been organized and conducted for camps’ staff and refugees in the following countries: Mozambique, Namibia, Zambia, Nigeria, Sierra Leone, Dadaab, Tanzania, Uganda, Egypt, Rwanda, Burundi, Nepal, Myanmar, Pakistan and Myanmar. | 90% 80% |
| Contingency Plans at camp level. Logistics and Food pipe line contingency planning with WFP Improvement and enhancement of water delivery capacity and sanitation conditions in view of creating optimal conditions for business continuity at camp level. AHI Coordination in Geneva, | Contingency Planning has been initiated in several camps in Kenya, in Rwanda, in Burundi, Ethiopia, Uganda, Tanzania, Nepal, and Bangladesh. Efforts are still made to mobilize IPs. And to assess real operationality. UNHCR participated in a WFP’s logistic workshop for developing coordination in case of a crisis in South Africa region. In other regions, coordinators are liaising with WFP counterparts for developing same mechanisms. In Botswana, Burundi, Ethiopia, Kenya, Malawi, Mozambique, Rwanda, Sudan, Tanzania, Uganda, Zambia, Zimbabwe, Bangladesh and Myanmar, water and sanitation projects are under progress. Rates of implementation varies from 60% to 90% AHI Coordination is operational in HIV and PH Section in UNHCR HQ. | 85% 75% 95% 100% |
| Qualitative achievements against outcomes and results: |
| Pandemic Preparedness Program, started in 2007, has continued throughout the year 2008 in the different countries where UNHCR has the responsibility of Refugee assisted camps. Missions of the Regional Coordinators to the different countries of their respective regions continued to take place according to approved work plans and depending on security situation. During the last quarter, second or third missions took place in Malawi, Djibouti, Tanzania, Yemen, Rwanda and Burundi. Refugee camps in countries with high security problems, like Chad, Algeria and Zimbabwe remained without mission during 2009. A mission took place in Pakistan, but only in regional capitals, not to the camps. Achievements in the different activities of the project can be reported as follows: 1/ Refugees included in National Plans. Despite efforts from our Regional Coordinators and from UNHCR representations , only DRC, Egypt, Burundi and Rwanda have formally included Refugee Communities into their Contingency Plans: This will be a major objective for our 2009 program requesting strong support of our colleagues of PIC OCHA to get full support of UNCT in the following countries: Ugada, Djibouti, East Sudan, ethiopia, Kenya, Tanzania, Yemen, Algeria, Bengladesh, Nepal, Myanmar, Pakistan, Thailand, Namibia, Zimbabwe, Zambia, Mozambique and Malawi. 2/ Medical supply and protection equipment. The distribution and the storage of medical supplies and protection equipment have been finalized at the different health posts in the camps. Storage conditions have been reviewed and refreshing drug management training has been completed In all the camps provided with equipment and supply. There are 3 countries with refugee camps assisted by HCR, Chad, Pakistan and Myanmar, where medical supplies and protection equipment have not been purchased. In Chad and Pakistan, for security reasons, missions have not been completed, and procurement for Myanmar should be initiated in 2009. 3/ Outbreak control Outbreak response task forces are in place in most of the camps with good operational capacities, except in some countries (Zambia, Zimbabwe, Namibia, Myanmar, Pakistan, DRC, Ethiopia and East Sudan) where efforts will be concentrated in 2009. Contingency planning process is on going with our implementing partners and has already reached an operational status except in the following countries: Zambia, Zimbabwe, Pakistan, Myanmar, DRC, Yemen, Algeria, Ethiopia and East Sudan. For maintaining a good level of vigilance of the task force and for regular assessment of the operationality of the contingency plans, focal points have been identified within local staff of Implementing Partners in camps in most of the countries visited, with exception of the following ones: East Sudan, Ethiopia, Algeria, DRC, Myanmar, Pakistan, Zimbabwe and ¦Zambia. 4/ Public Information and awareness campaigns. During every mission in the different camps, refreshing trainings and information campaigns sessions have been done. During these courses, specific emphasis has been put on non medical response at community level: social distanciation and preventive behaviour. In Yemen, Algeria, Pakistan and Bangladesh more campaigns have to be launched Communication material have been made accessible to Refugees in their own nativ language when necessary with the exception of Uganda, east Sudan, Ethiopia, Tanzania, Yemen, Algeria, Pakistan and Myanmar. We will seek more support and assistance from UNICEF in these countries. 5/ Business Continuity. Food UNHCR participated in coordination activities initiated by WFP at regional level for setting up operational mechanisms for sustaining logistics and food delivery in case of crisis. Regular meetings take place between WFP and HCR headquarters for exchange of informations and planning of workshops. Full coordination and common plans are not yet ready in the following countries: Mozambique, Ethiopia, Algeria, and Yemen. In some countries, for various reasons, refugees don not receive food assistance from WFP: Zimbabwe, Egypt, Pakistan, Thailand and Myanmar. Water and Sanitation After the large review of the existing water and sanitation facilities in all different camps with the perspective of creating optimal conditions for business continuity at camp, projects have been are implemented by our local partners and monitored by UNHCR water and sanitation Engineers under the supervision of the Coordinators. Projects are completed in 14 different countrie: Botswana, Burundi, Ethiopia, Kenya, Malawi, Mozambique, Rwanda, Sudan, Tanzania, Uganda, Zambia, Zimbabwe, Bangladesh and Myanmar. Implementation of the project is under completion in other countries: Nepal Uganda, DRC, Yemen, Algeria, Djibouti, Zambia, Eastern Sudan, Rwanda and Myanmar. |

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.