CFSN Color-Coded Annual Work Plan for the first Year of Implementation

Draft for Quarter 2 2010

Green      = Completed, Yellow      = Ongoing, Red      = Delayed, Purple      = Not Started.

| Annual targets | Activity | Time Frame 2010 | UN Agency | Responsible Party | Planned Budget |
| --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Source of funding | Budget description | Total amount |
| JP Output 1.1 Food security situation in pilot counties understood by policymakers |
| 1.1.1 Accurate data on food security, vulnerability in the six pilot counties available | 1. survey preparedness | X |  |  |  | WFP | MOA, CAAS | MDG-F | Contract | 1,466 |
|  | 2. sampling and questionnaire development |  | X |  |  |  |  |  | Contract | 11,555 |
|  |  |  |  |  |  |  |  |  | Training (intl. travel) | 27,662 |
|  | 3. data collection in six counties |  |  | X |  |  |  |  | Contract | 54,161 |
|  | 4.data analysis and reporting |  |  |  | X |  |  |  | Contract | 20,156 |
| 1.1.2 Data of under nutrition in the three pilot counties available | 1. micronutrient survey in pilot counties |  | X | X | X | UNICEF | CDC, MOH | MDG-F | contract | 96,000 |
|  | 2. Procurement of Microcurvettes to test hemoglobin concentration. |  | X |  |  | UNICEF | UNICEF | MDG-F | contract | 5,000 |
| JP Output 1.2 Targeting and monitoring improved through availability of an improved national database on nutritional status of women and children |
| Nutritional databases reviewed and revised and trialed in six counties by Quarter 4, Year 1. | Review existing nutritional databases. Prepare tools to improve data and trial their usefulness in the six pilot counties. Build capacity through training. |  |  | X | X | WHO | MOH, CDC, CIP | MDG-F | Personnel | 15,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 53,000 |
|  |  |  |  |  |  |  |  |  | Training | 10,000 |
|  |  |  |  |  |  |  |  |  | ODC | 2,000 |
| JP Output 2.1 Exclusive breastfeeding increased and safe complementary food and micronutrient supplementation provision expanded in pilot countries |
| 2.1.1 All health personnel at county and province level trained in preparation and use of complementary food supplement. | 1. Procurement and distribution of Complementary Food Supplements (CFS) for 3 UNICEF intervention counties. |  | X | X | X | UNICEF | CDC, MOH | MDG-F | contract | 146,075 |
|  | 2. Training and communication guidelines for health staff on knowledge of complementary feeding and CFS |  |  | X | X |  |  |  | contract | 40,000 |
|  | 3. Communication activities conducted by village doctors for the consumption and compliance of CFS |  |  |  | X |  |  |  | contract | 30,000 |
| 2.1.2 Data on infant food availability and on infant feeding preferences, knowledge and practice coverage available. | 1. Conduct baseline standardized coverage survey. (WHO/UNICEF) |  |  | X |  | WHO | CDC, MOH | MDG-F | Contracts | 40,000 |
|  | 2. Conduct focus group discussion on breastfeeding preferences. |  |  | X | X |  | CIP | MDG-F | Contracts | 10,000 |
|  | 3. Conduct focused ethnographic study on complementary food availability and preferences. |  |  | X | X |  |  |  | Contracts | 20,000 |
|  | 4. Conduct linear programming. |  |  | X | X |  |  |  | Contracts | 10,000 |
| 2.1.3 Survey businesses to determine the baseline of the proportion of businesses providing the right, and develop and trial advocacy, demonstration and other means of engaging businesses will be trialled in one of the pilot counties in year one | 1. Consult with Wuding County Trade Union on the baseline research and 1st-year-workplan under the support of ACFTU | X |  |  |  | ILO | ACFTU | MDG-F | Personnel | 19,000 |
|  | 2. Design the survey to determine the baseline of the proportion of businesses providing the right to breastfeed |  | X |  |  |  |  |  | Contracts | 20,000 |
|  | 3. Submit the draft of the survey questionnaire for ILO and other agencies’ comments and finalize the questionnaire accordingly |  | X |  |  |  |  |  | Training | 14,000 |
|  | 4. Conduct the survey in Wuding County under the support of Wuding TU and prepare 1st draft |  |  | X |  |  |  |  |  |  |
|  | 5. Submit the final report |  |  |  | X |  |  |  | SCET | 3,000 |
|  | 6. Carry out the capacity building on maternity protection at workplaces in Wuding County |  |  |  | X |  |  |  | ODC | 4,000 |
| JP Output 2.2 Household dietary intake of micronutrient-rich, locally-available food increased in 3 pilot counties |
| Baseline study of dietary intake conducted in 3 counties and training materials developed and applied in raising awareness of the importance of local production and consumption of micronutrient rich food and knowledge improved in 3 counties. | 1. Prepare for and conduct the baseline survey. | X | X |  |  | FAO | MOA | MDG-F | Personnel ODC Contracts Training SECT | 78,000 10,000 75,000 40,000 17,000 |
|  | 2. Laboratory analyses conducted. |  |  | X | X |  |  |  |  |  |
|  | 3. Training needs identified and training materials developed. |  |  | X | X |  |  |  |  |  |
| JP Output 2.3 Gather evidence and conduct a risk analysis as a basis for a national food fortification plan |
| Evidence on the effectiveness of in-home food fortification gather and the risk analysis conducted. The plan of in-home food fortification gathered. | 1.Experts meeting to discuss the strategy for food fortification in China including in-home fortification |  | X |  |  | UNICEF | CDC, MOH | MDG-F | contract | 5,000 |
|  | 2. Monitoring and evaluation the effectiveness and safety of in-home food fortification |  |  |  | X |  |  |  | contract | 25,000 |
|  | 3. Quality control of in-home food fortification |  |  | X | X |  |  |  | contract | 5,000 |
| JP Output 3.1 Food production for children made safer in pilot areas |
| 3.1.1 4-6 enterprises in 2 provinces trained in HACCP trained by year 3 | 1.Carry out on site survey and select five pilot enterprises | X |  |  |  | UNIDO | CNIS-AQSIQ | MDG-F | Supplies Personnel Training Contracts ODC | 15,000 22,000 22,000 35,000 6,000 |
|  | 2.Develop training materials and plan of action |  | X |  |  |  |  |  |  |  |
|  | 3.Deliver first training on at five pilot enterprises |  |  | X | X |  |  |  |  |  |
|  | 4.Conduct mid-term evaluation |  |  |  | X |  |  |  |  |  |
| 3.1.2 Four laboratories trained in standardization and management capacity related to food safety and quality by Year 3 | 1.Conduct on site surveys and capacity assessment and select four labs | X |  |  |  | UNIDO | CNIS-AQSIQ | MDG-F | Supplies Personnel Training Contracts ODC | 15,000 14,000 15,000 25,000 1,000 |
|  | 2.Conduct Gap analysis and prepare training materials combining ISO17025 with gap analysis. |  | X |  |  |  |  |  |  |  |
|  | 3.Carry out on-site training accreditation criteria & estimation of measurement uncertainty |  |  | X |  |  |  |  |  |  |
|  | 4.Provide first training on compilation of quality manual and procedure documentation |  |  |  | X |  |  |  |  |  |
| 3.1.3 Thirty inspectors trained in standardization and management capacity related to food safety and quality by Year 3 | 1.Select 30 inspectors and conduct assessment of their capacity | X |  |  |  | UNIDO | CNIS-AQSIQ | MDG-F | Supplies Personnel Training Contracts ODC | 10,000 12,000 12,000 15,000 1,000 |
|  | 2.Develop training manuals focused on management and operational capacities. |  | X | X |  |  |  |  |  |  |
|  | 3.Carry out first basic knowledge training |  |  |  | X |  |  |  |  |  |
| 3.1.4 Guidelines on safe and healthy work processes in industries producing child nutrition products developed, applied in 8 businesses and used and enforced by 50 OSH inspectors by Year 3 | 1.To draft work plan | X |  |  |  | ILO | NCIC, SAWS | MDG-F | Personnel | 35,000 |
|  | 2.Field visits to select 5 pilot enterprises |  | X |  |  |  |  |  | Contracts | 15,000 |
|  | 3.Develop training materials Outline |  | X |  |  |  |  |  | Training | 20,000 |
|  | 4.Develop enterprises training materials |  |  | X |  |  |  |  | SCET | 3,000 |
|  | 5.Provide training at 5 pilot enterprises |  |  |  | X |  |  |  | ODC | 7,000 |
|  | 6.The training materials will be further improved |  |  |  | X |  |  |  |  |  |
| 3.1.5 Management plans and policies advise developed/ formulated for target sectors in pilot areas by Year 3 | 1.Select local counterparts and partners for cooperation. | X |  |  |  | UNIDO | CNIS-AQSIQ | MDG-F | Personnel | 13,000 |
|  | 2.Survey production and inspection levels. |  | X |  |  |  |  |  | Training | 10,000 |
|  | 3.Begin dialogue with pilot governments and experts to develop framework. |  |  | X |  |  |  |  | Contracts | 25,000 |
|  | 4.Draft detailed content |  |  |  | X |  |  |  | ODC | 2,000 |
| Output 3.2 Handling and preparation of food for infants and children made safer |
| 3.2.1 Year 1 output: Develop a food safety training model targeted at women and children in rural areas. | 1.Develop questionnaire to assess current knowledge of target groups | X | X |  |  | WHO | NCHIS, MOH | MDG-F | Personnel Contracts Training ODC | 10,000 50,000 10,000 6,000 |
|  | Apply questionnaire in project counties |  | X | X |  |  |  |  |  |  |
|  | Develop training material based on outcome of questionnaire |  |  | X | X |  |  |  |  |  |
| 3.2.2 At least 50% of the schools in selected target counties will integrate nutrition and food safety into school health education curriculum with 100% of their science and health education teachers as well as head teachers in pilot schools trained in the use of newly developed supplementary materials in classrooms by Year 3 | 1.Collection of national policy documents and curriculum materials; 2.needs analysis of rapid assessment of teaching and learning methods and materials in health and nutrition education in schools; 3.consultation meetings with experts, teachers, parents and community members and development of outline for supplementary materials |  | X | X | X | UNESCO | MoE School of Public Health of China Central South University | MDG-F | Personnel Contract ODC | 23,000 27,000 2,000 |
| Output 3.3 New national food safety law successfully implemented |
| 3.3.1 Regulators, legal personnel and other key stakeholders including women and local communities become familiar with the details of the new food safety law. | 1. Launch of the Project and Opening Ceremony of the Research Center for China Food Safety Law |  | X | X |  | UNDP | CICETE，CLS | MDG-F | Contracts | 16,600 |
|  | 2. Training on food safety law and regulations |  |  | X | X |  |  |  | Training Contracts | 6,500 7,500 |
|  | 3. Launch of China Food Safety Law Website |  | X | X | X |  |  |  | Contracts ODC | 8,500 1,000 |
|  | 4. Establishment of the China Food Safety Law Magazine (bimonthly publication) |  | X | X | X |  |  |  | Personnel ODC | 2,100 21,200 |
|  | 5. National knowledge contest on the Food Safety Law |  |  | X |  |  |  |  | Contracts | 20,200 |
|  | 6. Pilot project on the Food Safety Supervision Mechanism in Shangluo City, Shaanxi Province |  |  | X | X |  |  |  | Personnel ODC | 10,700 21,200 |
|  | 7. Summit on China Food Law. |  |  | X |  |  |  |  | Contracts | 20,700 |
|  | 8. Domestic and international field studies on legal issues regarding food safety |  |  | X | X |  |  |  | Personnel ODC | 16,000 24,500 |
|  | 9. Consultation provided by invited experts on food safety law throughout the year |  | X | X | X |  |  |  | Personnel | 23,300 |
| 3.3.2 Data on awareness of new food safety law collected | Survey on awareness of new food safety law, needs for food safety services/support, through baseline study, questionnaire and in-depth interviews in women’s groups and local communities | X | X | X | X | UNESCO | ACWF | MDG-F | Personnel Contract Training ODC | 5,500 10,000 9,000 500 |
| 3.3.3 Food safety emergency and complaints system introduced or improved | 1. Review the existing work on food emergency and food complaints system in the pilot counties and identify needs to improve the systems. |  | X | X |  | WHO | NCHIS, MOH | MDG-F | Personnel Contract Training ODC | 3,000 13,000 2,000 600 |
|  | 2. Develop training program |  |  | X |  |  |  |  |  |  |
|  | 3. Develop guidelines for the establishment of such systems at county levels |  |  |  | X |  |  |  |  |  |
| 3.3.4 Training materials on food safety law for government regulators and food producers and traders developed. Training conducted at provincial level. | 1. Review the existing knowledge of regulatory enforcement agents and food producers and traders in the pilot counties and identify the training needs. |  | X |  |  | WHO | NCHIS, MOH | MDG-F | Personnel Contract Training ODC | 15,000 40,000 15,000 3,000 |
|  | 2. Develop training materials on the new food safety law. |  |  | X |  |  |  |  |  |  |
|  | 3. Conduct training at provinces |  |  | X | X |  |  |  |  |  |
| JP Output 4.1 Result incorporated in an advocacy package and used to orient key government officials and media on nutrition and child food safety |
| Develop advocacy strategy and plan for key bottlenecks to improve nutrition of women and children in China | 1. Launching meeting of the nutrition project |  |  | X |  | UNICEF | CDC, MOH | MDG-F | Contract | 20,000 |
|  | 2. Development and printing of advocacy package for in-home food fortification |  |  | X | X |  |  |  | Contract | 15,000 |
| JP Output 4.2 Media training of at least 100 journalists in pilot counties |
| Baseline assessment conducted and two journalist training workshops organized by Quarter 4, Year 1. | 1. Develop a baseline assessment; 2.Develop journalist training manual; 3.Train 60 journalists from 4 target counties. |  | X | X | X | UNESCO | SARFT Training Centre | MDG-F | Personnel Contract ODC | 11,000 48,000 1,000 |
| Project preparation / formulation (funds administered by UNDP) | 20,000 |
| Programme Coordinator (funds administered by WHO) | 80,000 |
| PMO budget (funds administered by WHO) | 30,000 |
| RC Office (funds administered by UNDP) | 20,000 |
| Total Planned Budget without management fee | 2,059,075 |
| Management fee for MDGF (7%) | 144,135 |
| Grand total | 2,203,210 |