**China**

|  |  |
| --- | --- |
| **Programme Title:** | Improving Nutrition Food Safety and Food Security for China's most vulnerable Women and Children |
| **Programme number & MDTF ref:** | MDGF-1991-I-CHN (67235) |
| **Window:** | Children, Food Security & Nutrition |
| **Approved Budget by NSC (US$):** | 6 million |
| **Participating Organizations:** | UNICEF, WHO, WFP, UNIDO, UNDP, ILO, FAO, UNESCO |
| **First Tranche transferred on:** | 4-Dec-2009 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Baseline data finished. Procurement of micronutrients and associated training materials completed. Survey on infant food practices and availability done. National code of breast milk substitutes revised. The maternity protection promoted at enterprises. Survey of household available micronutrient rich food completed and local famers were trained. Training in the production of safe food for children conducted in pilot areas. Survey on handling of food for children finished and training materials completed. Policy analysis and field work on nutrition and food safety education in school conducted and an outline of supplementary teaching and learning materials prepared.The first legal research center on Food Safety in China established. Web site for enforcement of National food Safety Law was set up. 64 journalists trained in child nutrition issues. |
|  |
| **Problems and lessons learned:** |
| UN Agency coordination (too many and different regulations, no specific fund for joint activity). Coordination within government (too many agencies, lack of interagency coordination mechanism). External to JP (drought, quickly changing economy and policy). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** No |

CHARTS & FIGURES

As of 31 December 2010

