**China**

|  |  |
| --- | --- |
| **Programme Title:** | Protecting and Promoting the Rights of China's Vulnerable Young Migrants |
| **Programme number & MDTF ref:** | MDGF-1880-H-CHN Protect/Promot (67197) |
| **Window:** | Youth, Employment & Migration |
| **Approved Budget by NSC (US$):** | 6.6 million |
| **Participating Organizations:** | UNDP, WHO, UNIFEM, UNICEF, UNESCO, ILO, UNFPA |
| **First Tranche transferred on:** | 11-Feb-2009 |
| **Second Tranche transferred on:** | 19-Feb-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:**Web based information platform on Youth Employment and Migration (YEM) launched. The platform will become part of the ChineseAcademy of Social Science (CASS) Centre for Migration Research thus ensuring its continuing usage beyond the JP. Indicator system to measure urban social inclusion for migrants developed. Policy framework for enhancing CSOs’engagement in promoting social protection and services for migrants drafted. YEM university volunteers tutoring young migrant students experiences contributed to a newly launched national programme and were shared with party Youth League committees of 31 provinces. Pre-vocational training courses developed and tested in three pilot sites. Life skills training package developed, distributed and tested at 35 pilot sites, and formed part of the School-based Curriculum in Cangzhou’s 10 pilot schools. YEM’s SOP for registering migrant children developed and being implemented in 3 pilot sites. Pilot one-stop community Centers started providing services in an integrated manner. Youth - and migrant-friendly services provided in pilot community health centers. Training delivered to relevant government officials and grassroots level service providers and awareness raising campaigns among young migrants and urban residents carried out in pilot sites. |
|  |
| **Problems and lessons learned:** |
|  |
| UN Agency coordination (regulations). Coordination within government (too many actors). JP design issues (too short implementation time).  |
|  |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

