**Colombia**

|  |  |
| --- | --- |
| **Programme Title:**  | Strengthening local capacities for peace-building in the Department of Nariño |
| **Programme number & MDTF ref:** | MDGF-1964-F-COL Strengthening (67227) |
| **Window:** | Conflict Prevention & Peacebuilding |
| **Approved Budget by NSC (US$):** | 7 million |
| **Participating Organizations:** | FAO, UNDP, UNHCR, UNICEF, UNIFEM |
| **First Tranche transferred on:** | 2-Sep-2009 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Integrated service plan for displaced population completed. Sub-regional human rights action plan developed. Pilot treatment and transformation plan for conflicts finalized. An early warning system to monitor potential crisis´ in place. Training provided in administrative and managerial capabilities, public policies and programmes, human rights and forced migration and gender. Two pilot communities victims of violence, chosen to develop a historic memory.  |
|  |
| **Problems and lessons learned:** |
|  |
| UN Agency coordination Coordination with Government Coordination within Government JP design issues (lack of communications strat.).  |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** None |

CHARTS & FIGURES

As of 31 December 2010

