**Colombia**

|  |  |
| --- | --- |
| **Programme Title:**  | Integration of EcoSystems and Adaptation to Climate Change |
| **Programme number & MDTF ref:** | MDGF-1759-E-COL Env Climate (67172) |
| **Window:** | Environment & Climate Change |
| **Approved Budget by NSC (US$):** | 4 million |
| **Participating Organizations:** | FAO, PAHO/WHO, UNDP, UNICEF |
| **First Tranche transferred on:** | 10-Mar-2008 |
| **Second Tranche transferred on:** | 28-Sep-2009 |
| **Third Tranche transferred on:** | 26-Aug-2010 |
|  |  |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Vulnerability to climate change diagnosed for selected basin. Accordingly a climate change coping strategy designed. Training requirements in climate change identified and training plan prepared. Indigenous groups and farmers associations have been identified and selected for training. A hydro-climate monitoring station has been set up in the Rio Piedras basin. |
|  |
| **Problems and lessons learned:** |
|  |
| Coordination with Government. External to the JP (violence affects pace). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

