**Colombia**

|  |  |
| --- | --- |
| **Programme Title:**  | Integrated strategy for the prevention, care and elimination of all forms of gender based violence in Colombia |
| **Programme number & MDTF ref:** | MDGF-1746-B-COL Gender (67169) |
| **Window:** | Gender Equality & Women's Empowerment |
| **Approved Budget by NSC (US$):** | 7.2 million |
| **Participating Organizations:** | IOM, UNFPA, UNIFEM |
| **First Tranche transferred on:** | 16-May-2008 |
| **Second Tranche transferred on:** | 4-Dec-2009 |
| **Third Tranche transferred on:** | 1-Dec-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Communications strategy completed. Women´s refuges operational and providing legal and psychological support to women. The Embara Chami indigenous community sensitized and has agreed to ban female genital mutilation. Regulations passed to prohibit this. Gender based violence training provided to government staff in 3 pilot territories. Several manuals and other training material prepared.  |
|  |
| **Problems and lessons learned:** |
|  |
| Coordination with Government.  |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

