**Egypt**

|  |  |
| --- | --- |
| **Programme Title:** | Mobilization of the Dahshur World Heritage Site for Community Development |
| **Programme number & MDTF ref:** | MDGF-1775-G-EGY Dahshur World (67175) |
| **Window:** | Culture & Development |
| **Approved Budget by NSC (US$):** | 3.09 million |
| **Participating Organizations:** | UNDP, UNESCO, UNIDO, UNWTO, ILO |
| **First Tranche transferred on:** | 13-Apr-2009 |
| **Second Tranche transferred on:** | 23-Aug-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Baseline studies completed. 1500 persons trained in community capacity building techniques. Business development and micro-finance services introduced. 40 people (20 women) getting financing and 60 vocational training. Strategic plans developed for environment, culture and tourism. Training in ready-made garments underway. Multiple workshops carried out. |
|  |
| **Problems and lessons learned:** |
| Managerial (difficulty coordinating many actors). UN Agency coordination (multiple regulations). Egyptian Revolution has put the project on hold for + 3 months. Interim Govt and changes of national partners impacted the pace of delivery. |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes (now the JP is implementing the action plan of the strategy) |

CHARTS & FIGURES

As of 31 December 2010

