**El Salvador**

|  |  |
| --- | --- |
| **Programme Title:**  | Building social capital to reduce Violence: A new Transition in El Salvador |
| **Programme number & MDTF ref:** | MDGF-1962-F-SLV Building socia (67226) |
| **Window:** | Conflict Prevention & Peacebuilding |
| **Approved Budget by NSC (US$):** | 8.5 million |
| **Participating Organizations:** | PAHO/WHO, UNICEF, UNDP, ILO, UNFPA |
| **First Tranche transferred on:** | 27-Jul-2009 |
| **Second Tranche transferred on:** | 14-Dec-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Strategic National plan for justice and public security completed. Municipal Policy of Coexistence, Mediation and Citizen Security and Gender Policy approved. Training of justice sector trainers on gender violence designed. The “I decide to Live in Peace” campaign launched. Programme for the prevention of violence launched in three youth centers. Vocational training and entrepreneurial promotion model operational. Arm sales moratorium in place for San Salvador Y26 MUNICIPIOS MAS VIOLENTOS.  |
|  |
| **Problems and lessons learned:** |
| UN Agency coordination. Coordination within government (national and local level not articulated).  |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** No |

CHARTS & FIGURES

As of 31 December 2010

