**Ethiopia**

|  |  |
| --- | --- |
| **Programme Title:** | National Nutrition Programme / MDG-F Joint Programme |
| **Programme number & MDTF ref:** | MDGF-2034-I-ETH (67252) |
| **Window:** | Children, Food Security & Nutrition |
| **Approved Budget by NSC (US$):** | 7 million |
| **Participating Organizations:** | WFP, UNICEF |
| **First Tranche transferred on:** | 3-Sep-2009 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Health extension and community health workers were trained on community based nutrition in 16 districts, necessary supplies for implementation of nutrition activities distributed and 3,685 severely malnourished cases received effective treatment. 5,760 children and 2,360 lactating women received supplementary feeding. 29,552 children are weighed/measured every month and counseled to improve the feeding practice of the children under the age of two years, children under five were supplemented by Vitamin A and de-wormed , Addis Ababa University has completed an assessment of complementary food and developed 8 recipes. |
|  |
| **Problems and lessons learned:** |
| JP design (flaw resulted in WHO and FAO not starting their activities). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** No |

CHARTS & FIGURES

As of 31 December 2010

