# United Nations Development Group Iraq Trust Fund

# Project #:A5-25

# Date and Quarter Updated: 07 April 2011 (January-March 2011, 1st Quarter)

| Participating UN Organisation: FAO | Sector: Agriculture and Food Security |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Agriculture (MoA) |

| Title | Rehabilitation and Development of the National Vegetable Seed Industry in Iraq |
| --- | --- |
| Geo. Location | Governorates of Baghdad, Babil and Kerbala |
| Project Cost | USD$ 2 828 263 |
| Duration | 24 months extended 11 months |
| Approval Date | 11/10/2008 | Starting Date | 15/10/2008 | Completion Date | 15.10.2010 extended to 10.09.2011 |
| Project Description | The project aims to improve food security and nutrition for the Iraqi people with increased domestic production of vegetable crops. This will be brought about by improved seeds use of locally adapted varieties of the major vegetable crops, by rehabilitation of the infrastructure in the government research centres and by enhancing seed production and quality control capacity. The project activities will be concentrated in the major vegetable growing areas of Iraq which are located in the Central and Southern regions. The implementing partner of the project will be the Iraqi Ministry of Agriculture (MoA) with active participation of State Company for Horticulture and Forestry (SCHF) and State Board for Seed Testing and Certification (SBSTC). At the end of the project it is envisaged that the capacity of the government research centres in production of foundation seed of improved vegetable varieties would be enhanced significantly, the damaged infrastructures would be rehabilitated with provision of the equipment for production, processing and quality control resulting in viable local seed multiplication and supply in place with considerable participation of private sector. The technical capabilities of Iraqi human resources will be enhanced. |

Development Goal and Immediate Objectives

The development goal of the project is to improve food security and nutrition for the Iraqi people with increased domestic production of vegetable crops. The immediate objectives of the project are: Rehabilitation of damaged infrastructure in the vegetable seed sector Enhancement of technical capacity in vegetable seed research and seed production and support to private sector in vegetable seed industry.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Construction of greenhouses for varietal improvement and seed production. Equipment for seed production, processing and quality control procured and installed. Buildings for seed processing plant and seed testing laboratories constructed/ rehabilitated Vegetable crops improvement programme rehabilitated. Model vegetable seed production farm, processing plant and quality control laboratories for vegetable seed established. Vegetable seed quality control standards established Modules for vegetable seed sector study tour, overseas and in-country training developed and implemented. GOI assisted in the implementation of seed policy and regulatory framework. Skills and knowledge constraints of the workers at the sectoral level overcome. Vegetable seed production added value created. Module of business development designed for capacity building. |
| Activities | Preparation of technical specifications, tendering, contract award, construction of greenhouses (15 units). Preparation of technical specification, issuance of purchase order through bidding process, procurement of equipment for seed production farm equipment (3 sets), vegetable seed processing plants (3 units). Vegetable seed testing equipment (2 sets), office automation (4 sets). Installation of vegetable seed processing machines (3 units) and setting up of seed testing equipment at the laboratories (2 sets). Organize vegetable seed workshop/seed review seminars Undertake baseline survey vegetable seed production and marketing. Identify suitable farm for vegetables crops improvement and early generation seed production, initiate germplasm collection, setting up guidelines Conservation, introduction of promising lines and their evaluation to identify suitable varieties, varieties maintenance. Setting up guidelines and initiation of works on breeders and foundation seed production in the farms. Assist State Company for Horticulture and Forestry in planning future programme in vegetable seed production. Technical guidelines to the private sector in vegetable seed production. Review and update of vegetable seed quality control standards. Organize vegetable seed sector study tour abroad (3 specialists). Organize vegetable seed technology training courses overseas (25 technicians). In-country training programme on vegetable varietal development and evaluation, vegetable seed production and marketing, vegetable seeds quality control, database management and entrepreneurship development (150 persons). Organizing workshop/seminar on principles of private sector support outlined in the National Seed Policy and on the provision of seed laws. Private sector assessment of skills enhancement needs on vegetable seed production, processing and entrepreneurship development undertaken and programmes initiated. |
| Procurement (major items) | Vegetable seed production farm equipment. Vegetable seed processing plant. Vegetable seed testing equipment Office automation (computer) equipment. |

| Funds Committed | USD 2,200,821 | % of approved | 77 |
| --- | --- | --- | --- |
| Funds Disbursed | USD 1,544,189 | % of approved | 70 |
| Forecast final date | 10/09/2011 | Delay (months) | 11 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 166 | 99% |
| Women | 45 | 98% |
| Children | n.a. |  |
| IDPs | n.a. |  |
| Others | n.a. |  |
| Indirect beneficiaries | 1266 | 99% |
| Employment generation (men/women) | 0 | 0 |

| Quantitative achievements against objectives and results | % |
| --- | --- |
| Computer and office automation for database management | Procurement of computer and office automation equipment has been completed | 100% |
| Procurement of farm equipment | Both internationally and locally procured remaining farm equipment farm equipments for use in seed production farm delivered to MoA. | 100% |
| Greenhouses construction | Upon issuance of purchase order for supply and construction of climate-controlled greenhouses in the three locations of project implementation areas, the equipments delivered and installation being completed. | 95% |
| Procurement of vegetable seed testing laboratory equipment | Vegetable seed testing equipment to be used by the State Company for Horticulture and Forestry of the Ministry of Agriculture delivered. | 96% |
| Baseline data assessment | Baseline data assessment of vegetable seed production and marketing undertaken based on field information collection. | 100% |
| Vegetable seed processing plants | Technical bid evaluation under process upon receipts of the offers from the bidders against re-tender for the r supply of vegetable seed processing plants | 85% |
| International Training of Trainers (ToT) on vegetable seed technology | Participated by MoA technical trainees, conduct of training on vegetable crops varietal development and evaluation (9 persons), vegetable seed production and marketing (9 persons) and vegetable seeds quality control (7 persons) completed. | 100% |
| Study tour on vegetable seed sector | A two-week international study tour programme on vegetable seed sector participated by 3 senior officials of Iraqi MoA undertaken. | 100% |
| In-country training programme | In-country training programme on: i) vegetable crops varietal development and evaluation, ii) vegetable seed production and marketing, iii) vegetable seed quality control, iv) vegetable seed sector entrepreneurship development, and v) vegetable seed database management participated by total 150 trainees comprised of technical personnel in vegetable seed technology and private sector. | 100% |
| National Vegetable Seed Workshop | The National Vegetable Seed Workshop participated by Iraqi public and private sectors, USDA, GNIS and FAO reviewed the status of seed sector and recommended action plan for further development of Iraq’s seed sector. | 100% |

Qualitative achievements against objectives and results

Delivery of the farm machineries has enhanced the technical capacity of the MoA in vegetable crops improvement and early generation seeds production. Delivery and installation of equipments for seed processing and testing would be valuable in further strengthening vegetable crops varietal improvement, early generation seed production , vegetable seeds quality control and their adequate supply as per the country’s needs. Upon the installation of the climate-controlled greenhouses, the stations of the State Company for Horticulture and Forestry, MoA would have added capacity for varietal screening and other crop improvement aspects. A two week vegetable seed sector study tour to the Netherlands and Italy was undertaken by three senior officials of the Iraqi MoA. The tour has given opportunity to learn more on developed technologies in different aspects and help for long-term action planning and regulatory framework for Iraq among others. The in-country training courses on seed technology have improved practical skill of the Iraqi technical personnel in which the resource persons were the participants of the training of trainers programme held abroad. A national training course on vegetable sector entrepreneurship development has greatly benefitted the private sector interested to take up vegetable seed marketing as business option. In the National Vegetable Seed Workshop, critical review of the present status of vegetable seed sector in Iraq was undertaken, constraints, issues and opportunities identified and strategy and action plan recommendations were prepared for further development of the sector building on the present programme achievement

Main implementation constrains & challenges

General implementation and monitoring aspects are affected due to the prevailing situation in Iraq. The general peace, law and order problem in Iraq creates problem for any expatriate staff to visit. Even local staffs have problems visiting concerned offices, research centres and farms. Consequently information flow from the field to Amman has been slow. This definitely affects the implementation of this remote-controlled project implementation. As expected, progress may be slow and output not as set in the work plan. However, it should catch up once peace and stability returns to Iraq. Other than this there are no other problems.