# United Nations Development Group - Iraq Trust Fund

# Project # A5-26

# Date and Quarter Updated: 01 January - 31 March 2011 (1STQuarter)

| Participating UN Organisation: FAO | Sector: Agriculture and Food Security |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Water Resources (MoWR) |

| Title | Improvement of Water Supply and Irrigation Provisions through the Rehabilitation of Abu Sabkha Pumping Station |
| --- | --- |
| Geo. Location | Qadessiya Governorate, Diwaniyah District, the station is in the countryside with the following coordinates: 44.89325E / 32.06345N |
| Project Cost | UNDG Fund US$ 3,004,979 plus US$ 1,000,000 (MoWR) in kind |
| Duration | 28 months |
| Approval Date | 11/10/2008 | Starting Date | 15.10.2008 | Completion Date | 15.10.2010 extended to 10.09.2011 |
| Project Description | Abu Sabkha pumping station is the main irrigation pumping station in Diwanyiah governorate providing irrigation water for 36,550 donums of agricultural land which supports approximately 8,000 farming families. The rehabilitation of this pumping station by providing four spiral pumps with all their necessary mechanical and electrical accessories will restore the pumping capacity to the original level of 5.88 m3/sec. This will enable to put a large arable land back into agricultural production, thus providing food security, job opportunities and improve livelihood in the rural command area. |

Development Goal and Immediate Objectives

Development Goal: The project intends to rehabilitate the infrastructure of Abou Sabkha pumping station by replacing the existing old pumps by new ones. The development goal of the project is to enhance the food security through sustainable agricultural production by provision of adequate amounts of irrigation water to cover increased areas under cropping. Immediate Objectives: 1. Increase agricultural production; 2. Improve farmers’ livelihoods; 3. Create an institutional understanding and capacity building, thus providing the means for a sustainable operation and maintenance of the rehabilitated infrastructure involving both the beneficiaries and the government institutions.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Damaged pump station infrastructure rehabilitated/old equipment replaced. 36,500 ha of agricultural land brought back into production with 8,000 families benefitting. 3. Technical capacity of MoWR staff greatly enhanced including technology transfer. 4. Water Users' Associations (WUA) establishment feasibility study completed. |
| Activities | 1.1 A detailed assessment of Abu Sabkha pumping station completed and technical requirements determined. 1.2 Tender for equipment procurement approved and contract award for manufacturing and supply of mechanical and electrical equipment. 1.3 Factory inspection of equipment completed. 1.4 Delivery of 4 spiral pumps each with a capacity of 1.47 m3/sec completed, equipment installation initiated in place, and training of staff accomplished. 2.1 Re-establishment of water supply to the irrigation command area not undertaken yet. 3.1 MoWR staff trained on operation and maintenance of the pumping station equipment at the supplier’s premises. 3.2 MoWR staff capacity building on technical specifications and procurement procedures enhanced. WUA: 4.1 Tasks and TOR laid down. 4.2 Budget Feasibility study completed 4.3 Security Feasibility study completed 4.4 Results shared with stakeholders |
| Procurement | 1000 KVA generator (100% complete) Water Pumps and all accessories: (100% complete) |

| Funds Committed | US$ 2,469,216 | % of approved | 82.17% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 2,073,370 | % of approved | 68.99% |
| Forecast final date | 30-4-2011 | Delay (months) | 9 |

| Quantitative achievements against objectives and results | % |
| --- | --- |
| Damaged pump station infrastructure rehabilitated/replaced | A detailed assessment of Abu Sabkha pumping station completed and technical requirements determined. | 100 % |
|  | Tender approved and completion of contract awards for manufacturing and supply of mechanical and electrical equipment | 100 % |
|  | Factory inspection of equipment completed | 100 % |
|  | Manufacture, delivery, and installation of equipment to restore Abu Sabkha pumping station to operate within efficiency norms which relates to capacity requirements for 4 spiral pumps each with a capacity of 1.47 m3/sec | 100 % |
| 36,550 donums of agricultural land will be brought back into production and assisting 8,000 farming families to improve their livelihoods | Awaiting completion of equipment installation at the pumping station by the MoWR | 0 % |
| Technical capacity of MoWR staff enhanced including technology transfer | MoWR staff trained on pumping station operations by supplier completed. MoWR staff capacity building on procurement and technical specifications greatly enhanced.. | 100 % |
| Water Users' Associations (WUA) establishment feasibility study completed | Tasks and TOR for WUA | 10 % |
|  | Budget Feasibility study completed | 7 % |
|  | Security Feasibility study completed | 5 % |
|  | Feasibility results shared with stakeholders | 0 % |

Qualitative achievements against objectives and results

Procurement of all equipments already done and delivered in March 2011. MoWR staff capacity building already in progress regarding procurement and technical specifications analysis and remaining training regarding operations of the pumping station will be completed after installation of new pumping station parts. Damaged pump rehabilitation and replacement of parts will commence after all the parts are fully procured and handed over to the MoWR which is its sole responsibility. Establish ToR for conducting feasibility study for a Water Users Association in consultation with MoWR and rural farming communities. In consultation with FAO, the MoWR have taken steps in 15 governorates out of 18 (the 3 in the KRG) plus two irrigation projects namely Al Ishaky and Mesopotamia to establish pilot area/project for application of the WUA. The MoWR have trained 10 engineers in each governorate to carry on this task. They also prepared posters and TV spots for this purpose and establish what they call office of water extension in each governorate for awareness. The director of Water Resources in each governorate was nominated as the chief of the WUA team. As from 2011 on, this project was transferred to the MoWR and became part of their plans for this year. They are now awaiting the in acting of the laws by the Parliament. It is worth mentioning that the pilot project in Kerbala only was funded by JICA.

Main implementation constrains & challenges (2-3 sentences)

There was an initial delay in the implementation of about 9 months in 2010 because of delays in fund allocation which resulted in delays in procurement and tendering finalizations. This delay was compensated for by the extension of the project, ensuring that the outcomes and outputs of the project will be completed before April 30, 2011.