#### Annual Work Plan (Cover Page)

#### Country: 		Papua New Guinea

#### DaO Outcome(s):	 Behavior Change Communications Program

#### Expected Output(s):	Promotion of MDGs through radio and other media

#### Partners: 		Population Media Center (PMC)

#### Participating Agencies: UNFPA and One UN Fund

| Expected output | Indicators | Baseline | Annual Target |
| --- | --- | --- | --- |
| Output code Behavior Change Communications Program to Achieve the Millennium Development Goals | National survey of PNG on issues to be addressed and media consumption | 0 | 1 Survey (minimum of 400 people) |
| Output text (as per the result matrix) | Focus groups conducted throughout PNG | 0 | 32 groups |
|  | Media personnel (writers, producers, directors) trained in the Sabido methodology | 0 | 40 trained |
|  | Pilot episodes produced and testing with target audience | 0 | 4 episodes |
|  | Episodes produced | 0 | 30 episodes in each language |
|  | Arrange for exit interviews at points in the service infrastructure that PMC’s program will be promoting | 0 | 8 clinics/4 regions |
|  | Establish listening groups | 0 | 32 groups |
| Annual Deliverable |  | Partner | UN Agency |
| Behavior Change Communications Program to Achieve the Millennium Development Goals Complete extensive nationwide quantitative and qualitative research Set-up Population Media Center-PNG office Train media personnel in Sabido methodology Distribute wind-up/solar radios to regions with low radio ownership Establish broadcasting partnerships Produce and test pilot episodes Produce episodes 1-30 (out of total project 208 episodes) Make broadcast arrangements for project launch in January 2011 | Population Media Center | UNFPA and UN MDG Task Team |

| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description (USD) | Amount (funded) | Amount (unfunded) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Program management | x | x | x | x | PSI and BeMobile | $79,559 | $79,559 74,368 (PSI) 5,191 (BeMobile) | $0 |
| 2. Create and convene advisory committee |  | x | x | x | UNFPA | $2,000 | $2,000 | $0 |
| 3. Conduct formative research and develop policy framework |  | x | x |  | UN One Fund and UNFPA | $77,130 | $77,130 22,123 UNFPA 55,007 UN One Fund | $0 |
| 4. Baseline survey (Quantitative Research) |  | x | x |  | UN One Fund and PSI | $76,950 | $76,950 65,727 One UN Fund 11,223 PSI | $0 |
| 5. In-depth training workshop for scriptwriters and producers |  |  |  | x | UNFPA | $90,388 | $90,388 | $0 |
| 6. Pretest pilot episodes |  |  |  | x | UNFPA | $64,060 | $64,060 | $0 |
| 7. Write, produce, and broadcast serial dramas |  |  | x | x | PSI | $148,315 | $148,315 | $0 |
| 8. Monitoring 9. Evaluation Research | not applicable in 2010 |  |  |  |  |
| 10. General Operations | x | x | x | x | BeMobile | $74,368 | $74,368 | $0 |
| 11. Durable Equipment | x | x |  |  | BeMobile | $43,000 | $43,000 | $0 |
| 12. Technical Assistance | x | x | x | x | UN One Fund, PSI, and BeMobile | $73,852 | $73,852 22,123 UN One Fund 12,523 PSI 389,206 BeMobile | $0 |
| Indirect Costs (Admin services @12%) | x | x | x | x | All | $87,555 | $87,555 21,429 UNFPA 17,143 One UN Fund 29,571 PSI 19,412 BeMobile | $0 |
| Subtotals |  |  |  |  |  | $817,177 | $817,177 | $0 |

# Text boxes

Total Estimated annualized budget:	 US $817,177

Unfunded budget:  0

Allocated resources

Government	N/A

Regular

Other:

Donor

UNFPA	     $200,000

One UN Fund	$160,000

Packard		0

PSI      $276,000

BeMobile      $181,177

Colgate        0

DaO Strategy Period:	2010-

2012

DaO Component:		MDGs

Award ID#:

Project ID#:

Year:			2010

Narrative

Development, Production, and Broadcast of Two Radio Serial Dramas for Social Change:

This project utilizes an innovative approach for behavior change that will help Papua New Guinea work toward achieving the Millennium Development Goals.

To this end, Population Media Center will create two radio serial dramas for Papua New Guinea, one to be broadcast nationwide in Pidgin and another to be broadcast in English throughout the English speaking regions of Papua New Guinea. These long-running serial (Sabido-style) dramas will address a range of interrelated issues such as: promoting the use of effective family planning methods; elevating women’s status; increasing HIV/AIDS awareness, decreasing stigma, and encouraging testing; reducing violence against women; building support for universal education; increasing enrollment of male and female children in primary school; preventing deforestation and promoting reforestation; reducing the use of harmful marine practices such as coral mining, overfishing, and dynamite fishing; increasing favorable attitudes towards locally protected and managed marine areas; and decreasing the use of clear-cutting agricultural practices. The story lines and characters will be developed based on extensive formative research. Each of the dramas will consist of 208 episodes and will be broadcast twice per week over the course of 2 years. The content for each of the dramas will be tailored to the needs and interests of each of the target audiences. Monitoring will be conducted throughout the duration of the project, and a comprehensive endline evaluation will be conducted at the conclusion of the project using both quantitative and qualitative measures.

This work plan represents year one of a multi-year project.