**Guatemala**

|  |  |
| --- | --- |
| **Programme Title:**  | Strengthening Environmental Governance in the face of Climate Risks in Guatemala |
| **Programme number & MDTF ref:** | MDGF-1740-E-GTM Env Climate (67167) |
| **Window:** | Environment & Climate Change |
| **Approved Budget by NSC (US$):** | 3.6 million |
| **Participating Organizations:** | UNDP, UNICEF, FAO |
| **First Tranche transferred on:** | 31-Jul-2008 |
| **Second Tranche transferred on:** | 20-Jan-2010 |
| **Third Tranche transferred on:** | 16-Dec-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Environmental governance diagnostic completed. Baseline studies for the six micro-basins completed. Training in social audit provided to community based organizations. Training and materials provided on safe water and basic sanitation. Municipal operational agreements in preparation.  |
|  |
| **Problems and lessons learned:** |
| JP Design (time for execution is too short). Managerial (weak counterpart). UN Agency coordination.  |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** No |

CHARTS & FIGURES

As of 31 December 2010

