**Honduras**

|  |  |
| --- | --- |
| **Programme Title:** | Human development for youth: overcoming the challenges of migration through employment |
| **Programme number & MDTF ref:** | MDGF-1926-H-HND Human Devt for (67207) |
| **Window:** | Youth, Employment & Migration |
| **Approved Budget by NSC (US$):** | 6.4 million |
| **Participating Organizations:** | UNFPA, UNICEF, UNODC, IOM, FAO, ILO, UNDP |
| **First Tranche transferred on:** | 8-Apr-2009 |
| **Second Tranche transferred on:** | 8-Aug-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Design for inter-institutional youth employment committees finalized. Design for multi-service field offices finalized. Technical equipment bought and distributed. Studies/Diagnostics on potential productive activities, training of trainers in YEM, irregular migration and youth employment plans finalized. Training provided in youth enterprise development, financial services, valuing cultural identity, gender and other related subjects provided. Financial resources transferred to cooperatives in order to start credit scheme foreseen. 15 large and small enterprises identified to establish youth entrepreneurial mentoring programme. |
|  |
| **Problems and lessons learned:** |
| Coordination with government (slow pace). Managerial (stakeholders must take on role). JP design issues (role of stakeholders needs to be made clearer). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

