Future Work Plan

The Activities for 2011 are built on those in the Trade JP project document. All adjustments were made in consultation with the Government. The AWP includes several activities that were not implemented in 2010. It is expected that these will be finalised in 2011.It is expected that the objectives of the JP will be fully met by the end of 2011.

In 2011 priority activities will include:

- Capacity-building for MIC technical staff, particularly at provincial and district levels;

- Institutional strengthening of the INFOCOM unit of MIC, including upgrading of technical skills in advanced market and price analysis and support to improved efficiency in information handling and analysis;

- Capacity-building for INE, IPEX and ATM to improve the quality of trade statistics;

- Capacity-building for UEM to improve trade research capacity;

- Training and equipment supply to improve the quality of services provided by the One Stop Shops (BAUs);

- Increasing agro-processing capacity at local level;

- Dissemination of trade  policy and international trade agreements;

- Promotion of non-traditional export products;

- Reinforcement of mediation and arbitration services in Maputo and other provinces, leading to the strengthening of trade policy management and trade policy harmonisation in the relevant subsectors.

In 2011 the Joint Programme will focus special attention on coordination activities, in order to ensure effective joint implementation  of the Programme as well as to support the Government to assign leadership. Given that 2011 is the final year of the Joint Programme, a final evaluation is being planned.

EFFECTIVE TRADE POLICY FORMULATION AND MANAGEMENT

JOINT PROGRAMME

2011 ANNUAL WORK PLAN

Maputo, December 2010

Introduction

The objective of the Effective Trade Policy Formulation and Management Joint Programme (“Trade Joint Programme”) is to strengthen Mozambique’s trade capacity to enable the country to respond appropriately to development challenges, and to fully reap the benefits of the global trading system. The main outcome, as stated in the JP document, is an improved and coherent trade capacity for Mozambique that is capable of growing the local private sector, creating employment and reducing poverty. This will be achieved through the following initiatives:

- Providing support to trade policy and trade facilitation capacities, including relevant competition enforcement frameworks, to the responsible government institutions;

- Capacity for independent trade policy analysis and policy influencing by non-state actors; Targeted assistance in external trade negotiations (especially on agriculture); and

- Support to improve the capacity of agro-industry to produce goods and services that meet quality, design, timeliness, health, safety and environmental standards of domestic and foreign markets.

The Joint Programme is implemented jointly by five UN agencies (UNDP, UNIDO, FAO, UNCTAD and ITC) and the Government of Mozambique (MIC-Ministry of Industry and Commerce, Ministry of Agriculture), Research Institutions (UEM) and specialized institutes (INE, IPEC, and INOQQ).

The late approval of the Trade Joint Programme required adjustments to the original activities in order to meet the Government’s current priorities, and these required further discussions with the Government.  It took some time before consensus was reached through these discussions. As a result the implementation of 2010 activities started late and most of them have been carried over to the 2011 AWP.

Objectives and Expected Results

The objective of the Trade Joint Programme is to support the Government of Mozambique to strengthen national capacity to effectively formulate and manage trade policies. In order to achieve this objective, the programme has three outputs, namely:

- Strengthened trade policy management and trade policy harmonisation;

- Increased supply capacity for agricultural and fishery products;

- Improved capacity of enterprises to meet international product standards.

The results anticipated for 2011 within the scope of the above objectives are the following:

- Research capacity on trade issues established at Eduardo Mondlane University;

- Trade statistics collection quality improved at the main borders;

- Information quality and response time by BAUs improved;

- Increased capacity of agro-processing at local level;

- Improved capacity of enterprises to meet international product standards;

- Increased number of product types for export.

Broad Overview of Main Activities

The activities for 2011 are built on those in the Trade JP project document. The adjustments were made in consultation with the Government. The AWP includes several activities that were not implemented in 2010. It is expected that these will be finalised in 2011.

In 2011 the priority activities will include:

- Capacity building for MIC technical staff, particularly at provincial and district levels;

- Institutional strengthening of the INFOCOM unit of MIC, including upgrading of technical skills in advanced market and price analysis and support to improved efficiency in information handling and analysis;

- Capacity building of INE, IPEX and ATM to improve the quality of trade statistics;

- Capacity building of UEM to improve trade research capacity;

- Training and equipment supply to improve the quality of services provided by the One Stop Shops (BAUs);

- Increasing agro-processing capacity at local level;

- Dissemination of trade  policy and international trade agreements;

- Promotion of non-traditional export products.

In 2011 the Joint Programme will focus special attention on coordination activities, in order to ensure effective coordination of the Programme as well as to support the Government to assign leadership. In addition, as 2011 is the final year of the Joint Programme a final evaluation of the programme is being planned.

Budget Forecast

The table below provides an overview budget by participating agencies. The total budget for 2011 is planned to be US$2,329,300.00. From this total amount, US$860,307.57 will be covered by the carry-over from the 2010 budget. The remaining US$1,468,992.43 will be covered by resources to be mobilized from the One Fund. Unfortunately, none of the participating agencies has regular resources which can contribute to the Trade Joint Programme.

|  | 2011 TRADE JOINT PROGRAMME BUDGET |  |
| --- | --- | --- |
| Joint Programme | Agency | 2011 Budget Needs |
|  |  | Total Budget for 2011 | Agency Resources- 2011 | Balance from 2010 One Fund Allocation | Unfunded | One Fund Allocation Needs in 2011 |
| Effective Trade Policy Formulation | ITC | 710,000.00 | 0 | 82 445.00 | 397,555.00 | 397,555.00 |
|  | UNCTAD | 120,000.00 | 0 | 0 | 120,000.00 | 120,000.00 |
|  | UNIDO | 261,000.00 | 0 | 67,862.57 | 193,137.43 | 193,137.43 |
|  | UNDP | 878,300.00 | 0 | 350,000.00 | 528,300.00 | 528,300.00 |
|  | FAO | 360,000.00 | 0 | 360,000.00 | 0 | 0 |
|  | Total | 2,329,300.00 | 0 | 860,307.57 | 1,238,992 | 1,238,992 |

UN Mozambique

Effective Trade Policy Formulation and Management

Joint Programme

Annual Work Plan 2011 Matrix

| Joint Programme Outputs, Indicators and Targets | Planned Activities | Q1 | Q2 | Q3 | Q4 | Responsible Parties | 2011 Budget | Allocated Funds | Source of Funds |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Strengthened trade policy management and trade policy harmonisation RESULT FOR 2011 1. Research capacity for trade issues established at Eduardo Mondlane University 2.Trade statistics collection quality improved at the main borders 3. Information quality and response time by BAUs improved | 1.1 Training of Legal Advisers on Contracts and Investment Law issues | X | X |  |  | UNDP; UEM | UNDP $47,000 | UNDP $47,000 | UNDP $47,000 OR |
|  | 1.2 Support to analytical work on trade by academic and research institutions | X | X | X |  | UNDP; UEM | UNDP $50,000 | UNDP $50,000 | UNDP $50,000 OR |
|  | 1.3 Support to quality improvement on trade statistics data collection | X | X | X |  | UNDP; INE; BM Alfândegas; IPEX; MIC | UNDP $140,000 | UNDP $140,000 | UNDP $140,000 OR |
|  | 1.4 Various stakeholders intervening on trade policies issues retreat | X |  |  |  | UNDP; MIC | UNDP $35,000 | UNDP $35,000 | UNDP $35,000 OR |
|  | 1.5 Situation analysis of the import and export sectors |  | X |  |  | UNDP; MIC; IPEX | UNDP $50,000 | UNDP $50,000 | UNDP $50,000 OR |
|  | 1.6 Improvement of One Stop Shops’ (BAUs) quality of public services and provision of information on business and investment | X | X | X |  | UNDP; MIC | UNDP $180,000 | UNDP $180,000 | UNDP $180,000 OR |
|  | 1.7 Design the national strategy for competitive exports and establish the capacity for its development and implementation in line with the PARPA objectives | X | X |  |  | UNDP; MIC; IPEX | UNDP $80,000 | UNDP $80,000 | UNDP $80,000 OR |
|  | 1.8 Organization of the International Trade week, seminar on trade policy and meetings on WTO notifications | X | X | X |  | UNDP; MIC DRI | UNDP $35,000 | UNDP $35,000 | UNDP $35,000 OR |
|  | 1.9 Implementation of competition policy | X | X |  |  | UNDP; MIC-DNC | UNDP $85,000 | UNDP $85,000 | UNDP $85,000 OR |
|  | 1.10Industrial property policy implementation | X | X |  |  | UNDP; IPI | UNDP $ 5.000 | UNDP $ 5.000 | UNDP $ 5.000 OR |
|  | 1.11 Strengthen MIC’s analytical capacity through training for provincial and district staff: 3 regional workshops including themes such as agricultural marketing, value chains, rural credit, market linkages etc. | X | X |  |  | FAO; MIC | FAO $170,000 | FAO $170,000 | FAO $170,000 OR |
|  | 1.12Reinforce MIC’s institutional capacity, particularly INFOCOM systems for data collection and analysis |  | X | X | X | FAO; MIC | FAO $190,000 | FAO $190,000 | FAO $190,000 OR |
|  | 1.13 Design and implement the National Export Strategy and its trade policy linkages (policies/strategies to enhance the economic and enabling business environment and to promote entrepreneurship) | X | X | X |  | ITC, IPEX, MIC | ITC $150,000 | ITC $80,000 | ITC $80, 000 OR |
|  | 1.14 Situation analysis of the import and export sectors |  | X |  |  | ITC; MIC; IPEX | ITC $120 000 | ITC $50,000 | ITC $170, 000 OR |
|  | 1.15 Building capacity of SMEs to deal with commercial contracts for exports. | X | X | X |  | IPEME; CTA; CACM; EduardoMondlane University | ITC $80,000 | ITC $80,000 | ITC $80, 000 OR |
|  | 1.16 Building capacity of commercial and labour mediation/arbitration for the benefit of SMEs and institutions. | X | X | X |  | CACM;COMAL;CTA | ITC$ 130,000 | ITC $130,000 | ITC $130, 000 OR |
|  | 1.17 Support to competition legislative process and establishment of competition authority & coordination of investment promotion with trade strategy | X | X | X |  | UNCTAD; MIC; CPI | UNCTAD $120,000 | UNCTAD $120,000 | UNCTAD $120,000 OR |
| 2. Increased supply capacity for agricultural and fishery products RESULTS FOR 2011 1-Increased capacity of agro-processing at local level | 2.1 Support to the agro-processing demonstration centre in Boane | X | X |  |  | UNDP; MIC-IPEME | UNDP $81,300 | UNDP $81,300 | UNDP $81,300 OR |
|  | 2.2 Implementation of “Global gap”/GAP requirements for certification of key agro-food products. | X | X | X | X | UNIDO; MINAG | UNIDO $26,000 | UNIDO $26,000 | UNIDO $26,000 OR |
|  | 2.3 10 companies ready for certification to Global Cap standard within 2 years | X | X | X |  | UNIDO; MINAG | UNIDO $35,000 | UNIDO $35,000 | UNIDO $35,000 OR |
|  | 2.4 Implementation of ISO 22000 | X | X | X |  | UNIDO; INNOQ | UNIDO $ 65,000 | UNIDO $ 65,000 | UNIDO $65,000 OR |
|  | 2.5 Strengthen/support national phytosanitary service and national capacity for food safety analysis | X | X | X |  | UNIDO; MINAG; FAO; MISAU | UNIDO $71,000 | UNIDO $71,000 | UNIDO $71,000 OR |
|  | 2.6 Improve production techniques in agro-processing | X | X | X |  | UNIDO; MINAG | UNIDO $32,000 | UNIDO $32,000 | UNIDO $32,000 OR |
|  | 2.7 Infrastructural improvement of targeted companies as required to meet international requirements | X | X | X |  | UNIDO; FAO | UNIDO $32,000 | UNIDO $32,000 | UNIDO $32,000 OR |
|  | 3.1 Promotion of products with potential for export and elaboration of the External Trade Manual |  | X | X | X | UNDP; IPEX | UNDP $90,000 | UNDP $90,000 | UNDP $90,000 OR |
|  | 3.2 Upgrading capability in Fish Inspection Services for Mozambique and to increase expertise and skill of a minimum of 18 officials of the Competent Authorities for evaluating the compliance status of fish facilities to the EU requirements and for providing training on EU fish requirements |  | X | X | X | ITC; INIP | ITC $100,000 | ITC $100,000 | ITC $100,000 OR |
|  | 3.2 Training and improving market access through Market Access and maintenance of Standards and Conformity Assessments |  | X | X | X | ITC; IPEX; MIC | ITC $80, 000 | ITC $80, 000 | ITC $80, 000 OR |
|  | 3.3 Strengthen the institutional linkages between Trade Promotion and National Standards Body (INNOQ) |  | X | X |  | ITC; IPEX; INNOQ | ITC $95,000 | $25,000 OR | ITC $70,000 OR |
| TOTAL |  |  |  |  |  |  |  |  | UNDP $878,3000 OR UNIDO $261,000 OR UNCTAD $120,000 OR FAO $360,000 OR ITC $710,000 |