### PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme |
| --- | --- | --- |
| Country | : | Lebanon |
| Project No. | : | LRF – 19 |
| Project Title | : | Socio – Economic Rehabilitation Programme in the Framework of ART GOLD Lebanon. |
| LRF Signature date | : | March 26, 2009 |
| Project Start date | : | April 2009 |
| Project Timeframe | : | Extended till end of February 2011 |
| Reporting Period | : | Oct-Dec 2010 |

I. PURPOSE

Project Summary:

Through ART GOLD’s participatory methodology and instruments, the programme will tackle issues of socio-economic local development for balanced regional development. This includes strengthening local participatory planning processes, local government strengthening, local economic development and decentralized cooperation. The programme builds on potentialities and capacities in target regions, hence contributing to recovery and socio-economic rehabilitation in Lebanon.

The programme responds to national priorities of poverty reduction and the reduction of regional disparities through interventions in four underserved regions of the country, including North Lebanon, south Lebanon, West Bekaa and Beirut Southern Suburbs.

Project Objectives and Outcomes:

The specific objective is to improve the local population’s living conditions through increased access to employment, income, education, health, social integration and the environment, with a special focus on the most vulnerable population. This is done through improving the functioning of local public administration, enhancing basic social services, and promoting a wide participation of local communities in development processes.

Outputs are carried out at the local, national and international levels:

At the local level:

- Governance:

- Improved skills and capacities of local authorities and administration to plan manage and promote human development.

- Improved partnerships between the local authorities and local actors such as civil society stakeholders.

- Lebanese institutions capacitated to take advantage of international partnerships such as decentralized cooperation networks.

- Members of public institutions and civil associations better prepared to operate jointly in local development processes.

- Local Economic Development:

- LEDAs established in the four regions of intervention.

- Local economic development promoted in a balanced and integrated way, hence reducing poverty and increasing access of the deprived sectors of the population to jobs and businesses.

- Endogenous resources and regional competitiveness maximized.

- Number of small productive enterprises increased.

- Increased income for the disadvantaged sectors of the population.

- Productive activities use local resources in a more sustainable way.

- Social Wellbeing:

- Improved coverage of public services and utilities in AGL’s priority sectors of education, health and the environment.

- Improved functioning of public services in the aforementioned social sectors.

- Access for excluded and marginalized areas and persons to basic social services increased.

- Innovations aimed at improving the quality and efficiency of services introduced.

- Social cohesion and dialogue promoted through ART GOLD’s participatory approaches and methodologies.

- Increased initiatives promoting social cohesion, such as the community maps of risks and resources.

Project Linkages to National Priorities and Reconstruction Goals:

The projects are in line with the Government’s goals to support basic social services and primary health care, enhance social integration and support to the youth, enhance the preservation of the environment (waste, water, energy and forestry) and Increase income generation and job opportunities.

Project Implementation Partners:

The ART GOLD Programme is a part of the ART global initiative that was specially designed by a group of UN Agencies under UNDP leadership (UNESCO, UNIFEM, WHO, UNITAR and UNOPS). The ART GOLD is based on a cooperation framework between local, national and international partners interested in combining and coordinating their efforts to achieve the Millennium Development Goals (MDGs) and to contribute to local governance, decentralization, and balanced socio-economic development in the medium and long term.

AGL adopts a multi donor framework where donor countries pool their contributions in support of the programme. Most of the donors contribute to the project according to predefined approved proposals and clear platform for intervention. Progress reports are prepared and submitted for the concerned donors about achievements at the field level in addition to the continuous exchange visits that take place between the countries.

The programme is managed at country level by UNDP in partnership with its national counterpart the Council for Development and Reconstruction (CDR).  Moreover, ART GOLD coordinates with the concerned line ministers and local authorities for the communal initiatives at the field level.

National Partners:

- Council for Development and Reconstruction.

- Line ministries and municipalities as local partners.

International Partners:

- Government of Italy

- Government of Spain

- Government of Belgium

- Principality of Monaco

DC partners: ART GOLD Lebanon has established partnerships with around 50 local European partners, to name a few: FAMSI (Federacion Andaluza de Muinicipios para la Solidaridad Internacional, SPAIN), Diputacion de Barcelona , Catalan Cooperative Agency for Development, Tuscany region, COCOPA (Coordinamento de Municipi de la province de Turino, Italy), Sint-Truiden Municipality (Belgium), and Les Amis du Liban from Monaco.

Decentralized Cooperation (DC) are local authorities of the North and their public and private stakeholders (NGOs, Universities, Enterprises, multi-utilities companies, etc.) make an important contribution to local development processes in the countries of the South by co-financing development programmes and by making their knowledge and experience available. It represents an innovative model of international cooperation which sets out to achieve the Millennium Development Goals through a relationship of partners and colleagues rather than the traditional beneficiaries and donors. In this way, DC can carry out initiatives that can have a significant impact on the territories, reducing fragmentation of resources and guaranteeing greater sustainability in terms of results.

Decentralized cooperation projects can encompass all or only some of the areas of activity in the framework program: governance, economic development, environment, health and welfare, education and training. The projects must be defined in collaboration with the local working groups, on the basis of the diagnosis made in the territorial marketing map.

# II. RESOURCES

|  | As of December 31st, 2010 |
| --- | --- |
| Total budget approved | $2,391,450.00 |
| Disbursements | $2,362,757.20 |
| Available Balance | $28,692.80 |
| Commitments for next quarter | USD 28,692.80 |

| Account | Amount Disbursed by project |
| --- | --- |
|  | 00053003 - ARTGOLD Lebanon | 00056944 - ARTGOLD BSS | 00056945 - ARTGOLD South | 00056946 - ARTGOLD Bekaa | 00056947 - ARTGOLD North | 00073242 - Guarantee fund |
| Non-Recurrent Payroll - IP Stf | 3,123.70 | - | - | - | - | - |
| After Service Insurance | 192.36 | - | - | - | - | - |
| ALD Employee Costs | 76,433.00 | - | - | - | - | - |
| International Consultants | 63,000.00 | - | - | - | - | - |
| Local Consultants | - | - | - | 2,600.00 | 500.00 | - |
| Contractual Services - Individual | 104,884.56 | 59,834.93 | 91,720.54 | 40,862.45 | 85,700.18 | - |
| UN Volunteers | 2,646.78 | - | - | - | - | - |
| Travel | 45,335.69 | 19,111.00 | 6,045.84 | 1,225.09 | - | - |
| Contractual Services-Companies | 17,540.33 | 232,916.00 | 105,361.91 | 30,850.00 | 24,000.00 | - |
| Equipment and Furniture | - | 5,571.00 | 77,352.40 | 10,239.55 | 69,296.57 | - |
| Materials & Goods | - | - | 4,836.20 | 48,557.00 | 42,573.63 | - |
| Communication & Audio Visual Equip | 896.62 | 4,556.23 | 12,665.24 | 1,317.06 | 5,599.89 | - |
| Supplies | 776.04 | 479.85 | 3,592.35 | - | 93.33 | - |
| Grants | - | - | 47,106.41 | 53,050.00 | 108,834.89 | 520,000.00 |
| Information Technology Equip | 4,890.00 | 20,183.45 | 3,644.00 | 159.50 | 10,113.70 | - |
| Rental & Maintenance-Premises | 30,496.45 | - | 271.00 | 13,017.13 | 2,689.27 | - |
| Rental & Maint of Info Tech Eq | 220.00 | - | 250.00 | - | - | - |
| Rental & Maint of Other Equip | 282.02 | 3,771.48 | 7,312.44 | 1,684.27 | 385.00 | - |
| Professional Services | 1,589.09 | 1,589.09 | 1,589.09 | 1,589.09 | 1,589.09 | - |
| Audio Visual&Print Prod Costs | 11,405.58 | 13,134.00 | 12,346.80 | 482.00 | 1,045.00 | - |
| Contributions | 18,642.37 | - | - | - | - | - |
| Miscellaneous Expenses | 2,556.02 | 2,142.97 | 4,103.59 | 3,653.52 | 78.67 | - |
| Agency Management Support (7%) | 26,943.74 | 25,430.30 | 26,473.85 | 14,650.07 | 24,674.95 | 36,400.00 |
| Total Expenditure per project | 411,854.35 | 388,720.30 | 404,671.66 | 223,936.73 | 377,174.17 | 556,400.00 |
| Amount Approved per project | 433,180.00 | 388,720.00 | 404,770.00 | 223,940.00 | 384,440.00 | 556,400.00 |
| Remaining Amounts per project | 21,325.65 | (0.30) | 98.34 | 3.27 | 7,265.83 | - |

III. RESULTS

During the months of Oct – Dec 2010, ART GOLD has been finalizing the implementation of the remaining few projects under the LRF funds in different areas, while the remaining minor budget will be used to cover minor logistics.

Achievements at the Field Level:

The Primary Health Care sector

- A primary Health care established in Al-Qaser, Bekaa. The beneficiaries from this initiative reached 15,000 inhabitants in Al Qaser the nearby villages as well.

- Two Primary health care centers rehabilitated in Abboudieh and in Tebbeneh, North Lebanon. These centers were equipped with modern Medical and Technological equipments.

- Female health workers trained to better address community’s health issues. More than 100 girls obtained skills in health issues to support families and communities through health awareness campaigns. Questionnaires were distributed to identify the needs and the types of topics to be addressed.

- Clinic Furniture provided to the primary health care centers in Haret Hreik, Ghobeiry and Burj Al Barajneh, Beirut Southern Suburbs.

- Quality and quantity of the services improved at relevant/targeted PHCCs in Bekaa, North Lebanon and Beirut Southern Suburbs. The outreach of the three PHCCs expanded as indicated by the increase in the visiting patients while the quality of service provided witnessed drastic improvement as shown in the results of satisfaction surveys conducted in some centers. The PHCCs are more recognized with some of them obtaining accreditation and on the right track for being sustainable; the municipalities are taking rigorous steps for their incorporation within their organigram.  These centers were capacitated to adapt the Lebanese context and to be accredited by the Ministry of Health”

PHCC medical and paramedical personnel skills improved through

- training on chronic diseases protocols
-training informatic medical record
- training on planning and implementing health prevention programme
- Study tour to Italy

PHCC management system enhanced

- Health Informatic System improved 
- Epidemiological data collected from the 3 PHCCs 
- training on financial management of the PHCCs

The Local Economic Development Component

- A soil and water testing facility established in Abdeh, North Lebanon.

- 50 kiosks constructed in Baalbeck, Bekaa

- A network of women cooperatives established. More than 10 women cooperatives were established in the North and South Lebanon. These women cooperative shared in several forums for resource mobilization in addition they participated in many trainings to strengthen their capacities and skills for production.

- A regional Mediterranean forum hosted with the Ministry of agriculture discussing and recommending solutions for enhancing beekeeping sector in Lebanon.

On the national level, intensive coordination efforts were exerted with the Ministry of Agriculture enforcing the collaboration on many levels and leading to amelioration of beekeeping sector whether strategically or operationally.

On the level of organization of beekeeping sector, AGL supported through international expertise, the issuing of national legislation – draft law- to organize the beekeeping sector in Lebanon. It also assisted the Lebanese Ministry of agriculture to develop software for managing the information collected by the government on the beekeeping sector in synergy to national strategy for performing a national census on beekeepers, bee hives and bee diseases.

Several trainings on disease control have been conducted for approximately 200 beekeepers in addition to analysis of honey quality and disease prevalence to prepare them for the market. An Italian expert has presented results of first analysis at March’s 2010 meeting.

Three beekeepers from North and South Lebanon and the Bekaa region attended a 10-day workshop in Perugia –Italy.

Over 130 [local and international] participants attended the fourth Mediterranean beekeeping forum conducted for two days which AGL organized with the MoA in collaboration with the Association of Umbrian Beekeepers (APAU), FELCOS Umbria, Foligno Municipality and ART Initiative.

The Forum which helped exchange ideas, information, and experiences, constituted a venue for elaboration of better solutions to the problems facing the beekeeping sector. A letter comprising main recommendations for improving the beekeeping sector in Lebanon was the outcome which was raised to the Minister’s attention for follow up.

The youth sector:

- Two offices for youth development established at Al Hadath and Furn El Chebbak municipalities, Beirut Southern Suburbs.

- Two Cultural Centers established in Halba and Azaki, North Lebanon.

- Four IT centers established in Akkar, Minnieh Dinnieh and Tripoli in North Lebanon;

- Two public parks for children established in Fneidek and Halba, North Lebanon. Number of beneficiaries reached 100 children from both villages. The intervention strengthened the social relationships among the youth and provided them a safe place to enjoy their leisure times and practice outdoor activities.

- A municipal playground built in Kfarchalan, North Lebanon. This project benefited Kfarchalan youth in addition to the ones in the nearby villages.  The project also allowed the youth to organize sports tournaments among the villages and thus created a social environment for youth to meet from different areas and share ideas and exchange thoughts. Total numbers of beneficiaries is estimated to be around 250 youths.

The Environment Sector

- A water irrigation canal of 500 ML constructed in Nahle, Baalbeck

- 7000 trees (for honey bees) planted to increase honey production in West bekaa and Rachaya

- Two water maintenance centres established in Tyre and Marjeyoun; South Lebanon.

The local governance Sector

- A programme for training around 300 newly elected local authorities (municipal offices) was set up to be complimented with different donors’ support. This programme is implemented at the national level in coordination with the Ministry of Interior and Municipalities. The project target newly elected municipalities in all over Lebanon through consecutive workshops (42 workshops) to introduce to the members the ABCs of the municipal work, laws, roles and responsibilities, financial rules and development opportunities. During 2010, the bases for this target are set however; the actual start up of those workshops is scheduled to start in January 2011.

Progress in Project Implementation Oct – Dec 2010:

North Lebanon:

In North Lebanon, the equipping and establishment of the youth IT center in Bakhoun village has been completed. Moreover, around 20 youth volunteers (male and female) in Akkar region have been trained as trainers on different IT topics (web design, accounting, computer fundamentals, entrepreneurship, etc...) to help transfer their skills and knowledge for local youth in market demanded topics.

The PHCC of Abboudieh has been established and equipped, allowing provision of enhanced health services. Additionally, the soil and water testing laboratory at LARI has been established and equipped with necessary equipment to provide critical information for farmers in North Lebanon that would eventually enhance their agricultural production.  The laboratory is operated by LARI. The production has enhanced due to the provision of modern and needed equipments that helped them to increase the quality and quantity of production.

South Lebanon:

In South Lebanon, a women cooperative network has been established comprised of 15 active cooperatives in food processing methods. A quality control center for agro-food products has been also established with LARI [testing equipment to chemicals, and glassware], which is expected to provide quality assurance for products of the women cooperatives. Moreover, the procurement of a vehicle for product distribution has been completed for the “Cooperative association for agricultural development in Tyre” – the major partner in this initiative which will be responsible to run and manage the “packaging and distribution center” funded by the UNDP socio economic rehabilitation project in south Lebanon.

Beirut Southern Suburbs:

During the final stage of the project in BSS, the supported social municipal offices carried out some activities to support social integration in their territories such as Gift distribution for elementary and intermediate public schools in Furn el Shubak, al Masque for youth aged between 13 and 17 years old and Christmas reception celebration to Al Hadeth community. Also, the SMO with the technical support of UNDP ART GOLD and the expert from the University of Florence prepared the proposal for a Household social survey (Action plan, Term of References, chronogram, budget) to be implemented in 2011 2nd  quarter. In order to ensure sustainability of interventions, it was agreed to integrate the staff of Social municipal offices as part of the municipalities’ structure.

Regarding the health component, conducted surveys has shown expansion in the outreach with more visiting patients which reached to 60% while the quality of service provided witnessed drastic improvement as according to satisfaction surveys. The PHCCs are more recognized with some of them obtaining accreditation and on the right track for being sustainable; the municipalities are taking rigorous steps for their incorporation within their organigram.

National level:

Capacity development programme:

After completing the initial preparatory phase of the “Capacity Development Programme” namely through developing a database on the newly elected municipal members, and selecting the implementing partner to conduct the training in partnership with the Ministry of Interior, the last quarter of 2010 focused on selecting the trainees based on the following criterion: 1- Municipalities elected for the first time, 2- Municipalities enrolled within UNDP program, 3- Big sizes municipalities, 4- Municipalities identified by the MOIM. Moreover, a consultant to coordinate programme activities was recruited, who delineated the schedules and details of the first pilot training workshops in collaboration with area managers. The total number of workshops is 42. The start up of the workshops will start in January 2011.

Mediterranean Beekeeping Forum:

Within the frame of honey value chain support, ART GOLD hosted the Mediterranean Beekeeping forum in Lebanon entitled “Honey Bees: promoters of biodiversity” in coordination with Italian partners and under the patronage of the Lebanese Ministry of Agriculture. More than 150 participants attended, representing honey producers’ associations and cooperatives, research institutes and public entities from 11 countries in the Mediterranean and abroad to discuss issues pertinent to biodiversity and honey role in it.

The Forum has helped exchange ideas, information, and experiences and provided better solutions to the problems facing the beekeeping sector. It was concluded with a letter comprising main recommendations for improving the beekeeping sector in Lebanon raised to the Minister’s attention for follow up.

For info pertaining on the progress/status of each project, please refer to annex (1).

Implementation Constraints and Lessons Learned:

Constraints: Two hindering factors have delayed the timely delivery of projects including: Working groups’ methodology represents the cornerstone of ART GOLD work. As such, in parallel to activities implementation, several efforts were exerted to capacitate and strengthen the role of working groups in the planning process, particularly in 2009. This delayed the pace of implementation of some planned activities with local authorities resulting in shifting more than 60% of project budget till 2010. The municipal elections which took place in June 2010 led to a practical freeze of partnering local authorities roles for a lengthy duration of four months -preparatory work before elections and formulation of municipal councils after the elections. This caused an enormous disruption to the rhythm of ART work, further exacerbated by the changes in partner municipalities’ composition, hence working groups’ membership. This prolonged the completion of project implementation given the timeframe required to acquaint the new municipal members with the ART work and their roles and responsibilities. Lessons Learned are identified under each of the programme’s three main components: 1)participatory approach and working groups, 2) Decentralized Cooperation and 3) Local economic Development 1)Participatory Approach and Working groups: Moving from local working group (WG) towards regional working group (RWG) Local ownership more obvious whenever a bottom-up approach is used 2)Decentralized partnerships: The DC Partnerships are sometimes more fruitful if the partners experience similar challenges and contexts Working groups’ efficient and effective cooperation with decentralised cooperation partners has contributed to sustainable local development DC is a learning opportunity for a country such as Lebanon with a strong centralized administration, moving towards administrative decentralization 3) Local Economic Development: Innovative solutions: LEDOs instead of LEDAs

IV. FUTURE WORK PLAN

In the final two months, ART GOLD will use the minor remaining budget to some logistical costs to ensure proper monitoring and closure of ongoing projects.

Annex: 1

Projects Status

Last Updated 31 December 2010

|  | Mohafaza | Village | Project Description | Sector | Starting Date | Expected Ending Date | Funding Source | Progress to Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ART GOLD – South Lebanon, Status of 2009 Projects |
|  | Tyre Caza |
| 1 | South Lebanon and Nabatiyeh | Tyre and Union of Jabal Amel Municipalities | Improvement in drinking water distribution infrastructures and the water resource management system in the districts of Tyre and Jabal Amel | Env't/Watr Mng't | Aug-09 | Dec-09 | Spain | Completed |
|  | All Cazas |
| 2 | South Lebanon and Nabatiyeh |  | Women cooperative network | LED | Aug-09 | Feb-2011 | Spain | Completed |
|  | ART GOLD – Bekaa, Status of 2009 Projects |
|  | Baalbeck Caza |
| 3 | Bekaa | Baalbeck | Construction of Kiosks – Municiplity of Baalbeck | Tourism | Aug-09 | Oct-09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
|  |  |  |  |  |  |  | Baalbeck Mun. |  |
| 4 | Bekaa | Nahle | Nahle irrigation canal | Env't/water Mng't | Oct-09 | Jan-10 | Spain | Completed |
|  | Hermel Caza |
| 5 | Bekaa | Alqaser | Establishment of a PHC (equipment) | Health | Aug-09 | Sep-09 | Spain | Completed |
|  | Rachaya Caza |
| 6 | Bekaa | Khawkaba | Reforestation & Fire Prevention (nursery) | Env't/ Watr Mng't | Sep-09 | Oct-09 | Spain | Completed |
|  |  |  |  |  |  |  | Kawkaba Mun. |  |
| 7 | Bekaa |  | Provision of 10000 pollen trees -eucalyptus & Acacia- to beekeepers in W.Bekaa & Rashaya | LED | Mid Nov. 2009 | Spain | Completed. |
|  | ART GOLD – North Lebanon, Status of 2009 projects |
|  | Al-Minnieh Al Dinnieh Caza |
| 8 | North | Azqi | Rehabilitation of cultural centre | Social | Nov. 09 | Dec. 09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 9 | North | Bakhoun | Rehabilitation of primary health care centre | Health | Nov. 09 | Feb 10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 10 | North | Bakhoun | Establish Youth IT center | Youth |  | Dec. 2010 | Belgium Spain | Completed |
| 11 | North | Deir Nbouh | Establish youth IT center | Youth | Nov. 09 | Dec.09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 12 | North | Kfarchalan | Build a municipal playground | Youth | Dec-08 | Sep-09 | Italy | Completed |
|  |  |  |  |  |  |  | Spain |  |
|  | Akkar Caza |
| 13 | North | Abboudieh | Rehabilitation of Primary health Care center | Health | Nov. 09 | Feb.10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 14 | North | Akkar | Establishment of a laboratory for soil & water testing & analysis at the LARI- Aabdeh station located in Akkar | Agriculture /LED | Nov. 09 | Dec.10 | Belgium | completed |
|  |  |  |  |  |  |  | Spain |  |
| 15 | North | Akkar Atika | Establish Youth IT Center 1 | Youth | Nov. 09 | Dec. 10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 16 | North | Fneidek | Establish a public park for children | Social | Oct-09 | Dec-09 | Italy | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 17 | North | Halba | Establish a public park for children | Social | Oct-09 | Dec-09 | Italy | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 18 | North | Halba | Rehabilitation of cultural center | Social | Nov. 09 | Dec. 09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 19 | North | Qobayat | Establish Youth IT center 2 | Youth | Nov. 09 | Dec. 09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
|  | Tripoli Caza |
| 20 | North | Tebbeneh | Rehabilitation of Primary health Care center | Health | Nov 09 | Feb 10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 21 | North | Tripoli | Support the Youth vocational Training project | Youth | Nov. 09 | Dec. 09 | Italy | Completed |
|  |  |  |  |  |  |  | Italian DC |  |
|  |  |  |  |  |  |  | Spain |  |
| 22 | North | Tripoli | Establish Youth IT center | Youth | Nov. 09 | Dec. 09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
|  | ART GOLD- Beirut Southern Suburbs, Status of 2009 projects |
|  | Baabda Caza |
| 23 | Mount Leb | Al Chiah, | Social intervention addressed to youth | Social | Jan-09 | Dec-09 | Spain | Completed |
| 24 | Mount Leb | Hadath | Social intervention addressed to youth | Social | Jan-09 | Dec-09 | Spain | Completed |
| 25 | Mount Leb | Furn El Chebbak | Social intervention addressed to youth | Social | Jan-09 | Dec-09 | Spain | Completed |
| 25.1 |  |  | Provision of equipment for the social programme in Al-Chiah - Al-Hadath - Furn Al Chebbak |  | 2009 | Spain | Completed |
| 25.2 | Mount Leb | Al-Chiah - Al-Hadath - Furn Al Chebbak | Capacity Building within the 3 projects "Social development addressed to youth" |  | 2009 | Tuscany Region -ARCI network | Completed |
|  |  |  |  |  |  | Spain |  |
| 26 | Mount Leb | Al Mreyjeh | Scholastic maps of Risk and Ressources | Social | Feb-08 | Oct-08 | Spain | Completed |
| 26.1 | Mount Leb | Al Mreyjeh | Capacity Building within the project "Scholastic maps of Risk and Ressources" | Social | Feb-09 | Oct-09 | Spain | Completed |
| 27 | Mount Leb | Haret Hreik | Pilot Programme for strengthening the Public Health Care Centers (PHCC) in Beirut Southern Suburbs | Health | Jul-08 | Dec-09 | Spain | Completed |
| 28 | Mount Leb | Haret Hreik Ghobeiri Burj Al Barajneh | Capacity Building within the "Pilot Programme for strengthening the Public Health Care Centers (PHCC)" |  |  |  | Spain | Completed |
|  |  |  |  |  |  |  | Arezzo Municipality- Tuscany region |  |
| 29 | Mount Leb | Haret Hreik Ghobeiri Burj Al Barajneh | Provision of equipment within the "Pilot Programme for strengthening the Public Health Care Centers (PHCC)" | Health |  |  | Spain | Completed |