LEBANON RECOVERY FUND

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2010

| Programme Title & Number |  | Country, Locality(s), Thematic Area(s) |
| --- | --- | --- |
|  Programme Title: Recovery and rehabilitation of theh dairy sector in Bekâa Valley and Hermel Akkar Uplands  Programme Number – LRF-21  MDTF Office Atlas Number: |  | Lebanon (Bekâa Valley) Livestock and dairy production |

| Participating Organization(s) |  | Implementing Partners |
| --- | --- | --- |
| Food and Agriculture Organization of the United Nations |  |  Ministry of Agriculture |

| Programme/Project Cost (US$) |  | Programme Duration (months) |
| --- | --- | --- |
| MDTF Fund Contribution:  US$2.5 million |  |  | Overall Duration | 41 months |
| Agency Contribution  by Agency (if applicable) |  |  | Start Date | 1 May 2009 |
| Government Contribution (if applicable) |  |  | End Date or Revised End Date, (if applicable) | 30 September 2012 |
| Other Contribution (donor) (if applicable) |  |  | Operational Closure Date | October 2012 |
| TOTAL: |  |  | Expected Financial Closure Date | December 2012 |

| Programme Assessments/Mid-Term Evaluation |  | Submitted By |
| --- | --- | --- |
| Assessment Completed - if applicable please attach Yes No Date: __________________ Mid-Evaluation Report – if applicable please attach Yes No Date: __________________ |  | Name: Mr Ali Moumen Title: FAO Representative in Lebanon Participating Organization (Lead): FAO Email address: ali.moumen@fao.org |

LIST OF ACRONYMS

FAO		Food and Agriculture Organization

FMD		Foot and Mouth Disease

LRF		Lebanon Recovery Fund

MoA		Ministry of Agriculture

PSC		Project Steering Committee

UNDP		United Nations Development Program

VDPA		Village Dairy Producer’s Association

# NARRATIVE REPORT

# I.	Purpose

The aim of this project is to enable the recovery-rehabilitation and assistance to the livelihoods of vulnerable livestock keepers (almost one-third of whom are female-headed families) from Central Bekâa Valley, North Akkar and Hermel-Akkar Highlands, who are currently unable to keep up with the serious competition in the sub-sector. Farmers will draw indirect benefits from the project through veterinary and artificial insemination services as well as training sessions. The proposed project therefore aims to provide the basic needs for livestock keepers and farmers to resume production and income-generation activities.

The aim of this project is to enable recovery-rehabilitation and assistance to the livelihoods of vulnerable livestock keepers in Central Bekâa Valley, North Akkar and Hermel-Akkar Highlands who are resource poor, with little or no assistance and currently unable to keep up with the highly competitive animal production sub-sector. Livestock farmers will draw indirect benefits from the project through veterinary and artificial insemination services as well as training sessions.  The project is helping to provide alternative income-generating activities to the poorest farmers with the highest level of socio-economic deprivation in Hermel-Akkar highlands in order to reduce their dependence on illicit crops and maintain their farming livelihoods.

# II.	Resources

Financial Resources:

Total Programme/Project Budget:  US$2 500 000

LRF:  US$2 500 000

Government Input: US$ 0

Other: US$ 0

Total:  US$2 500 000

MAIN BUDGET ACTIVITIES:

The tenedering process for the procurement of milking machines and milk cans was completed in September and the delivery of equipment is expected to be completed during the last quarter of 2010. Training on good agriculture and dairy production techniques to farmers was conducted during the reporting period as well as continued milk testing and analysis of dairy farmers to measure the quality and safety of milk at the farm level. FAO initiated formalities for organizing farmer cooperatives in the project region and is working with the Ministry of Agriculture in rehabilitating the milk collection centres in Bekaa.

Budget: commitment and disbursement:

| LRF-21 |
| --- |
| Item | Approved Budget (in US$): | Estimated Disbursement/ Commitment (in US$) |
| Personnel and travel: | 645 000 | 401,365 |
| Contracts | 100 000 | 0 |
| Training | 125 000 | 24,832 |
| Equipment and supplies: | 1 302 500 | 409,049 |
| Miscellaneous/Other: | 164 000 | 98,902 |
| Agency Support Costs: | 163 500 | 43,080 |
| TOTAL: | 2 500 000 | 977,228 |

Personnel and travel costs:

FAO expenditures for personnel and travel cover honorarium to the Chief Technical Advisor (CTA) and technical mission from FAO Headquarters Animal Production Officer to Lebanon. Costs for local technical consultants are also included in these expenditures.

| Item: | Approved Budget cost (US$): | Estimated Disbursement/Commitment (US$) |
| --- | --- | --- |
| Personnel and travel: | 645 000 | 401,365 |

Equipment and animal production supplies:

FAO plans to procure inputs valued at US$1 302 500 and includes rehabilitation of six dairy collection centres , dairy equipment, artificial insemination, veterinary drugs, animal feeds, forage seeds and fertilizer. During the reporting period, 300 milking machines and 1,200 milking cans were delivered to Lebanon. The distribution of inputs is to take place during next reporting period. Technical specifications were also prepared for milk cooling tanks and equipment and the tendering process is to be undertaken during the first quarter of 2011.

| Item: | Approved Budgeted cost (US$): | Estimated Disbursement /Commitment (US$) |
| --- | --- | --- |
| Équipment and feed: | 1 302 500 | 409,049 |

Training

FAO carried out training to farmers and livestock and veterinary field technicians from the Ministry of Agriculture during the reporting period.

| Item: | Approved Budgeted cost (US$): | Estimated Disbursement /Commitment (US$) |
| --- | --- | --- |
| Training: | 125 000 | 24,832 |

Other costs (General Operating Expenses, and Miscellaneous):

| Item: | Approved Budget cost (US$): | Estimated Disbursement/Commitment (US$) |
| --- | --- | --- |
| Other: | 164 000 | 98,902 |

Expenses under “Other”, which groups budget lines such as contracts, general operating expenses, miscellaneous and overhead costs are indicated below. Full charge to support costs appears only on delivery of project activities.

Human Resources:

	National Staff: Two national staff with casual labour for carrying out vaccination campaign

	International Staff: One Animal Production Specialist

# III.	Implementation and Monitoring Arrangements

In order to achieve immediate and conspicuous impact, the project is carrying out the following major prioritized interventions:

a.	Building capacity of dairy farmers through extensive program of training sessions and demonstrations in improved dairy farm management, feeding, milk hygiene and processing hygienic dairy products and animal health.

b.	Support to dairy smallholders for reinforcing artificial insemination and veterinary services.

c.	Assistance to dairy smallholders in milk collection and marketing by Setting up primary milk collection centers at village levels through constitution of Village Dairy Producers’ Association (VDPA’s) grouping neighbouring villages which will be used as focal points for extension, training and provision of services to dairy farmers.

d.	Assistance to dairy smallholders for improving milk hygiene, through provision of small equipment for milk handling & processing at farm level.

e.	Empowerment of dairy small producers and VDPA’s in milk collection and marketing (milk aggregation), through reviving the existing MOA’ milk transportation trucks.

	All procurement activities are carried out under the rules and regulations of the FAO Procurement Unit.

	The project has continuous field visits to farms by technical experts to work with farmers and also the Village Dairy Producers’ Association.

# IV.	Results

During the reporting period, FAO initiated the formation of milk producers cooperatives and associations through the constitution of Village Dairy Producers’ Association (VDPAs) to help improve the standard of the dairy sector in Lebanon. VDPAs’ aim is to upgrade the dairy sector for better marketing and profitable return on dairy products and act as focal points for providing other services to farmers including artificial insemination, training programs to improve farm management practices, milk hygiene and feeding. FAO plans to organize approximately 26 cooperatives throughout the project area (18 VDPAs in Beqaa-Hermel and 6 VDPAs in Akkar) and reaching most of the small to medium size farmers and dairy producers. FAO supported the legal procedures for the establishment of 15 VDPAs which were officially authorized by the Minister of Agriculture; in addition, the project helped set up a Management Board with the support of the Bekâa Directorate of Cooperatives.

During the reporting period, the Chief Technical Advisor (CTA) conducted comprehensive training, extension and demonstration programme covering practical technical areas to help increase small livestock holder dairy productivity to VDPAs. The VDPAs have begun training farmers to improve farm management practices, milk hygiene, animal feeding and animal health. Easy-to-understand training materials were prepared and on-farm demonstrations were carried out. Training topics included treating milk composition, pollution sources of the milk, and good milking practices as well as methods to improve dairy cow nutrition, basic elements of a good feed formula, roughage production in Lebanon and the diseases that could be prevented by good concentrate and roughage feed management. Milk testing is also done for farmers in the milk collection center so farmers understand the importance good milk hygiene. Approximately 25% of the trainees are women who are mainly involved in milk production.

FMD Vaccination campaign

According to the survey conducted by the FAO, it was found that the animal health situation in the region is alarming: most dairy farmers (60%) do not follow any regular vaccination program. They depend on very sporadic vaccination programs conducted by MOA in cases of outbreak of diseases. On the other side 28% of interviewed farmers do not vaccinate at all, whereas only 12% following regular vaccination programs. Since it is an indigenous disease in Lebanon, most if not all the dairy farms have suffered from the Foot and Mouth Disease. In many cases great losses has been encountered due to the depreciated economic and overall value of the cows after recovering from the FMD disease.

The MOA has launched a national vaccination campaign for the Foot and Mouth Disease after recording many outbreaks in dairy cattle farms. The LRF-FAO project has a major intervention concern to improve the general health and veterinary standards of dairy cows in the targeted areas. It is also a strategic stand for us to support all the MOA field activities. For that reason, the LRF – FAO project personnel and vehicles were engaged with the MOA veterinarians in covering all the dairy farms in the Beqaa area. It should be noted also that most of the farms vaccinated in this campaign are of the small size 1 – 10 cows since most of the larger farms have their own veterinarians that can do the job using the MOA vaccine or purchased vaccines. The total number of cows vaccinated in Beqa was 10 000 heads.

Workshop with Dairy Cooperatives

The project organized a workshop with dairy cooperatives in October 2010 to discuss the role of the Village Dairy Producers Associations (VDPA) and the new regulations issued by the MOA concerning the dairy sub-sector.  The attendance reached 280 people including H.E. Minister MOA Dr. Hussein Hajj Hassan and his consultants, FAO representative in Lebanon Dr. Ali Moumen, Head of Sugar Beet Cooperative Mr. George Herawi, Regional Director of the Cooperatives in Bekaa, Administrative Boards of the already established VDPAs and its members, milk dealers and collectors, owners of the dairy processing plants, and farmers.

Milk Testing and Analysis

In Lebanon the milk quality problem is old and critical. It has been correlated and linked to serious health hazards and diseases in addition to other troubles such as adulteration. One of the most important goals of the FAO project OSRO/LEB/901/UNJ   is the general improvement of raw milk quality at the different milk chain levels. Numerous diagnostic tests are used to evaluate the quality of milk. These tests can be grouped under the following major categories:   Biological and microbial tests, Physical tests, Chemical tests and Adulteration tests.

The milk quality tests to evaluate the general milk situation in the areas covered by the project are: Total Aerobic Count or Standard Plate Count (SPC), Coliform Count, Titratable milk acidity, pH, Specific gravity (Density) and temperature, Fat, SNF (Solids Non Fat), protein content, Added water, freezing point, and added Carbonates.

The sampling activity was planned and studied to cover all the areas and cazas in the Beqaa Valley. For that purpose the project team collected 100 samples from farms and from milk dealers’ transportation trucks, the results were very below standards.

The number of samples that scored for the E-coli count less than 1000 cfu/gr was about 23%, whereas the number of samples for the total aerobic count that scored less than 100,000 cfu/gr was 14 (about 14 %). As for the pH, (32.8 %) were found to have values above the acceptable minimum of 6.6. All the other values were below 6.6 and 16 (27.6 %) were dangerously below 6.5. While as for the Dornic Acidity only 25 samples (31.6 %) were found to have values below or equal to the acceptable maximum of 18 degrees. All the other values (68.4 %) were above 18. Fifteen samples (42.9 %) were found to have densities with acceptable values above 1.028 grs/c.c. and less than 1.032 grs/c.c. 25 samples (71.4 %) were found with a good freezing point lower than minus 0.54 0C with a corresponding added water content of acceptable value of below 2.5 %, 24 samples (68.6 %) had a fat content of more than 3.5 %,. 88.6 % of the samples were within the normal range for the solid non fat with a maximum of 8.89 %. All the results for the protein analysis were satisfactory and comply with the Lebanese and international standards of cow raw fresh milk (2.6 – 3.6 %).

Milk Collection Centres

FAO in full collaboration with the Ministry of Agriculture (MoA) began plans to revive six milk collection centers that belong to the MOA (funded by IFAD) located Barr Ellias, Kherbt Rouha, Hermel, Baalbeck, Al Abdeh, and Wadi Khaled. These centers are an important support to FAO LRF dairy project and act as intermediary between farmers and the milk processing plants. Therefore, the legal procedures for leasing the MOA’ milk collection centers are currently under preparation and very shortly a national bid invitation will be launched. The Council Of Ministers held on 21 July 2010 has officially agreed on their lease to private sector and the MOA will empower the position of VDPA’s through the lease of insulated milk trucks.

In the Bekâa and Akkar region, there is a total of 2 065 dairy farmers, of which 310 farmers are women and their role is mainly to take care of the cows. The average number of dependants for farmers is five to eight family members. The majority of farmers have poor living standards. Milk production is low and the total quantity of milk produced daily is 28 tons with an average of nine kg of milk per cow per day. Farmers still use rudimentary utensils and the hygiene level is low. Through this project, FAO is planning to help farmers increase milk production, increase farmer’s knowledge and capacity and improve hygiene.

Poor milk practices and handling are the major causes of low quality standards and low milk prices. Almost all the farmers and milk dealers use obsolete milk cans and milk cows by hand. These unhygienic methods are the source of contaminated milk.

Procurement and delivery of project inputs:

During the reporting period, the following equipment was delivered - 350 milking machines and 1 200 stainless steel milk cans and 1 200 milk filters. This equipment will be distributed to low-income and vulnerable beneficiaries that own between three to six cows during the first quarter of 2011.

As a support to small dairy farmers with veterinary services, including a vaccination campaign and supply with appropriate veterinary drugs and equipment to control the major diseases and milk hygiene. Veterinarians and technicians from MoA will be fully involved in supporting this programme through their assignment to the VDPA’s and FAO will support farmers through the distribution of veterinary drugs, vaccines and prevention and treatment kits for common animal diseases. A procurement plan of necessary supplies was prepared during the reporting period and tendering for supplies will be carried out during the next reporting period.

Technical specifications for essential tools and utensils for milk testing, receiving, filtration and refrigeration such as: milk cooling tanks, generators, milk testing and analysis kits, detergents and utensils for cleaning of cooling tanks were prepared during the reporting period and the tendering is to be completed during the first quarter of 2011.

# V.	Future Work Plan (if applicable)

The priority action plans for the project include the completion of the establishment procedures for the Village Dairy Producer’s Associations and that involves the election of the Administrative Board. It is important to mention that in most cases, especially in Baalbek and Hermel, the project is paying the enrolment fee for very poor farmers unable to afford the fee. During the next reporting period, technical specifications for all the equipment and materials to be used as support to needy farmers in order to upgrade the hygienic standards at all levels of milk production and handling will be completed. The milk testing and analysis of milk samples collected randomly for different farms and milk dealers will continue to evaluate the physical, chemical, and biological quality of the milk. These tests will provide a general idea about the present situation of the milk quality. In 2011, FAO will repeat the same tests in the same locations in order to see the impact of the project interventions on the milk quality.

Indication of major adjustments in the strategies, targets or key outcomes and outputs.

At the request of the MoA, FAO has extended project activities to a further geographical reach in the Bekâa Valley, particularly with the rehabilitation of the milk collection centres and extensive dairy production training, FAO received approval from the Chair, LRF on 4 October to extend the project closing date from 30 April 2011 to 30 September 2012.

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Reasons for Variance (if any) | Source of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 To enable recovery-rehabilitation and assistance to vulnerable livestock keepers in Central Bekaa Valley and Hermel-Akkar Highlands and alternative income-generating activities to the poorest farmers to help reduce dependency on trading of illicit crops |
| Output 1.1 Assist identified resource families through development of dairy production | Indicator 1.1.1 # of dairy inputs distributed to farmers | Farmers able increase milk production and improve hygienic practices | Distribution of 1,200 milking cans, 350 milking machines, | yes |  | distribution campaign and farm visits for on-farm training of inputs |  |
| Output 1.2 Setting up six primary milk collection points through the creatioin of village dairy cooperatives | Indicator 1.2.1 # of established dairy cooperatives in the region | Farmers have collection points to bring milk for processing | Set up of six collection centres at village level | yes |  | site visits and working with the Village Dairy Producer’s Association |  |
| Building capacity of dairy farmers through extensive programme of training sessions and demonstrations in improved dairy farm management | Indicator 1.2.2 # of farmers trained | Farmers skills developed on improved dairy production | 1,157 farmers trained on dairy good practices | yes |  | Training of participants |  |

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Priority Area for the Peacebuilding Fund; Sector for the UNDG ITF.

The start date is the date of the first transfer of the funds from the MDTF Office as Administrative Agent. Transfer date is available on the MDTF Office GATEWAY (http://mdtf.undp.org).

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office.