Lebanon Recovery Fund

Completion Report

Project Title: Enhance Perforamance of the Social Sector (Support to the Inter Ministerial Committee on Social Issues)

Project number: LRF 7

Completed as of March 31, 2011

- Background Information

  - General project information

| Project Title & Number |  | Country, Locality(s), Thematic Area(s) |
| --- | --- | --- |
| Project Title: Enhance Perforamance of the Social Sector (Support to the Inter Ministerial Committee on Social Issues) Project Number: LRF 7 MDTF Office Atlas Number: 00058325 |  | Country Level |

| Participating Organization(s) |  | Implementing Partners |
| --- | --- | --- |
| United Nations Development Programme |  | Ministry of Social Affairs acting as secretariat to Inter-Ministerial Committee on Social Issues (IMC includes representatives from the Ministries of Finance, Economy & Trade, Education & Higher Education, Interior & Municipalities, Public Health, and Labor in addition to the Council for Development and Reconstruction) |

| Programme/Project Cost (US$) |  | Programme Duration (months) |
| --- | --- | --- |
| MDTF Fund Contribution: by Agency UNDP | 270,000 |  | Overall Duration | 3 years |
| Agency Contribution by Agency (if applicable) |  |  | Start Date | April 2008 |
| Government Contribution (if applicable) |  |  | End Date or Revised End Date, (if applicable) | March 2011 |
| Other Contribution (donor) (if applicable) |  |  | Operational Closure Date | 31 March 2011 |
| TOTAL: | 270,000 |  | Expected Financial Closure Date |  |

| Number of extensions received and dates |
| --- |
| Two extensions were granted to the project | April 2009 till March 2010 |
|  | March 2010 till March 2011 |

| Item | Approved Budget (in US$): | Total Expenses (in US$) |
| --- | --- | --- |
| Personnel and travel: | 180,000 | 93,002 |
| Trainings | 35,000 | 154,958 |
| Miscellaneous/Other: | 36,100 | 3,140 |
| Agency Support Costs: | 18,900 | 18,900 |
| TOTAL: | 270,000 | 270,000 |

List of Acronyms

MOSA – Ministry of Social Affairs

UNDP – United Nations Development Programme

NEX – National Exectution

IT – Information Technology

IMC – Inter Ministerial Committee

LRF – Lebanese Recovery Fund

  - Attachments to be Provided

    - Financial statement

    - Project Deliverables (Final Reports)

    - Publications

    - Media coverage if any

    - Evaluation report

  - Background and Issues Addressed in the Project

The Project “Enhance the Performance of the Social Sector” aims at supporting the implementation of a number of reform initiatives that were called upon in the Social Action Plan to be undertaken by the inter-ministerial committee for Social Issues.  The Project calls for supporting the Inter-Ministerial Committee to enhance the performance of the Social Sector in the country through increased coordination in the implementation of social programs and provision of social services as well as in devising and building consensus around a social development strategy.

  - Name of the Responsible Officer

Mr. Raghed Assi, Social and Local Development Programme Manager

  - Project Partners and roles

MoSA is designated as the National Implementing Agency for this project on behalf of Government of Lebanon; MoSA is responsible for managing the project and provides overall support to enable it to achieve its intended outputs and results. On the other hand, the achievement of project objectives and implementation of activities rely on the collaboration of other ministries particularly in providing relevant and useful information and guidance.  Effective collaboration will ensure a more efficient delivery of activities.

The UNDP country office support to the National execution modality will prevail. In addition to regular technical backstopping and monitoring activities regularly provided, the UNDP country office shall provide the executing agency with support services for the execution of the programme. This will ensure that technical and substantive expertise is available to the programme for coordination, recruitment, and procurement and contracting.

The project execution is carried out by the “Capacity Building for Poverty Reduction”, a joint project between UNDP and MoSA, under the support to NEX modality. Under this modality, the project is headed by the Minister of Social Affairs acting as the National Coordinator approving on all financial transactions, implementation and other logistic procedures of the project.

- Project Implementation Details

  - Project Objectives

Project Objectives and outcomes are the following:

  - Elaborate a national social development policy, strategy and related implementation plan

Outcomes

- National comprehensive and integrated social strategy elaborated

- Implementation plan designed (including time frame, budget and performance indicators)

- Consensus around the plan built (Ministries)

  - Enhance effectiveness in social service delivery and implementation of social programs between public agencies

Outcome

- Duplication in the delivery of social services among the social ministries reduced

  - Enhance effectiveness in the implementation of local development initiatives

Outcomes

- Exhaustive mapping of local development initiatives completed

- Framework of national needs and priorities defined

- Consensus around needs and priorities built (Ministries and NGOs)

  - Project Activities (if any activity has been omitted provide relevant reasons)

In reference to the project objectives mentioned in Part II section 2.1, the project has been able to achieve the majority of its objectives and overcoming many obstacles mainly linked to the unblanced political situation and the lack of the Governent formation over different periods.

The social strategy document was produced in both Arabic and English which included a general overview of the socio-economic conditions in the country, a justification and rationale for a national social development strategy, the working methodology adopted in the preparation of the document as well as the strategy structure which is composed of two transversal pillars (inclusion and development) and six elements with their relevant sub-elements and objectives as the following:

Element 1:  Achieve Better Health

Element 2:  Strengthen Social Protection Mechanisms

Element 3:  Provide Quality Education

Element 4:  Improve Opportunities for Equitable and Safe Employment

Element 5: Revitalize Communities and Encourage the Development of Social Capital

Element 6:  Encourage Socio-Economic Development

The aim of the portal is to provide the different stakeholders with a user-friendly and easily accessible coordination tool/framework in the form of map-enabled on-line portal to be able to better assess, design and implement local development initiatives in the country.  The portal aims at reducing duplication and coordinating interventions at the local level in addition to providing a framework for identifying national priorities and developmental needs for the different regions.  The portal is an easily accessible and user friendly tool that include information on socio-economic indicators by region, implemented projects and distribution of organizations concerned with social development such as schools, NGOs, health care centres and others.

Reducing duplication in the implementation of social programs and provision of services among the ministries of Social Affairs, Education and Higher Education, and Public Health.  The project collected data on similar services and programs provided by the three ministries to serve for discussions on appropriate actions to be taken for increasing efficiency and coordination in service delivery.

The on-line portal includes the following information and data in both Arabic and English:

- Socio-economic indicators, developmental needs and overview of socio-economic conditions (by sector and region)

- Distribution and basic information on active development organizations (NGOs, schools, hospitals, etc.),

- Description of developmental projects and initiatives under implementation by different organizations (since 2005 till present)

- Arabia GIS, a competent IT firm, was recruited to undertake the task of developing the portal and initiate the process.

- More than 50 institutions/bodies were contacted for various types of data whether related to indicators, studies, reports, projects, organizations, or other.

- Huge sets of data were organized, structured and re-arranged according to the different templates and forms required by the portal.

- Different versions of the portal and of the requirement documents were revised and commented on.

The electronic portal has been finalized and a demonstration was submitted to the Minister and the IMC technical team to be indorsed by the ministry.

To reduce the duplication in the delivery of social services among social ministries, the report was prepared and shared with MoSA, under the supervision of number of advisors at MoSA and the direct supervision of the Minister of Social Affairs.

  - Project outputs (provide a comparative table between the generated outputs and the ones listed in the project document and state the progress  made for every  output)

| Project Outputs Output 1: A national social development strategy and related work plan developed. | Activities | Status | Indicators |
| --- | --- | --- | --- |
|  | Develop the social strategy – conduct desk review and situational analysis | Completed | The preparation of the strategy was done in close coordination and under the supervision of the technical team of the inter-ministerial committee for social issues (IMC). Four drafts of the strategy were prepared, reviewed and thoroughly discussed by the project team, IMC, independent consultants, and various stakeholders and partners. Interviews and focus groups to discuss suggested objectives and recommendations on specific issues. Moreover, periodic meetings were also organized gathering the IMC team to stand on their views during the different phases of preparing the strategy. A national workshop with the aim of discussing the proposed draft of the strategy was organized gathering a wide spectrum of stakeholders including representatives from the government, civil society, donor and international agencies, academia, political parties and the private sector. A strategy document was produced in both Arabic and English which included a general overview of the socio-economic conditions in the country, a justification and rationale for a national social development strategy, the working methodology adopted in the preparation of the document as well as the strategy structure which is composed of two transversal pillars (inclusion and development) and six elements with their relevant sub-elements and objectives as the following: Element 1: Achieve Better Health Element 2: Strengthen Social Protection Mechanisms Element 3: Provide Quality Education Element 4: Improve Opportunities for Equitable and Safe Employment Element 5: Revitalize Communities and Encourage the Development of Social Capital Element 6: Encourage Socio-Economic Development A complete and elaborated version of the strategy (120 pages) was also developed which is an expanded version of the strategy document that provides a detailed situational analysis of major challenges, issues and conditions for each sector/element. The action plan was not finalized due to the latest political situation. |
|  | Elaborate vision statement, pillars and elements of social strategy and share with technical team | Completed |  |
|  | Consult with stakeholders including government officials, international organizations, experts, and CSOs on elements, priorities and activities for social strategy | Completed |  |
|  | Elaborate draft social strategy | Completed |  |
|  | Present draft strategy to the technical team of the Inter-ministerial committee for comments and feedback | Completed |  |
|  | Organize national workshop to present and discuss strategy | Completed |  |
|  | Update strategy based on workshop outputs and comments of IMC | Completed |  |
|  | Produce strategy document in both Arabic and English | Completed |  |
|  | Submit strategy document to Council of Ministers | On going by Minister’s office (90%) |  |
| Output 2: Provision of Social Services and implementation of programs coordinated between MoSA, MoPH and MEHE | Identify duplicated programs between ministries of Social Affairs, Public Health, and Education and Higher Education | Completed | The report on duplicated programs was prepared and shared with MoSA, under the supervision of number of advisors at MoSA and the direct supervision of the Minister of Social Affairs. |
|  | Organize/coordinate working sessions/ meetings to discuss and reach consensus on actions to reduce duplication | Completed |  |
| Output 3: Implementation of local development initiatives better coordinated and synchronized with needs and priorities – an electronic portal to coordinate local development initiatives developed and functioning | Coordinate/support the establishment of national database of local development initiatives | Completed | The aim of the portal is to provide the different stakeholders with a user-friendly and easily accessible coordination tool/framework in the form of map-enabled on-line portal to be able to better assess, design and implement local development initiatives in the country. The on-line portal includes the following information and data in both Arabic and English: Socio-economic indicators, developmental needs and overview of socio-economic conditions (by sector and region) Distribution and basic information on active development organizations (NGOs, schools, hospitals, etc.), Description of developmental projects and initiatives under implementation by different organizations (since 2005 till present) Arabia GIS, a competent IT firm, was recruited to undertake the task of developing the portal and initiate the process. More than 50 institutions/bodies were contacted for various types of data whether related to indicators, studies, reports, projects, organizations, or other. Huge sets of data were organized, structured and re-arranged according to the different templates and forms required by the portal. Different versions of the portal and of the requirement documents were revised and commented on. The electronic portal has been finalized and a demonstration was submitted to the Minister and the IMC technical team to be indorsed by the ministry. |

  - Immediate objectives, Desired Outcomes and Extent of Achievements (explain extent of achievements as compared to design and how and why it has deviated from original plan; provide actions required to improve future performance of similar activities)

All of the project objectives were accomplished during the life time of the project. However, developing the action plan related to the formulation of the national social strategy was not finalized. The main reason for not having the action plan established is that the implementation of the IMC project is done in coordination with the Ministry of Social Affairs under the direct supervision of the Minister. Given the fact that the Lebanese Government was not active for more than four months, and the porject duration ended, lead to not having the action plan in place. The current political situation has been changed and the Lebanese Government is formed, UNDP will liase with the Minister of Social Affairs to endorse the social strategy and develop the action plan accordingly .

  - Constraints (list of constraints that were encountered and measures adopted to address them)

- The endorsement of the strategy faced serious delays for reasons beyond the capacity of the project.  The strategy needs to be endorsed by the Council of Ministers, which is currently inactive given the political context the country is going through.

- The electronic portal faced delays in implementation due to the fact that the UNDP-MoSA Project “Capacity Building for Poverty Reduction” (which is the working body of the LRF project) closed by end of February 2011, whereas the end date of the LRF project activities is end of March 2011 and require on-going follow up for maintenance and updating.  To overcome this risk, the project handed over the electronic portal to another department (or project) at MoSA to follow up and maintain all portal-related activities.

- The component related to eliminating duplication in the delivery and implementation of social services was not easy to be achieved since the program team faced difficulties in obtaining relevant reliable data from concerned ministries; however, a continous follow up with the ministries took place to get the needed info.

  - Monitoring of Project Implementation (describe the monitoring and review arrangements, who was responsible for monitoring and review,  reviews that took place and what were the recommendations)

The agreed upon monitoring system for this project is similar to all other project managed and implemented by UNDP. As such, the following actions are taken to ensure the proper implementation of the project and the re-alignment to specific objectives if need be:

- Quarterly reports: the project team prepares quarterly progress reports and work plans in addition to annual reports and other reports as required by UNDP and LRF committee in Beirut.

- Periodic meetings: UNDP holds periodic meetings with the project team to substantively assess the progress of the project and advise on future steps and rectification if needed.

All of the above contributed to an in-depth follow up of the project implementation facilitating the corrective measures to be taken if amendment of specific activities is required. This is logged as a lesson learned in the quarterly report submitted to UNDP.

  - Development Impact (estimate the probable long-term effects of the project)

The Project is actually the implementation tool of many of the Social Action Plan recommendations.  The Social Action Plan that was prepared submitted by the government to the Paris III donors’ conference back in January 2008 called for a number of initiatives to enhance the performance of the social sector.  The initiatives include the elaboration of a social strategy which represents the government’s vision and policy to improve the social conditions of the population and to push the social development forward.  In addition to the social strategy, the Social Action Plan emphasized the need for increasing coordination and synchronization in the delivery of social services and programs and the implementation of local development initiatives; both are crucial to improve efficiency in public social spending and implementation of social interventions.

  - Cross-sectoral Imapct (provide an assessment of the impact of the project on poverty, gender and environment. Provide quantifiable date if possible and if not explain why?)

The main objective of the Project is to enhance the leadership and the advocacy role of the Ministry of Social Affairs, to mainstream social policy considerations in the national decision making; and to assist in the formulation and implementation of social policies at the national level.

  - Sustainability (explain how the outcomes of the project will be sustained after the project completion; provide an overview of the sustainability of the project’s outcomes with respect to financial, technical and institutional issues)

The ownership of the project results goes to the Ministry of Social Affaris, and thus the sustainability of the project outcomes is guarenteed by the Ministry of Social Affairs. On another note, it is worth mentioning that inter-ministerial committee for Social Issues and its responsibilities will remain operational even after the implementation of the aforementioned activities is completed. UNDP will continue coordination with the Minsitry of Social Affairs for other local initiatives and will ensure that the Minsitry is providing sustainability of the acheivements.

  - Beneficiaries (list of beneficiaries and participating countries).

The main beneficiary of the project is the Ministry of Social Affairs in addition to the various development stakeholders active in promoting social development and reducing poverty.  Civil Society Organizations are also major beneficiary through the work of the NGO resource unit, whereas vulnerable and poor population are indirectly targeted by the project.

  - Feedback from recipients/stakeholders

- Conclusions and Recommendations

  - Lessons learned (enumerate the lessons learned during the project’s implementation; conbcentrate on the design and management of the project including the principal factors which determined success or failure in meeting the objectives set down in the project document)

- Political stability plays a major role in achieving the project objectives whenever the project is conducted in coordination with a pulblic entity (Ministry).

- Appropiate follow up should be done with all ministries to gather needed information.

  - Recommendations (make recommendations to (a) improve the effect and impact of similar projects in the future, (b) indicate what further actions might be needed to enhance the project results)

# Footnotes

Priority Area for the Peacebuilding Fund; Sector for the UNDG ITF.

The start date is the date of the first transfer of the funds from the MDTF Office as Administrative Agent. Transfer date is available on the MDTF Office GATEWAY (http://mdtf.undp.org).

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office.

Poverty, gender and environemnt are internationally agreed cross-sectoral issues.