### PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme |
| --- | --- | --- |
| Country | : | Lebanon |
| Project No. | : | LRF 7-00058325 |
| Project Title | : | Enhance Performance of the Social Sector |
| LRF Signature date | : | October 2007 |
| Project Start date | : | April 2008 |
| Project Timeframe | : | Extended till end of March 2011 |
| Reporting Period | : | Oct. – Dec. 2010 |

I. PURPOSE

Project Summary:

The Project “Enhance the Performance of the Social Sector” aims at supporting the implementation of a number of reform initiatives that were called upon in the Social Action Plan to be undertaken by the inter-ministerial committee for Social Issues.  The Project calls for supporting the Inter-Ministerial Committee to enhance the performance of the Social Sector in the country through increased coordination in the implementation of social programs and provision of social services as well as in devising and building consensus around a social development strategy.

Project Objectives and outcomes:

  - Elaborate a national social development policy, strategy and related implementation plan

Outcomes

- National comprehensive and integrated social strategy elaborated

- Implementation plan designed (including time frame, budget and performance indicators)

- Consensus around the plan built

  - Enhance effectiveness in social service delivery and implementation of social programs between public agencies

Outcome

- Duplication in the delivery of social services among the social ministries reduced

  - Enhance effectiveness in the implementation of local development initiatives

Outcomes

- Exhaustive mapping of local development initiatives completed

- Framework of national needs and priorities defined

- Consensus around needs and priorities built

Project Linkages to National Priorities and Reconstruction Goals:

The Project is actually the implementation tool of many of the Social Action Plan recommendations.  The Social Action Plan that was prepared submitted by the government to the Paris III donors’ conference back in January 2008 called for a number of initiatives to enhance the performance of the social sector.  The initiatives include the elaboration of a social strategy which represents the government’s vision and policy to improve the social conditions of the population and to push the social development forward.  In addition to the social strategy, the Social Action Plan emphasized the need for increasing coordination and synchronization in the delivery of social services and programs and the implementation of local development initiatives; both are crucial to improve efficiency in public social spending and implementation of social interventions.

Project Implementation Partners:

International Partners: 	United Nations Development Program

National Partners:	Ministry of Social Affairs and the Inter-Ministerial Committee for Social Issues

II. RESOURCES

|  | As of December 31st, 2010 |
| --- | --- |
| Total budget approved | $270,000.00 |
| Disbursements | $195,578.69 |
| Available Balance | $74,421.31 |
| Commitments for next quarter | $74,421.31 |
| CATEGORY | TOTAL BUDGET (USD) | TOTAL EXP. TO DATE (USD) |
| Personnel | 180,000.00 | 156,259.76 |
| Training | 35,000.00 | 26,325.75 |
| Miscellaneous | 36,100.00 | 198.31 |
| Agency Management Support (7%) | 18,900.00 | 12,794.87 |
| Total | 270,000.00 | 195,578.69 |

III. RESULTS

Progress in Project Implementation:

| Project Outputs Output 1: A national social development strategy and related work plan developed. | Activities | Status |
| --- | --- | --- |
|  | Develop the social strategy – conduct desk review and situational analysis | Completed |
|  | Elaborate vision statement, pillars and elements of social strategy and share with technical team | Completed |
|  | Consult with stakeholders including government officials, international organizations, experts, and CSOs on elements, priorities and activities for social strategy | Completed |
|  | Elaborate draft social strategy | Completed |
|  | Present draft strategy to the technical team of the Inter-ministerial committee for comments and feedback | Completed |
|  | Organize national workshop to present and discuss strategy | Completed |
|  | Update strategy based on workshop outputs and comments of IMC | Completed |
|  | Produce strategy document in both Arabic and English | Completed |
|  | Submit strategy document to Council of Ministers | In progress |
| Output 2: Provision of Social Services and implementation of programs coordinated between MoSA, MoPH and MEHE | Identify duplicated programs between ministries of Social Affairs, Public Health, and Education and Higher Education | Almost completed |
|  | Organize/coordinate working sessions/ meetings to discuss and reach consensus on actions to reduce duplication | On going by Minister’s office |
| Output 3: Implementation of local development initiatives better coordinated and synchronized with needs and priorities – an electronic portal to coordinate local development initiatives developed and functioning | Coordinate/support the establishment of national database of local development initiatives | Completed / Under final revision |
|  | Contract website/portal developing company | Completed |
|  | Compile data on social indicators, projects, and concerned organization from different ministries and public institutions | Almost completed |
|  | Prepare first skeleton of portal | Completed |
|  | Prepare final version of portal and share with IMC team | Planned for February |

Implementation Constraints and Lessons Learned:

The major implementation difficulty was faced in the collection of data related to the electronic portal from the various ministries and development agencies. Some ministries and organizations showed little cooperation in providing relevant data, add to it that a good portion of the data provided required substantial efforts for organization and restructuring. Delays in feedback and redundant procedures were also very much encountered. A strong leadership and coordination among the IMC members at the ministerial level would have facilitated and speeded up the data collection process. At another level, the risk in implementation in the coming phase is mainly related to the political situation which has its implications on the possibility of endorsing the strategy by the Council of Ministries. Moreover, the fact that the Project Capacity Building for Poverty Reduction – which acts as the Secretariat to the Inter-ministerial Committee for Social Issues – will be closing end of February 2011 imposes additional risk on maintaining a proper and thorough follow up on the undertaken activities, specifically the electronic portal for coordinating local development initiatives. The work on the portal need to be handed over to another unit within the Ministry of Social Affairs, an issue that will be discussed and confirmed in the coming months.

IV. FUTURE WORK PLAN

Future work-plan for the first quarter of 2011 includes:

- Social Strategy:

  - Launch the final draft of the Social Strategy

  - Endorse the Strategy by the Council of Ministers

  - Initiate work on the action plan

- Framework of developmental needs and priorities / Development of Electronic Portal to Coordinate Local Development Initiatives

  - Finalize the development of the portal. Continue with data collection on various issues and from different organizations and institutions.  Reorganize and structure data to fit the portal’s templates and structure.

  - Continue to coordinate with Arabia GIS on portal development, structure, usability and design.

  - Present the portal to the IMC technical team and other concerned partners to stand on their opinion and feedback.

  - Modify and update portal in light of comments and feedback received; test portal for a temporary period.

  - Organize a launching event to introduce the portal and encourage further collaboration in provision of relevant information and data.

Adjustments to strategies, outcomes or outputs:

No adjustments have taken place