## Sheet1
EXPECTED OUTPUTS (YERP Component 1) | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE | PLANNED BUDGET |  | TOTAL Y1 | Balance (transferred from Y1) | TOTAL Y2 | Balance (transferred from Y2 to Y3)
|  | Q1 | Q2 | Q3 | Q4 | PARTY | Funding Source | Budget Description | Y1 |  | Y2
Output: | 1.1.1. Research conducted on the present curriculum in the 50 primary schools (grades 7, 8, and 9) with a focus on defined life skills and key competencies for primary schools | X | X | [5 empty] | 45165.49 | 176795.51 | 219885
1.1 50 primary schools (7, 8, and 9 grade) and 50 secondary schools implemented syllabi developed for the life-skill program including professional orientation and career component | [5 empty] | UNICEF | MDG-F Spain | 764140 Cash transfer to implementing partner |  |  | 60500
[8 empty] | 721030 External meetings and Conferences |  |  | 5000
[8 empty] | 611030 Salaries Costs - GS Staff |  |  | 75000
[8 empty] | 611020 Salary Costs - NP Staff |  |  | 64000
[8 empty] | 734050 Telephone usage |  |  | 1000
[8 empty] | 75100 Indirect support costs (7%) |  |  | 14385
| 1.1.2 Research conducted on the present curriculum in the 50 (20 general and 30 specialized) secondary schools with a focus on defined life skills and key competencies for secondary schools | X | X | [5 empty] | 68694 |  | 48150
[8 empty] | 721 010 Travel - related to country Programme |  |  | 15000
[8 empty] | 731010 Contractual translation |  |  | 5000
[8 empty] | 731 020 Contractual editing |  |  | 5000
[8 empty] | 752040 Programme supply |  |  | 20000
[8 empty] | 75100 Indirect support costs (7%) |  |  | 3150
| 1.1.3 Modular Life Skills-based curriculum developed, based on analyses of the findings of the studies, |  |  | X | X |  |  |  | 74900 |  | 48150
[8 empty] | 711010 International consultant |  |  | 20000
[8 empty] | 721010 Travel |  |  | 10000
[8 empty] | 732010 Rental of premises |  |  | 10000
[8 empty] | 732070 Utilities |  |  | 5000
[8 empty] | 75100 Indirect support costs (7%) |  |  | 3150
| 1.1.4. Training package developed and teachers and pedagogues trained |  | X | X | X | [5 empty] | 94160
[8 empty] | 711010 International consultant |  |  | 20000
[8 empty] | 764140 Cash transfer to implementing partner – Gvrt |  |  | 58000
[8 empty] | 731010 Contractual translation |  |  | 5000
[8 empty] | 731 020 Contractual editing |  |  | 5000
[8 empty] | 75100 Indirect support costs (7%) |  |  | 6160
| New activities | X | X | X |  |  |  |  | 31725 |  | 72632
| 1.1.5 Empowering Young People in BiH - Life skills & key competencies based approach in education and its application in practice ( work with children in secondary schools) | [6 empty] | 764 240 Other cash assistance – NGO/CSOs |  |  | 67962
[8 empty] | 75100 Indirect support costs (7%) |  |  | 4670
| 1.1.6 Empowering | X | X | X | X | [5 empty] | 72225
| Children in BiH - Life skills & key competencies based approach in education and its application in practice ( work with children in primary schools) | [6 empty] | 764 240 Other cash assistance – NGO/CSOs |  |  | 67500
[8 empty] | 75100 Indirect support costs (7%) |  |  | 4725
1.2 Capacities of 100 local communities in 17 municipalities to develop early school leavers’ database and mitigation plans enhanced to keep pupils in school and improve their employability, with specific focus on monitoring the involvement and participation of girls and other excluded children | 1.2.1 Research conducted on | X | X |  |  | UNICEF | MDG-F Spain | 764 240 Other cash assistance – NGO/CSOs | 75776 | 25553 | 47829
the evidence and reasons for: a) non-enrolment into
| primary and general secondary schools in the communities | [6 empty] | 721010 Travel - related to country Programme
| included in the project, |  | X | [7 empty] | 30000
| and | [6 empty] | 752040 Programme supply
b) evidence and reasons for dropouts in both primary
| and secondary schools | [6 empty] | 75100 Indirect support costs (7%) |  |  | 10200
| 1.2.1.a.Development of the data base on drop-outs in YERP municipalities |  |  | X | X | [5 empty] | 4500
3129
| 1.2.2 Information on dropout |  |  | X | X |  |  | 721010 Travel | 7704 |  | 7704
| of school children fed from | [9 empty] | 2000
| community system as well as on dropout/non-enrolment | [6 empty] | 764230 Meetings and conferences – NGOs/CSOs
| into local Youth employment Resource Centers | [9 empty] | 4000
734050 Telephone usage
[8 empty] | 75100 Indirect support costs (7%) |  |  | 1200
504
[8 empty] | SUBTOTAL | 303964.49 | 202348.51
SUBTOTAL | [10 empty] | 610735
EXPECTED OUTPUTS (YERP Component 2) | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE | PLANNED BUDGET |  |  |  |  | Balance (transferred from Y2 to Y3)
|  | Q1 | Q2 | Q3 | Q4 | PARTY | Funding Source | Budget Description | TOTAL Y1 |  | TOTAL Y2
[9 empty] | Y1 | Balance (transferred from Y1)
Output: | 2.1.1. Reconstruction/refurbishment of CISO |  | x |  |  | UNDP |  |  | 819544 | 139100 | 395038
2.1. Youth Information Counseling and Training Centres (CISO) established, equipped, staffed and operational | 2.1.2.1 Reconstruction/refurbishment work for the establishment of CISO (overview of location, technical documentarian for reconstruction prepared, conducting tender procedures, providing reconstruction/refurbishment services) for Gorazde, Grude, Banja Luka, Trebinje and Bijeljina | x |  |  |  |  | MDG-F Spain/ UNV SVF | 71300 Local Consultants |  |  | 5000
[8 empty] | 72100 Contractual Services-Companies |  |  | 150000
| 2.1.2.2 Supply and delivery of office furniture to CISO Banja Luka, Trebinje and Bijeljina (and Grude?) |  | x |  |  | UNDP | MDG-F Spain
| 2.1.2.3 Prepare specifications for purchase of office furniture | x
| 2.1.2.4 Conducting the tender procedure for procurement of office furniture | [6 empty] | 72200 Equipment and Furniture |  |  | 10000
2.1.2.5 Delivery of office furniture
| 2.1.1. Supply and delivery of computer equipment to CISO Banja Luka, Trebinje and Bijeljina (and Grude) |  | x |  |  | UNDP | MDG-F Spain
| 2.1.4.1 Prepare specifications for purchase of IT equipment | x | [5 empty] | 72400 Communic & Audio Visual Equip |  |  | 17000
| 2.1.4.2 Conducting the tender procedure | [6 empty] | 72800 Information Technology Equipmt |  |  | 21000
2.1.4.3 Delivery of office IT equipment
| 2.1.2. Employment of 3-4 persons in the CISO Banja Luka, Trebinje and Bijeljina (and Grude) | x | x |  |  | UNDP/ UNV | MDG-F Spain
| 2.1.2.1. Preparation ToR (job descriptions) for national UN volunteer – advisor engaged through YERP | x | [5 empty] | 71500 UN Volunteers |  |  | 142038
2.1.2.2. Hiring of UNV volunteer-advisor in additional CISOs
2.1.2.3. Appointing 1-2 persons by the PES for additional locations
2.1.2.4. Employment of 16 interns by PES
2.1.2.5. Training-mentoring of volunteer interns by UNV volunteer-advisors
| 2.1.3. Strengthening the capacity of CISO staff for more efficient and higher quality services to young people | x | x |  |  | UNDP | MDG-F Spain
| 2.1.3.1. Training needs assessment for training packages defined by PES experts | [6 empty] | 71400 International Consultants |  |  | 25000
| 2.1.3.2. Preparation of ToR (job description) for national/international consultant(s) and trainer(s) |  |  | x | x
2.1.3.3. Selection of the national/international consultant(s) and trainer(s)
| 2.1.3.4. Training preparation and delivery | [6 empty] | 72100 Contractual Services-Companies (hotels) |  |  | 25000
2.1.3.5. Strengthening of capacity of CISO interns-transfer of knowledge
2.1.3.6. Organization of exchange visits to all CISOs
2.1.3.7. Organization of study travel to CISO in EU
2.1.3.8. Purchase of books and literature for CISOs libraries
2.2. 8 500 young people, male and female provided with job counseling assistance, trainings and access to up to date labour market information | 2.2.1. Beneficiary selection and counseling | x | x | x | x | UNDP/ UNV | MDG-F Spain / UNV SVF |  | 149800 | 135323.53 | 264323.53
| 2.2.1.1. Collecting data in regard to unemployed people | [6 empty] | 74200 Audio Visual&Print Prod Costs |  |  | 40000
2.2.1.2. Preparation of CISO promotion materials (booklets, leaflets, etc.)
| 2.2.1.3. Contacting and identification of beneficiaries | [6 empty] | 72100 Contractual Services-Companies - training and counseling) |  |  | 74323.53
| 2.2.1.4. Identification of specific needs of target beneficiaries | [6 empty] | 72100 Contractual Services-Companies (campaign) |  |  | 70000
2.2.1.5. Organization and implementation of individual and group counseling interviews and sessions
2.2.1.6. Organization of specific trainings and education sessions for beneficiaries
| 2.2.2. Establishing info channels | [6 empty] | 72100 Contractual Services-Companies (design, printing and information distribution) |  |  | 80000
2.2.2.1. Information of beneficiaries about YERP activities and outcomes
2.3. Civil society and private sector engaged in development of Youth Work Experience Policy for introduction and formalization of youth work experience schemes | 2.3.1. Establishing Youth Work Experience Task Forces and actively engaging civil society and private sector | X | X | X | X | UNDP/ UNV | MDG-F Spain |  | 377906 | 498701 | 817554.24 | 216894.82
| 2.3.1.1. Management and coordination of YERP activities between agencies, contracts, assessments, workshops and trainings | [6 empty] | 61100 Salary Costs - NP Staff |  |  | 22470
| 2.3.1.2.Two Entity Youth Work Experience Task Force, involving a broad range of stakeholders including CSOs, private sector, public and governmental institutions, established and active | [6 empty] | 61200 Salaries Costs - GS Staff |  |  | 22259
| 2.3.1.3 Youth Work Experience Policy developed and submitted for adoption to governments and preparation of the Works Schemes. | [6 empty] | 71400 Contractual Services – Individuals |  |  | 162155
[8 empty] | 73100 Rental & Maintenance-Premises |  |  | 32000
[8 empty] | 71600 Travel |  |  | 20000
[8 empty] | 72100 Contractual Services-Companies (hotels) |  |  | 10000
[8 empty] | Local consultant |  |  | 27730
[8 empty] | International consultant |  |  | 25000
| 2.3.2. Providing work experience for at least 550 young people (male and female) through different employment schemes |  | x | x | x | UNDP/ UNV | MDG-F Spain | 72100 Contractual Services-Companies -Ttransfer to PESs |  |  | 495940.24
2.3.2.1. Establishment of contacts with labour market-potential employers and networking and matching with beneficiaries
2.3.2.2. Work experience provided to young people (male and female) by civil society and private sector actors by the end of programme through co-financing schemes with PES
2.4. 850 young unemployed women and women from vulnerable categories in particular received direct, one-on-one job counseling assistance (individual employment plans), training to improve employability, and direct, one-on-one job-search assistance | 2.4.1. Providing job counseling services and developing individual employment plans. | x | x | x | x | UNDP | MDG-F Spain |  | 123942 | 123941.62 | 341863.93 | 163267.3
| 2.4.1.1. Contacting and identification of beneficiaries | [6 empty] | 71600 Travel |  |  | 20000
| 2.4.1.2. Identification of specific needs of target beneficiaries | [6 empty] | 72100 Contractual Services-Companies (material) |  |  | 10000
2.4.1.3. Organization and implementation of individual and group counseling interviews and sessions
2.4.1.4. Development of individual employment plants and their monitoring and follow up
2.4.1.5. Organization of specific trainings and education sessions for beneficiaries
| 2.4.2. Identifying partners and delivery of trainings | x | x | x | x | UNDP | MDG-F Spain | 72100 Contractual Services-Companies (training) |  |  | 311863.93
2.4.2.1. Preparation of ToR for selection of service provider
2.4.2.2. Conducting the tender procedure for procurement of services provider
2.4.2.3. Delivery of services
2.6. Enhanced awareness and understanding of the value of volunteerism and civic or community engagement among citizens and local government officials in general and in relation to the role and value of volunteering in enhancing employment prospects | 2.6.1 Mapping and building links with local civil society, educational, government and private sector actors undertaken | x | x | x | x | UNV | UNV |  | 0 |  | 25500
2.6.1.1 Identify potential local CSO, educational, private sector and government sector contacts and partners
2.6.1.2 Establish contact and build relationships with local partners
| 2.6.2 Outreach activities on volunteerism and employability developed and delivered | x | x | x | X |  | UNV
2.6.2.1 Ongoing meetings and consultations with local civil society, educational, government and private sector actors
| 2.6.2.2 Delivery of presentations, public events, etc. by NUNV volunteers in local communities served by CISO |  |  |  |  | UNV
| 2.6.3 Training-capacity building activities developed for and delivered to NUNV Employment Counselor-Advisors | x | x | x | x
2.6.3.1 Assessment-mapping of training-capacity development needs
| 2.6.3.2 Development of training- capacity development content | [5 empty] | UNV
| 2.6.3.3 Delivery of training- capacity development activities |  |  |  |  | UNV
[8 empty] | 70000 – Operating Expenses* |  |  | 10000
(*Actual expense lines will be fully defined in Q1 2011)
| 2.6.4. Opportunities for Volunteering' grants for local initiatives or projects selected and disbursed | x | x | x | X
2.6.4.1 Development, launch and local promotion of call for proposals
2.6.4.2 Evaluation and selection of local initiatives – projects to be funded
| 2.6.4.3 Disbursement of grants |  |  |  |  | UNV | UNV SVF | 70000 – Operating Expenses* |  |  | 4000
| 2.6.4.4 Monitoring and follow up on funded initiatives and projects | [6 empty] | (*Actual expense lines will be fully defined in Q1 2011)
| 2.6.5 Community volunteer mobilization project(s) identified, developed and implemented | x | x | x | X
2.6.5.1 Identify potential local projects and community or CSO implementing partners
2.6.5.2 Development of local volunteer mobilization project(s) with local partner(s)
| 2.6.5.3 Mobilize additional resources and community support |  |  |  |  | UNV | UNV SVF | 70000 – Operating Expenses* |  |  | 10000
| 2.6.5.4 Implement community volunteer mobilization project(s) | [6 empty] | (*Actual expense lines will be fully defined in Q1 2011)
2.6.5.5 Post project follow up and assessment
| 2.6.6 Communications, promotional and logistical support provided for YERP community outreach activities | x | x | x | x
2.6.6.1 Ongoing communications, promotional and logistical support from UNV CO
UNV SVF
[8 empty] | 70000 – Operating Expenses |  |  | 1500
4.Monitoring and evaluation |  | x | x | x | x | UNDP | MDG-F Spain |  | 63999 | 8715.47 | 29551.46
5 MDGF Communications |  | x | x | x | x | UNDP | MDG-F Spain |  | 0 |  | 14766
SUBTOTAL | [10 empty] | 1863097.16 | 380,162,12
1482935.04
EXPECTED OUTPUTS (YERP Component 3) | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE | PLANNED BUDGET
|  | Q1 | Q2 | Q3 | Q4 | PARTY | Funding Source | Budget Description | TOTAL Y1 | Balance (transferred from Y1) | TOTAL Y2 | Balance (transferred from Y1)
Y1
[9 empty] | 32100 | 9300 | 9160.33
3.1. BiH statistical agencies equipped and trained to create migration statistics including youth migration statistics. | 3.1.1 Overall migration statistics methodology in BiH developed to ensure quality of the migration data and compatibility with EUROSTAT standards |  | X | X | X | UNFPA | MDG-F Spain | 71600 – Travel |  |  | 1000
| 3.1.1.1 Completion of mapping of legislation/forms/administrative procedures | X | [5 empty] | 71400 – Service Contracts-Individuals |  |  | 2000
| 3.1.1.2 WG regular meetings | X | X | X | X |  |  | 72145 - Training and educ,. Services |  |  | 1700
Year II Migration statistics methodology finalised; | 3.1.1.3 Study Tour |  | X |  |  |  |  | 73400 - Maint, Oper of Transport Equip |  |  | 500
| 3.1.1.4 Methodology for monitoring migration, including youth, developed |  |  |  | X |  |  | 72000-73000 – Common premises and Services (rent and utilities) |  |  | 1000
| 3.1.1.5. Dissemination/ communication of the outcomes of the WGs and the methodology |  |  |  | X |  |  | 75700 - - Training and educ,. Services (Government) |  |  | 1750
[8 empty] | 75000 – Overhead Costs (7% overhead) |  |  | 1210.33
[9 empty] | 95230 | 60300 | 180110.33
Year II Hardware and software selection completed; | 3.1.2 The central BiH and entities’ database for migration, including youth, established |  |  |  | X | UNFPA | MDG-F Spain | 71600 – Travel |  |  | 8000
Year II 5-8 of BiH statistical agencies statisticians successfully trained in migration software usage; | 3.1.2. Central BiH and entities’ database for migration, including youth, functional. |  |  |  | X |  |  | 71400 – Service Contracts-Individuals |  |  | 59000
[8 empty] | 72145 - Training and educ,. Services |  |  | 1700
[8 empty] | 72500 - Stationery & other Office Supp |  |  | 2000
[8 empty] | 73400 - Maint, Oper of Transport Equip |  |  | 1500
| 3.1.2.2 Piloting of migration database |  |  |  | X |  |  | 72000-IT Equipment |  |  | 36000
[8 empty] | 72000-73000 – Common premises and Services (rent and utilities) |  |  | 7000
[8 empty] | 74000 - Miscellaneous Operating Expens |  |  | 5700
[8 empty] | 75700 - - Training and educ,. Services (Government) |  |  | 50000
[8 empty] | 75000 – Overhead Costs (7% overhead) |  |  | 9210.33
[9 empty] | 36915 | 14502 | 49660.34
3.2. Legal basis and national coordination mechanism for monitoring migration flows, including youth migration, established. Strategy for migration with action plan created | 3.2.1. A youth migration working group, consisting of relevant institutions and organizations, will be established for the coordination of work and development of the evidence-based strategies | X | X | X | X | UNFPA | MDG-F Spain | 71600 –Travel |  |  | 4000
| 3.2.1.1 Legal solutions for all changes required in methodology identified | X | X | X |  |  |  | 71400 – Service Contracts-Individuals |  |  | 15000
| 3.2.1.2 WG regular meetings | X | X | X | X |  |  | 72145 - Training and educ,. Services |  |  | 1700
Year II Consensus building discussions among stakeholders held and consensus concerning glossary reached; | 3.2.1.3. Study Tour |  | X |  |  |  |  | 72000-IT Equipment |  |  | 10000
Year II Overall migration data recording and coordination mechanism including youth developed and established; | 3.2.1.4. Strategy for compliance with Regulation 862/2011 including action plan developed |  |  |  | X |  |  | 72000-73000 – Common premises and Services |  |  | 4000
Year II Strategy for migration with action plan created. | 3.2.1.5. Dissemination/ communication of the outcomes of the WGs and the strategy |  |  |  | X |  |  | 75700 - - Training and educ,. Services (Government) |  |  | 9750
[8 empty] | 75000 – Overhead Costs (7% overhead) |  |  | 5210.34
SUBTOTAL | [10 empty] | 238931
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
|  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Total Y1 | Balance (Transferred from Y1) | Total Y2 | Balance (Transferred from Y2 to Y3)
3.3.1 Strengthened institutional capacities and systems to reduce irregular migration and introduce circular migration schemes | [5 empty] | IOM | MDG-F Spain | JP budget 3.3.1 | 145572 | 9850 | 48792
[8 empty] | 6110 Salary costs |  |  | 19200
| 3.3.1.1 Deliver training to up to 40 CISO staff in coordination with UNDP | x | [5 empty] | 6120 Salaries |  |  | 26400
[8 empty] | 75100 Facilities & Administration |  |  | 3192
3.3.2 BiH youth provided with organized and legal opportunities for employment and internships/ apprenticeship in a selected country of destination and support to BiH returning youth on reintegrating into the BiH labour market. | [5 empty] | IOM | MDG-F Spain | JP budget 3.3.2 | 48792 |  | 112350
[8 empty] | 26110 Salary costs |  |  | 19200
[8 empty] | 6120 Salaries |  |  | 26400
| 3.3.2.1 Conduct exploratory/ negotiation visits to countries in the region (Slovenia), Sweden, and Italy regarding the possibility of circular migration schemes for young Bosnians | x | x | x |  |  |  | 75100 Facilities Administration |  |  | 7350
[8 empty] | 72400 Com. & Audio Visual |  |  | 3600
| 3.3.2.2 Conduct first circular migration schemes for young Bosnians (possibly with Slovenia or Italy) |  |  | x | x
[8 empty] | 72500 Supplies |  |  | 1800
[8 empty] | 71400 Contractual Services |  |  | 5000
[8 empty] | 7311 Rental & Maintenance |  |  | 7200
[8 empty] | 72100 Contract. Services |  |  | 20000
[8 empty] | 74500 Miscellaneous |  |  | 1800
[8 empty] | 72600 Grants |  |  | 20000
3.4. Increased awareness amongst BiH youth, their families and the general public regarding the dangers of irregular migration and the benefits of regular migration. | 3.4.1.1 Develop media plan and detailed budget, identify and contract a company(s) to design the print media (posters, leaflets and newspaper advertisements |  | x |  |  | IOM | MDG-F Spain | JP budget 3.4.1 | 12519 |  | 80603
[8 empty] | 75100 Facilities & Administration 7% |  |  | 5273
| 3.4.1.2 Identify and involve focus groups in the design and testing, and/or evaluation of the materials and message |  | x | x
[8 empty] | 74200 Audio Visual & Print Productions |  |  | 55780
| 3.4.1.3 Campaign |  | x | x | x
[8 empty] | 72200 Equip. & Furniture |  |  | 11500
| 3.4.1.4 Youth Labour Migration Working group meetings |  | x | x | x |  |  | 72700 Hospitality Catering |  |  | 2450
| 3.4.1.5 With YERC conduct trainings in schools |  | x | x | x |  |  | 73200 Premises Alteration |  |  | 5600
[6 empty] | IOM | MDG-F Spain | JP budget 3.4..2 |  |  | 30783.9
| 3.4.2 Provide targeted outreach and training to migrants participating in organized circular schemes. |  | x | x |  |  |  | 75100 Facilities & Administration |  |  | 2013.9
[8 empty] | 71300 Local Consultants |  |  | 7200
[8 empty] | 72500 Supplies |  |  | 2400
[8 empty] | 72700 Hosp/catering |  |  | 1250
[8 empty] | 73100 Rental/maintenance |  |  | 1200
[8 empty] | 74200 Audio visual & print |  |  | 1600
[8 empty] | 74500 Misc |  |  | 800
[8 empty] | 71600 Travel |  |  | 14320
SUBTOTAL YEAR 2 IOM | [10 empty] | 272528.9
[10 empty] | TOTAL YEM BiH YEAR 2 | 2985292.06
Note on J127: AHANDZIC: activity2.5 removed in 2011 funds transferred to 2.2
Note on L66: AHANDZIC: UNV 70400USD
Note on L91: AHANDZIC: 54100USD UNV
Note on L123: AHANDZIC: transfered from Activity 2.5 93,980USD

## Compatibility Report
Compatibility Report for MDGF-1931-H-BiH - 2AWP - 2011 UNFPA UNICEF IOM UNV input UNDP.xls
Run on 7/5/2011 16:01
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 4