JOINT PROGRAMME MONITORING REPORT

CONFLICT PREVENTION AND PEACE BUILDING WINDOW

This report is due no more than 20 days following the end of the 2nd and 4thquarter. Please submit to the MDF-G Secretariat at: mdgf.secretariat@undp.org

Section I: Identification and Joint Programme Status

a. Joint Programme Identification and basic data

| Date of Submission: Submitted by: Name: Mark McGinty Title: Coordination and Monitoring Officer a.i. Organization: UNRCO Contact information: mark.mcginty@undp.org +389 2 3249 574 |  | Country and Thematic Window fYR Macedonia Conflict Prevention and Peace-Building Window |
| --- | --- | --- |

| MDTF Atlas Project No: 00067217 Title: “Enhancing Inter-Ethnic Community Dialogue and Collaboration” |  | Report Number: 4 Reporting Period: January-June 2011 Programme Duration: 2009-2012 Official starting date: August 2009 |
| --- | --- | --- |

| Participating UN Organizations: UNDP UNICEF UNESCO |  | Implementing partners Secretariat for Implementation of the Ohrid Framework Agreement Municipalities of Kicevo, Kumanovo and Struga Ministry of Culture Ministry of Education and Science Bureau for Education Development State Education Inspectorate Primary and Secondary Schools in the Selected Municipalities Forum ZFD (NGO) Centre for Intercultural Dialogue (NGO) Centre for Human Rights and Conflict Resolution (NGO) Commission for Relations with the Religious Communities and Faith Groups University of Ss. “Cyril and Methodius” School of Journalism and Public Relations Additional NGO partners to be found in Annex 1 |
| --- | --- | --- |

The financial information reported should include overhead, M&E and other associated costs.

| Budget Summary |
| --- |
| Total Approved Joint Programme Budget | UNDP: | US $1,834,941 |
|  | UNICEF: | US $1,239,060 |
|  | UNESCO: | US $925,999 |
|  | Total: | US $4,000,000 |
| Total Amount of Transferred to date | UNDP: | US $1,453,756 |
|  | UNICEF: | US $895,400 |
|  | UNESCO: | US $645,745 |
|  | Total: | US $2,994,901 |
| Total Budget Committed to date | UNDP: | US $ 1,297,936 |
|  | UNICEF: | US $ 824,083 |
|  | UNESCO: | US $539,883 |
|  | Total: | US $ 2,661,902 |
| Total Budget Disbursed to date | UNDP: | US $ 1,212,881 |
|  | UNICEF: | US $ 698,311 |
|  | UNESCO: | US $379,587 |
|  | Total: | US $ 2,290,779 |

BENEFICIARIES

Direct Beneficiaries: “The individuals, groups, or organizations, targeted, that benefit, directly, from the development intervention”.

| Indicate Beneficiary type | Expected number of Institutions | Number of Institutions to date | Expected Number of Women | Number of Women To date | Expected number of Men | Number of men to date | Expected number of individuals from Ethnic Groups | number of individuals from Ethnic Groups to date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Government | 7 | 9 | 40 | 45 | 40 | 21 | 80 | 60 |
| Local Government | 3 | 3 | 15 | 29 | 25 | 48 | 45 | 77 |
| Professional Associations | 10 | 7 | 15 | 14 | 15 | 6 | 30 | -14 |
| Universities and Other Higher Education Institutions | 7 | 5 | 20 | 9 | 15 | 11 | 35 | 20 |
| CSOs | 35 | 32 | 100 | 172 | 100 | 98 | 200 | 313 |
| Secondary School Students | 90 | 90 | 44,595 | 44,595 | 49,248 | 49,248 | 93,843 | 93,843 |
| Primary School Students | 350 | 350 | 104,445 | 104,445 | 111,735 | 111,735 | 216,180 | 216,180 |
| Teachers/Professors | n/a | n/a | ~960 | ~960 | ~380 | ~380 | 1,340 | 1,340 |
| Total | 502 | 473 | 150,190 | 150,109 | 161,558 | 161,470 | 311,753 | 311,604 |

Indirect Beneficiaries: “The individuals, groups, or organizations, not targeted, that benefit, indirectly, from the development intervention”

| Indicate Beneficiary type | Expected number of Institutions | Number of Institutions to date | Expected Number of Women | Number of Women To date | Expected number of Men | Number of men to date | Expected number of individuals from Ethnic Groups | number of individuals from Ethnic Groups to date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-national government | 12 | 3 | 60 | 60 | 60 | 60 | 120 | 199 |
| Parents | n/a | n/a | ~300,000 | ~300,000 | ~300,000 | ~300,000 | ~600,000 | ~600,000 |
| CSOs | 50 | 63 | ~200 | ~ 230 | ~200 | ~110 | ~400 | ~ 340 |
| Religious Institutions | 23 | 12 | 200 | 200 | 1,100 | 1,100 | 1,300 | 1,300 |
| Media Institutions | 50 | 28 | 50 | 30 | 50 | 30 | 100 | 60 |
| Total | 135 | 72 | 300,510 | 300,365 | 301,410 | 301,265 | 601,920 | 601,709 |

- Joint Programme M&E framework

This template is the same as the one you will find in the JP documents. We have added 3 columns to provide spaces for baselines of the indicators as well as targets. All the values for indicators in this template are cumulative. This means the past values obtained accumulate (add up over time) as the joint programme gets implemented. We are expecting you to include not only the indicators but the value of these indicators. If you do not provide them, please explain the reason and how you are going to obtain this information for the next reporting period.

| Expected Results (Outcomes & outputs) | Indicators | Baseline | Overall JP Expected target | Achievement of Target to date (31 December 2010) | Means of verification | Collection methods (with indicative time frame & frequency) | Responsibilities | Risks & assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| From Results Framework (Table 1) | From Results Framework (Table 1) | Baselines are a measure of the indicator at the start of the joint programme | The desired level of improvement to be reached at the end of the reporting period | The actual level of performance reached at the end of the reporting period | From identified data and information sources | How is it to be obtained? | Specific responsibilities of participating UN organizations (including in case of shared results) | Summary of assumptions and risks for each result |
| Joint Programme Outcome 1: By 2012, key national and local institutions dealing with inter-ethnic relations more effectively build inter-ethnic consensus. |
| Outcome 1 Indicators | 30% of 45 recommendations from Assessment of National and Local Capacities for strengthening inter-ethnic dialogue and collaboration fully implemented by government, media and civil society organizations | 0% | 30% | 29% | Annual assessment by JP of implementation rate | Annual review of 45 recommendations and the extent to which they were implemented | UNDP |  |
|  | No. of dispute resolution situations where key national and local institutions follow the coordination and communication protocol | 0 | 20 | 0 | Annual assessment by JP based on sample survey | Sample survey based on observation |  |  |
|  | % of cases where pool of experts was engaged per year, disaggregated by gender | 0 | 30% | 0 3 | Report by unit that hosts pool of experts | none |  |  |
|  | No. of times Commissions for Inter-Community Relations in three target municipalities provide inputs into local decision making processes per year | 0 | 10 | 3 | Annual assessment by JP | Communication by JP with three Commissions for Inter-Community Relations |  |  |
| 1.1 Key national and local institutions in 3 micro-regions dealing with inter-ethnic relations have a system to address issues that may weaken inter-ethnic cohesion | Assessment of National and Local Capacities for strengthening inter-ethnic dialogue and collaboration completed (2008: no, 2010: yes) | No | Yes | Yes | Assessment report | none | UNDP | Political will to prioritise and revise the current regulatory framework low or political focus overwhelmed by other issues. (High) Institutional stakeholders do not participate consistently in the process. (Medium) Lack of willingness by local and national institutions to apply the coordination and communication protocol (Medium) Shortfall of M&E officers at the national and local institutions (Medium) |
|  | % of 45 recommendations of the Assessment of national and local capacities addressed through at least one activity of the Joint Programme | 0 | 60% | 54% | Annual assessment by JP of recommendations through JP activities | Annual Review of 45 recommendations and the extent to which they were implemented |  |  |
|  | No. of national and local institutions that endorse coordination and communication protocol dealing with dispute resolution | 0 | 25 | 0 | Annual assessment by JP | Review of signed decision of institution |  |  |
|  | Development of training to strengthen capacity and enhance functions for dialogue, consensus building and dispute resolution | 0 | 3 points | 2 points | curricula, training reports, How-To guide document | none |  |  |
|  | Progress towards establishing an M&E system for inter-ethnic relations | 0 points | 3 points | 2 points | methodology, training reports for M&E officers, reports of M&E officers | none |  |  |
| 1.2 Key national and local institutions dealing with inter-ethnic relations have access to a pool of facilitation experts and resources | Establishment of a pool of facilitation experts, 2008: 0, 2012: 3 points) | 0 | 3 points | 1 point | Contract with institution, training reports, campaign reports | None | UNDP | Critical number of facilitation experts may not be easy to attain. (Medium) |
|  | No. of times key national and local institutions call upon pool of facilitation expertise | 0 | 20 | 0 |  |  |  |  |
| 1.3 Local governments and community organizations have better opportunities to collaborate in 3 micro-regions | No. of fora on conflict-sensitive development, study tours and training of municipality stakeholders conducted | 0 | 10 | 8 | Fora Reports; Training reports | None | UNDP | Community response affected by extra-municipal developments. (Low) Scarce collaboration of the local-self-government units with civil society (Medium) |
|  | No. of Inter-Municipal Cooperation Agreements that facilitate interethnic collaboration among ethnically diverse municipalities signed within 3 micro-regions | 0 | 3 | 3 | Agreement documents | None |  |  |
|  | No of cases of successful collaboration between civil society organizations and local self-government units that work to improve interethnic collaboration and dialogue that are result of Grant Scheme project activities | 0 | 25 | 18 | JP on-going monitoring | Final project reports of grantees |  |  |
| Outcome 2: Capacity of the National Education System to Promote and Enhance Ethnic and Cultural Diversity Strengthened. |
| Outcome 2 Indicators | Life-Skills Based Education introduced as separate subject in secondary education | No | Yes | No | National curricula for secondary education | none |  |  |
|  | No. of new or revised text books that follow new methodology for review of text books | 0 | 13 | 0 | Assessment by Bureau for Development of Education and MoE | Text analysis of new and revised text books based on criteria |  |  |
|  | Ministry of Education adopt at least one policy or programme for dispute mitigation and resolution (refer to M&E framework for points) | 0 | 2 point | 1 point | Policy or programme document | none |  |  |
|  | No. of schools that implement inter-ethnic extracurricular activities based on the national curriculum | 0 | 18 | 18 | Implementing partners reports | List of participants |  |  |
|  | Intercultural and conflict resolution courses offered as elective offered at three universities | No | Yes | No | University Study Programmes | None |  |  |
| 2.1 Understanding, tolerance and respect for ethnic and cultural diversity incorporated in the national education policies | Life Skills Based Education curriculum for secondary education developed | No | Yes | No | Curriculum Development | None | UNICEF | It is expected that textbook review in the language subject will be easier to agree upon; may not be so. (High) Political consensus to allow objective assessment of textbooks, especially history textbooks, will be hard to achieve. (High) |
|  | No. of primary education teachers trained by 20 Bureau for Development of Education advisors in Live Skills Based Education | 750 | 1070 | 1070 | List of participants from training workshops | None |  |  |
|  | No. of secondary education teachers trained by 20 Bureau for Development of Education advisors in Life-Skills Based Education ( 2008: 0, 2012: 300) | 0 | 300 | 0 | List of participants from training workshops | None |  |  |
|  | No. of revised text books per grade following the new criteria to promote multiculturalism and inter-ethnic relations (2008: 0, 2012: 13) | 0 | 13 | 0 | Quarterly reports by Bureau for Development of Education to JP | Internal assessment of Bureau for Development of Education and the Pedagogical Service |  |  |
| 2.2 Mechanisms For Democratic Participation, Good Governance And Dispute-Resolution In The Education Sector Strengthened In 3 Micro-Regions | Training of students, teachers and parents to strengthen the existing school capacities and structures for democratic participation, governance and dispute resolution | 0 | 2 points | 1 points | Weekly reports by JP implementing partners | Training curricula and list of participants | UNICEF | Low participation and effectiveness of bodies for participation of students, parents and community members. (Low) Strong political influence in schools. (High) |
|  | No. of municipality council and inter-ethnic commission meeting attended by school representatives in 3 selected municipalities, 2008: 0, 2010: 0, 2012: 10) | 0 | 10 | 0 | Weekly reports by JP implementing partners | Minutes and list of participants from municipality council and inter-ethnic commission meeting |  |  |
|  | No. of schools in 3 selected municipalities that adopt statute, mandate and working protocols for schools bodies in a democratic and participatory manner (2008: 0, 2010: 0, 2012: 12) | 0 | 12 | 4 | Monthly monitoring reports by Centre for Human Rights | Monthly assessment based on defined criteria |  |  |
|  | No. of decisions taken by school boards in 3 selected municipalities that pilot taking decisions of the school board upon initiatives from students and parent bodies (2008: 0, 2010: 0, 2012: 10) | 0 | 10 | 5 | Monthly monitoring reports by Centre for Human Rights and the implementing partners | Monthly assessment based on defined criteria, reports |  |  |
| OUTPUT 2.3.: Children and youth have opportunities for interaction and dialogue in school and the community | No. of joint curricular and extracurricular activities for ethnically mixed groups (2008: 0, 2010: 125, 2012: 400) | 0 | 400 | 250 | Quarterly reports by JP implementing partners | Review of list of participants | UNICEF, UNESCO | School space and availability of school staff and time may be limited since most of the schools operate in shifts; (Medium) Sports and other activities may bring different ethnic groups together, but may also antagonize if first interactions not managed properly. (Low) Slow University bureaucracy |
|  | No. of children and youth that complete a course in 3 inter-ethnic community based centres | 0 | 2,500 | 900 | Quarterly reports by JP implementing partners | Review of list of participants |  |  |
|  | A university set up a centre of excellence in intercultural and peace studies | 0 points | 5 points | 2 points | Quarterly JP assessment | Assessment of a) statute of university, b) 5 study papers, c) conference report, d) study programme |  |  |
|  | No. of youth clubs that implement activities that promote inter-ethnic dialogue among university students (2008: 0, 2010: 9, 2012: 5) | 0 | 5 | 10 | Reports by youth clubs , reports by UNESCO national commission | Registry of clubs at national commission |  |  |
|  | World Heritage in Young Hands programme piloted in Associated Schools Project Network schools as elective course or extra-curricular activity | No | Yes | No | reports by schools and implementing partners | Macedonian World Heritage in Young Hands teachers kits |  |  |
| Outcome 3: By 2012, media, local and religious leaders and civil society organizations promote and practice a greater level of cultural sensitivity and civic awareness . |
| Outcome 3 Indicators | % of local and religious leaders and civil society representatives that participated in a leadership, communication skills, mediation, gender training in three municipalities that have engaged at least in one mediation over the past 12 months | 0% | 25% | 0% | Annual follow-up survey report of former training participants by JP | Random sample survey by telephone of 20% of former participants done annually by JP |  |  |
|  | [Indicator on changes in media coverage of cultural sensitivity and civil awareness (pending the development of methodology for a MRRM media monitoring mechanism) ] |  |  |  | Monitoring report by MRRM monitoring team | pending data collection |  |  |
|  | Increased media programming content which is affirmative in relation to developing a culture of dialogue between different nations, religions and cultures. (2011: pending first data collection, target: 30%) |  |  |  | Monitoring report by MRRM monitoring team Programme reports | Press reviews and media analysis on |  |  |
| OUTPUT 3.1.: Local and religious leaders and civil society are better able to participate in dispute resolution processes | Nr. of participants (local and religious leaders and civil society representatives) at leadership, communication skills, dispute resolution, local development activities and community processes in three municipalities, disaggregated by gender and ethnicity (representation of non-majority groups) | 0 | 1200 (30% women and 35% representatives of non-majority groups) | 3466 (45% women and 52% representatives of non-majority groups) | Training sheets | Quarterly review of training sheets | UNDP, UNESCO | Political/Party capture of process. (Medium) External political developments that have spill over effect on interethnic and interreligious life. (Medium) |
|  | Nr. of events which raise awareness on inter-cultural and inter-religious sensitivity | 0 | 35 | 38 | Event reports | Quarterly review of event reports |  |  |
| OUTPUT 3.2.: Journalists supported to practice culturally and conflict sensitive reporting | Nr. of participants (practicing journalist, students of journalism, related staff) at culturally and conflict sensitive media education events | 0 | 300 | 80 | Event reports | Biannual review of event reports by JP | UNDP, UNESCO | Politicization of the media (High) Reluctance/apathy by journalists and media houses. (Medium/High) Frequent turnover of journalists (Medium) |
|  | Progress towards a higher education programme on conflict sensitive reporting in School of Journalism (2008: 0, 2010: 0, 2012: 3 points) | 0 points | 3 points | 2 point | Quarterly assessment | curriculum; accreditation board in Ministry of Education; resource documents |  |  |
| OUTPUT 3.3.: Media support mechanism (expertise, monitoring, tools) established for reducing social tensions | Nr. of TV/radio/news programmes hours produced to reduce social tension (2008: 0, 2010: 0, 2012: 20) | 0 | 20 | 0 | Reports by contracted entities | Quarterly assessment of reports by contracted entities | UNDP, UNESCO |  |
|  | Progress towards setting up a Media Rapid Response Mechanism | 0 points | 5 points | 1 points | Biannual report by the School of Journalism | MRRM documentation and reports, website |  |  |
|  | Hits per month on Media Rapid Response Mechanism website (proxy for level of usage & quality) | 0 | 2000 | 0 | Quarterly review by JP | visitor log of website |  |  |

- Joint Programme Results Framework with financial information

This table refers to the cumulative financial progress of the joint programme implementation at the end of the semester. The financial figures from the inception of the programme to date accumulated (including all cumulative yearly disbursements). It is meant to be an update of your Results Framework included in your original programme document. You should provide a table for each output.

Definitions on financial categories

- Total amount planned for the JP: Complete allocated budget for the entire duration of the JP.

- Estimated total amount committed: This category includes all amount committed and disbursed to date.

- Estimated total amount disbursed: this category includes only funds disbursed, that have been spent to date.

- Estimated % delivery rate: Funds disbursed over funds transferred to date.

|  | Output 1.1: Key National And Local Institutions In 3 Micro-regions Dealing With Interethnic Relations Have A System To Address Issues that May Weaken Interethnic Cohesion Rate of Delivery: Funds transferred for Output 1.1: 509,345 Funds disbursed for Output 1.1: 503,072 Estimated % delivery rate: 99% |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 1.1: Key National And Local Institutions In 3 Micro-regions Dealing With Interethnic Relations Have A System To Address Issues That May Weaken Interethnic Cohesion | 1.1.1 Mapping of existing capacities and capacity gaps of central and local level institutions for democratic dispute settlement. |  |  |  | UNDP | Local Contracted Experts | 68,100 |  | 68,100 | 100% |
|  | 1.1.2 Initiating consensus-building dialogue at local and national level for establishing comprehensive systems of dispute resolution. |  |  |  | UNDP | Local and International experts | 125,000 |  | 125,000 | 100% |
|  | 1.1.3 Establishing systemic coordination of facilitation expertise to support dispute settlement institutions and procedures |  |  |  | UNDP | Local and International experts | 167,000 | 5,858 | 160,727 | 96 % |
|  | 1.1.4 Supporting the establishment of M&E functions within national system for inter-community dialogue. |  |  |  | UNDP | International Experts (to be contracted) | 82,645 |  | 82,645 | 100% |
|  | 1.1.5 Development of training to strengthen capacity and enhance functions for dialogue consensus building and dispute resolution of existing bodies. |  |  |  | UNDP | International Experts | 66,600 |  | 66,600 | 100% |
|  | Total |  | 509,345 | 5,858 | 503,072 | 99% |

|  | Output 1.2: Key National And Local Institutions Dealing With Interethnic Relations Have Access To A Pool Of Facilitation Experts And Resources Rate of Delivery: Funds transferred for Output 1.2: 183,000 Funds disbursed for Output 1.2: 42,428 Estimated % delivery rate: 24% |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 1.2: Key National And Local Institutions Dealing With Interethnic Relations Have Access To A Pool Of Facilitation Experts And Resources Rate of Delivery: Below 35% | 1.2.1 Strengthening capacity of Support Unit to coordinate facilitation expertise. |  |  |  | UNDP | ZELS | 79,000 |  | 19,000 | 24%% |
|  | 1.2.2 Identification of experts with dispute resolution skills and conducting advanced training |  |  |  | UNDP | ZELS | 104,000 | 80,000 | 23,428 | 23% |
|  | Total |  | 183,000 | 80,000 | 42,428 | 24% |

|  | Output 1.3: Local Governments And Community Organizations Have Better Opportunities To Collaborate In 3 Micro-Regions. Rate of Delivery: Funds transferred for Output 1.3: 552,050 Funds disbursed for Output 1.3: 472,561 Estimated % delivery rate: 86% |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 1.3: Local Governments And Community Organizations Have Better Opportunities To Collaborate In 3 Micro-Regions. | 1.3.1 Facilitating dialogue on conflict-sensitive development at local and micro-regional levels, involving relevant stakeholders. |  |  |  | UNDP |  | 41,000 |  | 10,000 | 24% |
|  | 1.3.2 Facilitate development of Inter-Municipal Cooperation agreements among municipalities in micro-regions on conflict-sensitive and inclusive economic development plans |  |  |  | UNDP |  | 75,500 | 20,000 | 55,500 | 74% |
|  | 1.3.3 Creating links among local bodies for conflict transformation, including inter-ethnic relations commissions, school boards, religious leadership and student organizations |  |  |  | UNDP | 3 Municipalities CICRs | 53,000 |  | 53,000 | 100% |
|  | 1.3.4 Organizing a Grant Scheme with incentives for conflict transforming initiatives |  |  |  | UNDP |  | 344,600 | 12,517 | 316,111 | 92% |
|  | 1.3.5 Enhancing capacity of municipalities to take up decentralized responsibilities on managing local culture and cultural diversity |  |  |  | UNDP |  | 37,950 |  | 37,950 | 100% |
|  | Total |  | 552,050 | 32,517 | 472,561 | 86% |

|  | Output 2.1: Understanding, Tolerance And Respect For Ethnic And Cultural Diversity Incorporated In The National Education Policies Rate of Delivery: Funds transferred for Output 2.1: 610,000; Funds disbursed for Output 2.1: 144,210 Estimated % delivery rate: 23% |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 2.1: Understanding, Tolerance And Respect For Ethnic And Cultural Diversity Incorporated In The National Education Policies | 2.1.1 Strengthen capacity of the MoES and its related institutions for incorporating contents related understanding, tolerance and respect for ethnic and cultural diversity in the secondary education curricula |  |  |  | UNICEF | BED MoES; Centre for Human Rights and Conflict Resolution (CHRCR) | 10, 000 | 5,670 | 2,330 | 23% |
|  | 2.1.2 Create capacity within the existing in-service teacher training system for enforcement of understanding, tolerance and respect for ethnic and cultural diversity in both primary and secondary education schools |  |  |  | UNICEF | BED MoES CHRCR | 500,000 | 356,680 | 98,327 | 20% |
|  | 2.1.3 Support the Pedagogical Service in the BED (MoES) for introducing and applying criteria related to multiculturalism, understanding, tolerance and respect for ethnic and cultural diversity in textbooks development and accreditation |  |  |  | UNICEF | BED MoES CHRCR | 40,000 | 24,096 | 13,561 | 35% |
|  | 2.1.4 Support the Department for Advancement of the Education of Minorities in building their capacity to develop policies and programmes for communication and dispute resolution |  |  |  | UNICEF | BED MoES | 60,000 | 40,874 | 29,992 | 50% |
|  | Total |  | 610,000 | 427,320 | 144,210 | 23% |

|  | Output 2.2: Mechanisms For Democratic Participation, Good Governance And Dispute-Resolution In The Education Sector Strengthened In 3 Micro-Regions Rate of Delivery: Funds transferred for Output 2.2: 173,000; Funds disbursed for Output 2.2: 50,876 Estimated % delivery rate: 29% |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output: 2.2: Existing mechanisms for democratic participation, good governance and conflict resolution at all levels of the education sector strengthened in 3 selected micro-regions. | 2.2.1 Strengthen capacity (mandate, statute, working protocols, election criteria) of existing governance bodies and structures at schools level (school boards, parents’ councils, students’ organization) |  |  |  | UNICEF | BED FORUM ZFD CID CHRCR | 150,000 | 32,476 | 50,876 | 25% |
|  | 2.2.2 Support establishment of communication and coordination mechanism between school boards and municipal bodies (councils and inter-ethnic committees) and national structures (MoES, BED) for increased democratic participation and dispute resolution |  |  |  | UNICEF | BED FORUM ZFD CID CHRCR | 23,000 | 0 | 0 | 0% |
|  | Total |  | 173,000 | 32,476 | 50,876 | 29% |

|  | Output 2.3: Children And Youth Have Opportunities For Interaction And Dialogue In School And The Community Rate of Delivery: Funds transferred for Output 2.3: 615,420; Funds disbursed for Output 2.3: 241,173 Estimated % delivery rate: 39% |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 2.3: Children And Youth Have Opportunities For Interaction And Dialogue In School And The Community | 2.3.1 Joint curricular activities in mixed schools (e.g. on subjects such as IT, physical education, civic education, foreign languages) and extracurricular activities (e.g. sport activities, school events, school camps) organized |  |  |  | UNICEF | 3 Municipalities; FORUM ZFD CID CHRCR | 180,000 | 45,929 | 56,097 | 32% |
|  | 2.3.2 Support the functioning of community-based youth centers. |  |  |  | UNICEF | 3 Municipalities FORUM ZFD CID | 195,000 | 29,316 | 54,367 | 28% |
|  | 2.3.3 Promote intercultural dialogue and multiple partnerships through higher education structures (e.g. student clubs , university chairs) |  |  |  | UNESCO | Ministry of Education; UNESCO National Commission Ministry of Culture School of Journalism and Public Relations University of Ss. “Cyril and Methodius” FON MIT International University of Struga UNESCO Clubs School of Journalism and Public Relations | 240,420 | 192,272 | 130,709 | 54% |
|  | Total |  | 615,420 | 267,517 | 241,173 | 39% |

|  | Output: 3.1: Local And Religious Leaders And Civil Society Are Better Able To Participate In Dispute-Resolution Processes Rate of Delivery: Funds transferred for Output 3.1: 245,500 Funds disbursed for Output 3.1: 155,968 Estimated % delivery rate: 64% |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output: 3.1: Local And Religious Leaders And Civil Society Are Better Able To Participate In Dispute-Resolution Processes | 3.1.1 Identification of local leaders and facilitation of local civic dialogue on topical issues |  |  |  | UNDP | (Implementing Partners to be determined upon end of Procurement process) | 22,000 |  | 22,000 | 100% |
|  | 3.1.2 Leadership and communication skills training of local leaders |  |  |  | UNDP |  | 18,500 |  | 18,500 | 100% |
|  | 3.1.3 Support for the establishment of public dialogue opportunities on topics relevant to intercultural and interreligious dialogue . |  |  |  | UNESCO | Ministry of Culture; Commission for Relations among the Religious Communities and Faith Groups UNESCO National Commission; UNESCO Clubs | 205,000 | 164,620 | 115,468 | 56% |
|  | Total |  | 245,500 | 164,620 | 155,968 | 64% |

|  | Output 3.2: Journalists Supported To Practice Culturally And Conflict Sensitive Reporting Rate of Delivery: Funds transferred for Output 3.2: 237,000; Funds disbursed for Output 3.2: 70,889 Estimated % delivery rate: 30% |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 3.2: Journalists Supported To Practice Culturally And Conflict Sensitive Reporting | 3.2.1 Formal and informal education of reporters, editors and media owners on the aspects of the conflict-sensitive reporting. |  |  |  | UNESCO | School of Journalism and Public Relations Association of Journalists | 220,000 | 113,896 | 70,889 | 32% |
|  | 3.2.2 Facilitating a 'Community of Interest' among opinion-makers nation-wide on providing conflict-mitigating perspectives |  |  |  | UNDP |  | 17,000 | 0 | 0 | 0% |
|  | Total |  | 237,000 | 113,896 | 70,889 | 30% |

|  | Output 3.3: Media Support Mechanism Established For Reducing Social Tensions Rate of Delivery: Funds transferred for Output 3.3: 400,000; Funds disbursed for Output 3.2: 51,492 Estimated % delivery rate: 12% |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 3.3: Media Support Mechanism Established For Reducing Social Tensions | 3.3.1 Setting up of an online resource, connected to the Pool of Facilitation Expertise housed in ZELS, with the aim of making a positive contribution to debates on sensitive multicultural and multireligious issues. |  |  |  |  |  | 200,000 | 45,780 | 39,426 | 20% |
|  | 3.3.2 Support to local media in developing and broadcasting social content programmes and public service announcements that promote harmony and peaceful settlements of disputes |  |  |  | UNDP |  | 200,000 | 28, 934 | 12,066 | 6% |
|  | Total |  | 400,000 | 74,714 | 51,492 | 12% |

SECTION II: Joint Programme Progress

The second section of the report is intended to shed light on the major advances and difficulties of the Joint Programme. It also aims to collect information on two important objectives that all joint programmes are contributing towards (interagency work, delivering as One and Development effectiveness as described by the Paris Declaration and the Accra Action Agenda).

- Narrative on progress, obstacles and contingency measures

Please provide a brief overall assessment of the extent to which the joint programme components are progressing in relation to expected outcomes and outputs, as well as any measures taken for the sustainability of the joint programme during the reporting period. Please, provide examples if relevant. Try to describe facts avoiding interpretations or personal opinions.

A full, results-based report on outputs and outcomes can be found in Annex 2 of this document.

These are the highlights of progress in relation to outcomes and outputs during the reporting period:

Outcome 1 (Governance):

- Key national and local institutions dealing with inter-ethnic relations achieved significant progress towards the building of inter-ethnic consensus. 29% of the recommendations of the participatory assessment were addressed by Government and civil society organizations, strengthening inter-ethnic dialogue, collaboration and coordination.

- At national level, the Secretariat for Implementation of the Ohrid Framework Agreement was supported to implement a grant scheme to enhance the role of civil society in the area of inter-ethnic relations.

- At the local level, the decision-making processes of Commissions for Inter-Community Relations (CICRs) have been strengthened, turning the CICRs into a mechanism for efficient facilitation of dialogue between the communities and local self-governments.

Outcome 2 (Education):

- Concept for textbook development and methodology for textbooks review to ensure respect for of the ethnical, religious and gender diversity developed and launched with key stakeholders.

- Digital educational contents for the subjects of: Macedonian language, Albanian language, Macedonian language for students of the other communities, Albanian language as an elective subject, history, music education, art education and civic education developed and launched in schools. The aim of these digital contents is to promote multiculturalism and inter-ethnic relations in education. These are also a model for developing additional digital contents in other relevant curricula contents.

- Draft LSBE curriculum for secondary education developed.

- Strategies and action plans for implementation of extracurricular activities on multiculturalism at municipal level for Kumanovo, Kicevo and Struga developed.

Outcome 3 (Society):

- In order to create a network of dispute resolution practitioners, representatives of civil society organizations and community leaders were trained in dispute resolution methodologies. These participants will become part of a cadre of dispute resolution practitioners connected to a larger national pool of facilitation experts.

- The UNESCO Chair in Media, Dialogue and Mutual Understanding was established at the School of Journalism and Public Relations.

- “The Role of Higher Education in Fostering Inter-cultural Dialogue and Understanding in a Multiethnic Society” Conference gathered academics and students from most higher education institutions in the country to reflect on their work in this field and begin to chart a path ahead.

- Capacity building project grants implemented by UNESCO Clubs for enhancing interethnic dialogue in universities and the three pilot municipalities focusing on themes such as culture, environment and technology.

- “Diversity Reporting” handbook was produced and printed, which offers guidelines and recommendations to journalists on the ways in which the media can better reflect the diversity in their newsrooms and through the daily journalistic work.

Are there difficulties in the implementation? What are the causes of these difficulties? Please check the most suitable option

b.

UN agency Coordination

Coordination with Government

Coordination within the Government (s)

Administrative (Procurement, etc)  /Financial (management of funds, availability, budget revision, etc)

Management: 1. Activity and output management 2. Governance/Decision making (PMC/NSC) 4. Accountability

Joint Programme design

c.

External to the Joint Programme (risks and assumptions, elections, natural disaster, social unrest, etc)

Other. Please specify:

- Please, briefly describe (250 words) the current difficulties the Joint Programme is facing. Refer only to progress in relation to the planned in the Joint Program Document. Try to describe facts avoiding interpretations or personal opinions.

Have not encountered major problems that hamper progress in relation to the planned results outlined in the Joint Program Document.

- Please, briefly describe (250 words) the current external difficulties (not caused by the joint programme) that delay implementation. Try to describe facts avoiding interpretations or personal opinions.

Have not encountered major external difficulties that have delayed implementation.

Slight delays were encountered for few activities corresponding to the parliamentarian elections, which took place in June 2011. Two CSOs postponed the activities for one month, given the local authorities’ engagement in the campaigns and election process itself.

Please, briefly explain (250 words) the actions that are or will be taken to eliminate or mitigate the difficulties (internal and external referred B+C) described in the previous text boxes b and c. Try to be specific in your answer.

N/A

- Inter-Agency Coordination and Delivering as One

The MDG-F Secretariat asks the office of the Resident Coordinator complete this subsection, briefly commenting on  the joint programme, providing its perspective from within the broader country context. The aim is to collect relevant information on how the joint programme is contributing to inter-agency work and Delivering as One.

You will find some multiple choice questions where you can select the most appropriate to the case, text boxes to provide narrative information and 2 indicators on common processes and outputs to measure interagency coordination. These indicators have been already used to measure progress on the One UN pilot countries. Please, refer to the examples in the subsection to complete the information requested.

- Is the Joint Programme still in line with the UNDAF? Please check the relevant answer

Yes No

- If not, does the Joint Programme fit into the national strategies?

Yes No

If not, please explain:

What types of coordination mechanisms and decisions have been taken to ensure joint delivery?

Are different joint programmes in the country coordinating among themselves? Please reflect on these questions above and add any other relevant comments and examples if you consider it necessary:

Joint Coordination Mechanisms & Decisions

The programme teams of each implementing agency sit together in common premises to allow for better coordination and cross fertilisation between the programme’s components. The team, while having its own office space, also use office space provided by the Government where specifically joint programme meetings with Government partners take place.

A tri-lateral MoU has been developed and agreed between agencies for the common premises and programme services.

An online workspace for the programme team has been established that contains a calendar of activities, news feed, important documents / reports, etc.

Organisational arrangements

The Programme Management Team meets weekly to discuss and decide on joint implementation issues.

The Coordination Programme Coordinator to ensure day-to-day coordination and coherence of programme activities. Since June, the UN Coordination Officer is acting as Programme Coordinator a.i.

The heads of UN implementing agencies meet at least every two months to assess progress and to give direction to the PMT.

The PMC responsible for the technical and operational oversight, management and coordination meets bi-annually.

The NSC responsible for the overall programme activities meets annually.

Other Joint Programmes

The area of intervention of this MDGF Joint Programme is quite specific and has no overlap with the other Joint Programme area of the UN – domestic violence. However, the programme coordinators are encouraged to share best practices and the RC and RC Office act as a conduit to and between the two programmes.

Please provide the values for each category of the indicator table described below:

| Indicators | Baseline | Current Value | Means of Verification | Collection methods |
| --- | --- | --- | --- | --- |
| Number of managerial practices (financial, procurement, etc) implemented jointly by the UN implementing agencies for MDG-F JPs. | 0 | 6 | Internal Reporting System | Internal Minutes |
| Number of joint analytical work (studies, diagnostic) undertaken jointly by UN implementing agencies for MDG-F JPs. | 0 | 4 | Internal Reporting System | Internal Minutes |
| Number of joint missions undertaken jointly by UN implementing agencies for MDG-F JPs. | 0 | 12 | Internal Reporting System | Internal Minutes |

Please provide additional information to substantiate the indicators value (150 words). Try to describe qualitative and quantitative facts avoiding interpretations or personal opinions.

The JP has taken several missions and trainings together, such as on communication, conflict-sensitivity, capacity assessment, as well as gathering other donors on inter-ethnicity in education.

Many field visits are organised jointly among the agencies, and several workshops were organised as a joint activity between agencies.

- Development Effectiveness: Paris Declaration and Accra Agenda for Action

This subsection seeks to gather relevant information on how the joint programme is fostering the principles for aid effectiveness by having appropriate ownership, alignment, harmonization and mutual accountability in the last 6 months of implementation.

You will find some multiple choice questions where you can select the most appropriate to the case, text boxes to provide narrative information and 2 indicators on ownership ad alignment. These indicators have been used extensively to measure progress on the Paris Declaration. Please, refer to the examples in the subsection to complete the information requested.

Ownership: Partner countries exercise effective leadership over their development policies, and strategies and co-ordinate development actions

Are Government and other national implementation partners involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the government involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Who leads and/or chair the PMC and how many times have they met?

Institution leading and/or chairing the PMC:

Resident Coordinator and DPM for Implementation of the Ohrid Framework Agreement

Number of meetings: 3

Is civil society involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the civil society involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Are citizens involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities are citizens involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Where is the joint programme management unit seated?

National Government  Local Government  UN Agency  By itself  other, specify

Based on your previous answers, briefly describe the current situation of the government, civil society, private sector and citizens in relation of ownership, alignment and mutual accountability of the joint programmes, please, provide some examples. Try to describe facts avoiding interpretations or personal opinions.

Government, fully supportive and involved in the programme through regular meetings, consultations, coordination with and among other government bodies, adopting methodologies and concepts for JP activities. The highest level political leadership has consistently supported JP activities. The Deputy Prime Minister co-chairs the Programme Management Committee and all government counterparts have demonstrated their commitment to the programme through the engagement of senior representatives.

Many of the activities of the JP are fully implemented by civil society   organisations.  Also, partnerships with institutions at the national level are established, in particular related to the support of dispute resolution system to enhance inter-ethnic dialogue and collaboration through national and local level through the Support Unit.

- Communication and Advocacy

Has the JP articulated an advocacy & communication strategy that helps advance its policy objectives and development outcomes?  Please provide a brief explanation of the objectives, key elements and target audience of this strategy, if relevant, please attach (max. 250 words).

Yes   No

A draft Advocacy and Communication Strategy is developed. A full-time UNCT Communications Officer has been hired who is providing support to the communications and advocacy of the programme.

A website dedicated to the JP as part of the UN website (www.un.org.mk) has been set up and provides a space for communicating the objectives, activities and results of the programme to partners and the general public.

A number of communications products have been produced during the reporting period – a programme leaflet, programme banner and local programme factsheets.

What concrete gains are the advocacy and communication efforts outlined in the JP and/or national strategy contributing towards achieving?

Increased awareness on MDG related issues amongst citizens and governments

Increased dialogue among citizens, civil society, local national government in relation to

development policy and practice

New/adopted policy and legislation that advance MDGs and related goals

Establishment and/or liaison with social networks to advance MDGs and related goals

Key moments/events of social mobilization that highlight issues

Media outreach and advocacy

Others (use box below)

What is the number and type of partnerships that have been established amongst different sectors of society to promote the achievement of the MDGs and related goals? Please explain.

Faith-based organizations     	Number

Social networks/coalitions    	Number 1

Local citizen groups                	Number

Private sector 		      	Number

Academic institutions              	Number 5

Media groups and journalist   	Number

Others (use box below)          	Number

Informal Civil Society Network on local level in three municipalities formed under JP.

Partnership agreement is signed with the Institute for Social, Political and Judicial Research and Centre for Human Rights and Conflict Resolution.

Partnership formed with OHCHR in relation to grant giving programme for CSOs related to Human Rights “Assisting Communities Together. In addition, a   Partnership with UN Women has been established related to Gender and Local Development Forum.

The UNESCO Chair at the School of Journalism is developing partnerships with a number of academic institutions, including the Southeast European University.

What outreach activities do the programme implement to ensure that local citizens have adequate access to information on the programme and opportunities to actively participate?

Focus groups discussions

Household surveys

Use of local communication mediums such as radio, theatre groups, newpapers, etc

Open forum meetings

Capacity building/trainings

Others

Section III: Millennium Development Goals

- Millennium Development Goals

The MDG-F main objective is to contribute to progress to the attainment of the Millennium Development Goals worldwide. This subsection aims to capture data and information on the joint programmes contribution to 1 or more Millennium Development Goals and targets.

For this purpose the Secretariat has developed a matrix where you should link your joint programme outcomes to 1 or more Millennium Development Goals and Targets. This matrix should be interpreted from left to right. As a first step you should reflect on the contributions that each of the JP outcomes is making to one or more MDGs. Once this linked is established, it needs to be further developed by connecting each joint programme outcome to one or more MDG targets. As a third step you should estimate the number of beneficiaries the JP is reaching in each of the specifics outcomes. Finally you should select the most suitable indicators from your joint programme’s M&E framework as a measure of the Millennium targets selected. Please, refer to the example provided below.

| MDG 2 | Joint Programme Outcome 1 | MDG Target | # Beneficiaries reached | MDG Indicators | JP Indicator |
| --- | --- | --- | --- | --- | --- |
| Goal #2: Achieve Universal Primary Education |  |  |  |  |  |
|  | Joint Programme Outcome 2 | MDG Target 2.A |  | Indicator | JP Target |
|  | Outcome 2: Capacity of the national education system to promote and enhance ethnic and cultural diversity strengthened | Ensure that, by 2015, children everywhere, boys and girls alike, will be able to complete a full course of primary schooling |  | 2.1 Net enrolment ratio in primary education 2.2 Proportion of pupils starting grade 1 who reach last grade of primary 2.3 Literacy rate of 15-24 year-olds, women and men | - Proportion of ethnic groups in the completion of primary and secondary education. - Proportion of girls and boys completing primary education, by ethnic background. - Proportion of girls and boys completing secondary education, by ethnic background. - No of revised textbooks as per new criteria promoting multiculturalism and inter-ethnic relations |
|  | Joint Programme Outcome 3 | MDG Target |  | Indicator | JP Target |

Additional Narrative comments

Please provide any relevant information and contributions of the programme to the MDGs, whether at national or local level.

Please provide other comments you would like to communicate to the MDG-F Secretariat:

Section 4: General Thematic Indicators

| Type/number of new mechanisms (supported by the joint programme) that respond to popular demands/dissatisfaction related to existing and/or potential sources of conflict (i.e. denial of rights, urban violence, discrimination, etc.) Applies Does not apply. if so, please move forward to section 2 |
| --- |
| Policies Laws Plans Forums/roundtables Working groups Dialog clubs Cooperation agreements Other, pls. specify: | No. National 2 No. National No. National 1 No. National 15 No. National 1 No. National No. National No. National 1 | No. Regional No. Regional No. Regional No. Regional No. Regional No. Regional No. Regional | No. Local No. Local No. Local 1 No. Local No. Local No. Local No. Local No. Local |
| Please briefly provide some contextual information on the above mentioned mechanisms and the country/municipality where it will be implemented (base line, stage of development and approval, potential impact): “Participatory Assessment of National and Local Level Capacities Strengthening Inter-Ethnic Dialogue and Collaboration” Baseline: None Stage of Development: Assessment finalized Potential impact: Systemic approach at national and local levels for addressing tensions; same mechanisms to be used for development planning in mixed communities. Donor’s coordination meetings on donors’ activities on inter-ethnic issues in education Baseline: N/A Stage of Development: Matrix of activities completed. To be disseminated. Potential impact: Improved coordination among donor organizations which have activities related to inter-ethnic relations in education for greater overall impact. Working group for policy and programme development for communication and advancement of the inter-ethnic relations in education established within the Ministry of Education and Science as part of the programme. Baseline: None Stage of Development: Established, one meeting. Potential impact: Coordination of activities among ministry bodies on inter-ethnic issues. Channel of implementation of JP activities. |
| Number of citizens benefiting from the above mentioned mechanisms to channel their concerns: Applies Does not apply |
| Total No. Citizens Youth under the age of 25 years IDPs/refugees other, pls. specify: municipal staff, parents, teachers,... | Total No. ~900,000 ( % of ethnic groups100%) Total No. 310,164 Total No Total No Total No ~600,000 | Total Women Men Urban Urban ~230,000~115,000 ~115,000 Urban Urban ~450,000 ~225,000 ~225,000 | Total Women Men Rural Rural ~80,000 ~40,000 ~40,000 Rural Rural ~150,000 ~75,000 ~75,000 |

| Number of local and/or community plans for violence prevention implemented targeted to: Total No. 0 Youth No. ( % of ethnic groups ) Women No. ( % of ethnic groups ) Ethnic groups No. other, pls. specify: No. ( % of ethnic groups ) | Comments |
| --- | --- |

| Number of organizations and individuals with strengthened capacity in the following areas: |  |
| --- | --- |
| Violence prevention/conflict Conflict mediation Conflict resolution Resolution and settlement of disputes Cooperation agreements Create dialogue | Religion leaders No. 10 ( % of ethnic groups100) Community leaders No. 10 ( % of ethnic groups100) Citizens: women # men No. ( % of ethnic groups ) Judges No. ( % of ethnic groups ) Policeman No. ( % of ethnic groups ) Civil servants No. 6 ( % of ethnic groups100) Government representatives No. 20 ( % of ethnic groups100) Youth organizations No. 10 ( % of ethnic groups100) Community based organizations No ( % of ethnic groups ) |

| Number and type of violent incidents reported in the area of intervention through formal and informal channels: | Comments: None. |
| --- | --- |
| Social incidents (e.g. riots) No. Crime (Theft, etc) No. Ethnic groups related No. Other, pls. Specify No. |  |

Annex 1:

UNITED NATIONS JOINT PROGRAMME

“Enhancing Inter-Ethnic Community Dialogue and Collaboration”

LIST OF NGO PARTNERS

| Geographical Focus of Work | Name of NGO | UN Agency |
| --- | --- | --- |
| Skopje | Centre for Human Rights and Conflict Resolution | UNICEF |
| Skopje | Stranskite jazici – prozorec kon svetot (,,Foreign languages - a window of the world”) | UNESCO |
| National | Visokata skola za novinarstvo I odnosi so javnosta | UNESCO |
| National | Institut za razvoj na zaednicata (IRZ) -Community Development Institute (CDI) - | UNESCO |
| Kicevo | Centar za razvoj na zaednicata - Kicevo | UNESCO |
| Kicevo | Association of Albanian Women in Macedonia | UNDP |
| Kicevo | Civic Association “Dituria”, | UNDP |
| Kicevo | Active of Roma women “Prerodba” | UNDP |
| Kicevo | “DEA” | UNDP |
| Kicevo | “ORT” | UNDP |
| Kicevo | “Gajret” | UNDP |
| Kicevo | “Alliance of blind” | UNDP |
| Kicevo | Women association “Integra” | UNDP |
| Kicevo | NGO ”Center for rural development” | UNDP |
| Kicevo and Struga | Forum ZFD | UNICEF |
| Struga | Women’s Association Struga | UNDP |
| Struga | Association of Egyptian “Esnafot” Struga | UNDP |
| Struga | “Uranija” | UNDP |
| Struga | "Ezerka” | UNDP |
| Struga | “Aureola” | UNDP |
| Struga | “Punkte” | UNDP |
| Struga | “Akva” | UNDP |
| Kumanovo | Centre for Intercultural Dialogue | UNICEF |
| Kumanovo | “Kolo Srpskih Sestara” | UNDP |
| Kumanovo | “Vior” Women Multiethnic Center | UNDP |
| Kumanovo | “Majka” Center, Youth Organization, | UNDP |
| Kumanovo | “Sirma” | UNDP |
| Kumanovo | “Roma Information Center” (part of DROM) | UNDP |
| Kumanovo | Mesecina”, Humanitarian Association of Roma | UNDP |
| Kumanovo | DROM-Kumanovo | UNESCO |
|  |  | UNDP |
| Bitola | Mladinski Kulturen centar - Bitola | UNESCO |
| Krusevo | Mladinska alijansa - Krusevo | UNESCO |
| Ohrid | Mladinski sovet - Ohrid | UNESCO |
| Struga | Trening centar za menagment na konflikti - Struga | UNESCO |
| Stip | Detski parlament - Stip | UNESCO |

ANNEX 2:

20 July, 2011

UN Programme to Enhance Inter-Ethnic 
Dialogue and Collaboration

Report on Results

January -June 2011

Programme Duration:  August 2009 - July 2012

Programme Funds:  USD $4 Million

Donor: Government of Spain through the UN MDG Achievement Fund

| UN Implementing Agencies UNDP UNICEF UNESCO | Implementing partners Secretariat for Implementation of the Ohrid Framework Agreement Municipalities of Kicevo, Kumanovo and Struga Ministry of Culture Ministry of Education and Science Bureau for Education Development State Education Inspectorate Primary and secondary schools in the selected municipalities Commission for Relations with the Religious Communities and Faith Groups University of Ss. “Cyril and Methodius” |
| --- | --- |

RESULTS HIGHLIGHTS

Outcome 1 (Governance):

- Key national and local institutions dealing with inter-ethnic relations achieved significant progress towards the building of inter-ethnic consensus. 29% of the recommendations of the participatory assessment were addressed by Government and civil society organizations, strengthening inter-ethnic dialogue, collaboration and coordination.

- At national level, the Secretariat for Implementation of the Ohrid Framework Agreement was supported to implement a grant scheme to enhance the role of civil society in the area of inter-ethnic relations.

- At the local level, the decision-making processes of Commissions for Inter-Community Relations (CICRs) have been strengthened, turning the CICRs into a mechanism for efficient facilitation of dialogue between the communities and local self-governments.

Outcome 2 (Education):

- Concept for textbook development and methodology for textbooks review to ensure respect for of the ethnical, religious and gender diversity developed and launched with key stakeholders.

- Digital educational contents for the subjects of: Macedonian language, Albanian language, Macedonian language for students of the other communities, Albanian language as an elective subject, history, music education, art education and civic education developed and launched in schools. The aim of these digital contents is to promote multiculturalism and inter-ethnic relations in education. These are also a model for developing additional digital contents in other relevant curricula contents.

- Draft LSBE curriculum for secondary education developed.

- Strategies and action plans for implementation of extracurricular activities on multiculturalism at municipal level for Kumanovo, Kicevo and Struga developed.

Outcome 3 (Society):

- In order to create a network of dispute resolution practitioners, representatives of civil society organizations and community leaders were trained in dispute resolution methodologies. These participants will become part of a cadre of dispute resolution practitioners connected to a larger national pool of facilitation experts.

- The UNESCO Chair in Media, Dialogue and Mutual Understanding was established at the School of Journalism and Public Relations.

- “The Role of Higher Education in Fostering Inter-cultural Dialogue and Understanding in a Multiethnic Society” Conference gathered academics and students from most higher education institutions in the country to reflect on their work in this field and begin to chart a path ahead.

- Capacity building project grants implemented by UNESCO Clubs for enhancing interethnic dialogue in universities and the three pilot municipalities focusing on themes such as culture, environment and technology.

- “Diversity Reporting” handbook was produced and printed, which offers guidelines and recommendations to journalists on the ways in which the media can better reflect the diversity in their newsrooms and through the daily journalistic work.

OUTCOME 1 - Governance: By 2012, key national and local institutions dealing with inter-ethnic relations build inter-ethnic consensus more effectively

OUTPUT 1.1 - Key national and local institutions in 3 micro-regions dealing with inter-ethnic relations now have a system to address issues that may weaken inter-ethnic cohesion

The key national and local institutions dealing with inter-ethnic relations achieved significant progress towards more effective inter-ethnic consensus building. 29% percent of the recommendations deriving from the participatory assessment produced in 2010, were addressed by Government and civil society organizations, strengthening inter-ethnic dialogue, collaboration and coordination.

At the national level, the Secretariat for Implementation of the Ohrid Framework Agreement was supported to implement a grant scheme to enhance the role of civil society in the area of inter-ethnic relations.

At the local level, the role of the Commissions for Inter-Community Relations (CICRs) has been significantly strengthened for decision-making processes in the three focus municipalities, turning the CICRs into a mechanism for efficient facilitation of dialogue between the communities and the local self-Governments. For example, the CICR in Kumanovo, submitted a proposal to the Municipal Council for the improvement of the conditions for children in the municipalities’ multi-ethnic secondary schools, and the CICR in Struga submitted a proposal to the Council to encourage all political parties “to stay away from schoolyards”, particularly during  election periods.

All of these changes directly resulted from the capacity development activities implemented in the period January-April 2011. The seven workshops held throughout this period, enabled more than 150 representatives from the Secretariat for Implementation of the Ohrid Framework Agreement, the Agency for Minority Rights Realization, the Ministry of Local Self-Government, the Ombudsman, the local authorities, the CICRs, CSOs, neighbourhood unit leaders and the media to enhance their leadership skills and to strengthen multi-level coordination and cooperation. Additionally, the cooperation between the CICRs and the municipal council members has been further strengthened, ensuring that all information on inter-ethnic issues coming from the CICRs, such as religious holidays and cultural issues are discussed during the council sessions. For example, the Municipal Council of the Kumanovo Municipality established a practice of consultation and takes into consideration the CICR’s opinion on inter-ethnic relations, prior to proceeding with sessions. Furthermore, the Annual Work-Plan of the CICR, adopted by the Municipal Council, is officially reflected in the Annual Budget of the Municipality as of this year.

More than 13 Monitoring and Evaluation Officers from national and local institutions attended a monitoring and evaluation workshop at the end of February 2011, which aimed to further strengthen their capacities in information and data collection, monitoring, implementation and measuring of inter-ethnic relations’ progress indicators. As a result, an M&E methodology has been produced.  It will be operated through the Support Unit, via the Pool of Facilitation Experts, to measure the progress of inter-ethnic relations. Also, a Training Curriculum on dispute resolution, facilitation and mediation techniques is now available to the Support Unit as a valuable tool for implementing future mediation and facilitation training courses.  A “How-to-Guide” handbook on mediation was compiled with technical assistance from the UN Programme Team. It includes best practices and experiences from around the word, serving as a useful reference for all newly trained practitioners and public officials.

Three workshops were held for more than 60 national and local counterparts to raise their knowledge of the legal and institutional environment for inter-ethnic relations (including human rights instruments). The workshops also provided the participants with skills and tools to further enhance the systems aimed to enhance inter-ethnic relations. At an individual level, the participants gained a better understanding of the human rights dimensions of inter-ethnic confidence and diversity management. At an organizational level, the participants gained a better understanding of the human rights environment in which they work and the roles on how they should be positioning themselves in line with their various mandates. For example, the local Ombudsman offices pledged to increase their involvement in the work of the local municipalities with regards to minority rights and inter-ethnic relations. This implies working more closely with the Commissions for Inter-Community Relations, which is in line with the recommendations from the Participatory Assessment. In addition, the CICR pledged to apply human rights principles to their work, particularly the rights of the smaller communities, in close collaboration with civil society organizations. The workshops were organized in collaboration with the UN Human Rights Advisor and the national Helsinki Committee for Human Rights.

OUTPUT 1.2 - Key national and local institutions dealing with inter-ethnic relations have access to a pool of facilitation experts and resources

In line with the strategy for the advancement of a comprehensive (alternative) dispute resolution system, centered on facilitation and mediation, UNDP worked on further strengthening national mediative capacities. Activities included: the establishment of a Support Unit based at the Institute for Social Political and Juridical Research; linking of experts from the Chamber of Mediators’ existing database with informal communities (also known as neighbourhood communities) and community leaders.

OUTPUT 1.3 - Local governments and community organizations have better opportunities to collaborate in 3 micro-regions

Inter-Municipal Cooperation agreements were signed in three micro regions. The agreements served to further improve inter-ethnic relations, by addressing local needs among the ethnically diverse municipalities. A technical workshop was held for all three micro-regions during which provisions were proposed for enhancing inter-ethnic dialogue via the establishment of inter-municipal cooperation. Working groups were established in six municipalities (Kumanovo, Staro Nagoricane, Kicevo, Oslomej, Struga and Vevcani) and the first activities were implemented.

In order to strengthen the role of civil society in the area of inter-ethnic relations and community dialogue, UNDP and the Secretariat for the Implementation of the Ohrid Framework Agreement designed and implemented a Grant Scheme (small grants programme). The Grant Scheme paved the way for the successful implementation of several quick impact projects that enhanced inter-ethnic community dialogue and collaboration. It fully addressed the recommendations generated in the Assessment Report for strengthening dispute resolution and inter-ethnic collaboration. In total, 11 civil society organizations were selected to implement activities in the three municipalities. Activities focused on strengthening the capacities of the Commissions for Inter-Community Relations, improving the co-ordination and co-operation with Municipal Councils, bridging and enhancing dialogue between religious leaders and neighbourhood units, the youth, majority and non-majority groups.

Within the scope of these grants, local self-Government, civil society and CICRs jointly addressed the recommendations from the Participatory Assessment, to strengthen the collaboration between the different sectors in multi-ethnic communities. A total of 144 activities were implemented. For example, for the first time in Kumanovo, the Municipal Council, the CICR and the civil society organizations organized together a series of activities to enhance and promote the values of a multicultural society. This was done during the “Week of Active Citizenship”, which included visits to religious buildings, poetry readings in six languages, training on ‘how-to-find a job’, and a conference titled “Multiethnic Triangle”, which aimed at strengthening the links between the local self-government, civil society and the schools in the area of inter-ethnic collaboration. Another significant achievement is that again, for the first time in Kumanovo, the civil society and the Municipal Council developed a joint concept on the mandate and the role of the Committee on Interethnic Community Relations and agreed an annual work plan. The activities foreseen in the work plan are funded from the Municipal budget. Some of the activities include observing celebration days of the smaller communities; Serbian holiday St. Sava, the Roma holiday Gjurgovden, Vasilica and the Day of the Vlachs. The Commission also launched its own website, www.komzku.mk.

“The 2011 Action Plan is a big success for the Commission. We have already implemented many activities that promote the multicultural spirit of Kumanovo” Mr. Bogdan Tanevski, President of the Commission for Inter-Community Relations.

Another success story came from the Kicevo micro-region.  Through the establishment of the three support centres for neighbourhood units in the three municipalities (Kicevo, Zajaz and Drugovo), the coordination and collaboration between the local self-government and the neighbourhood units were enhanced. This has had a three-fold effect: 1) capacity development of the neighbourhood units; 2) addressing the needs of citizens and offering equal opportunities to services regardless of ethnic or other belonging, and 3) creating networks among neighbourhood units for the building of stronger inter-ethnic cohesion.

The Programme also developed the capacities of the CSOs from the three micro-regions in Project Cycle Management, enabling them to better articulate their ideas for activities that could further strengthen and sustain the coordination and collaboration with local self-governments. A Gender and Local Development Forum at municipal-level enabled more than 35 representatives (men and women) from the local self-government units, civil society, the Commissions for Inter-Community Relations and the Commissions for Equal Opportunities to discuss citizens, and particularly women’s civic engagement in local development policies and budgets.

Examples from all over the world were used along with best practices of using Gender Responsive Budgeting (GRB) as a tool. For this purpose, representatives of two local self- government units from Bitola and Elbasan (Albania) were invited to share experiences on GRB. This was also supported by UN Women in the South Eastern European region. As a result, the participants developed tailored actions, identifying five local priorities for each of their municipalities, and finalized the development of an action plan for one priority, including a budget plan reflecting beneficiary groups divided by ethnic belonging and gender. The participants were encouraged to organize a public hearing for the citizens of Struga, Kicevo and Kumanovo, to present the policy options and the planned budget.

“This was a very useful and rich forum. We had two organisations contributing to its preparation, two trainers, five presenters and many experiences to share from two countries. I have learned many things in only two days and when I arrived home, I knew that this was the beginning of a great new initiative” Quote from a participant (taken from the evaluation form).

OUTCOME 2 - Education: By 2012, The Capacity of the National Education System to Promote and Enhance Ethnic and Cultural Diversity Strengthened.

Output 2.1 - Understanding, tolerance and respect for ethnic and cultural diversity incorporated in the national education policy and curricula, and enforced in schools

During the reporting period UNICEF supported the Ministry of Education and Science and related institutions in strengthening their capacities for ensuring diversity and respect for multiculturalism in all segments of the education system. This includes incorporating contents related to understanding, tolerance and respect for ethnic and cultural diversity in the secondary education curricula through the Life skills based education (LSBE) subject. The LSBE has been introduced in the primary education curricula in 2008 and following its success a first draft curricula for the secondary education has been produced under this program. The curricula will officially be used in the secondary education as of school year 2011/12.

Training of additional primary education teachers from all primary schools in the country on LSBE was also conducted

UNICEF supported the Bureau for Educational Development (BED) to develop the Concept for textbook development and methodology for textbooks review to ensure respect for the ethnical, religious and gender diversity.  The next step is to train authors in using the methodology in developing textbooks.

As part of the program, the BED developed and launched digital educational contents for the following subjects: Macedonian language, Albanian language, Macedonian language for students of the other communities, Albanian language as an elective subject, history, music education, art education and civic education. The aim of these digital contents is to promote multiculturalism and inter-ethnic relations in education.

A teacher conference on multiculturalism, during which school principals and teachers, representatives of the Ministry and related institutions participated was organized in January 2011. The Manual for Multicultural Workshops for Primary and Secondary Schools in Macedonian, Albanian, Turkish and English languages was presented and launched at the event. The Manual consists of summarized workshops which were developed and piloted in seven elementary and five secondary schools and in total 1,000 children, teachers and parents have participated. The implemented workshops triggered great interest and participation among students and teachers.  The main purpose of the workshops is to encourage communication, respect and cooperation among children, and to offer a model for multicultural extracurricular activities that could be scaled up to all schools in the country.

During the reporting months, the expert team from the Queen’s University from Belfast, Northern Ireland conducted in-country assessment mission in February 2011 for the purpose of developing a country specific capacity development program. The team assessed training needs as a basis for developing a programme for training that will be implemented in 2011. The Queen’s University experts used this opportunity to meet with representatives from the Ministry of Education and Science, the municipalities, the schools and the national working Group in the Ministry established for this purpose.

During the second visit of the research team from the Queen’s University from Belfast in May 2011, the process for developing action plans for the implementation of the Nationals Strategy on Integrated Education with a focus on joint activities began with national and municipal policy makers. This is a direct contribution to the implementation of the strategy for integrated education adopted by the Government in 2010.

Three planning workshops at municipal level (Kicevo, Struga and Kumanovo) with an aim to develop a strategy and action plan for implementation of extracurricular activities that promote multiculturalism were organized in June and July 2011. The events were organized in light of decreasing number of schools with children from different ethnic groups and lack of opportunities for organizing joint activities within schools. The local plans include options and scenarios for inter-school cooperation. They are aligned to the specific situation at municipal level and as such will ensure scaling up and sustainability at municipal level. Participants included: members of municipalities, schools, local NGOs but also BED representatives, members of the Commission for inter-ethnic relations, members of the Education commission and the State Education Inspectorate.

Output 2.2 - Existing mechanisms for democratic participation, good governance and conflict resolution at all levels of the education sector strengthened in 3 selected micro-regions

During the reporting period, students, teachers and parents from selected schools in the target municipalities participated in on-going workshops during which approaches to multiculturalism were explored. Over 100 teachers and parents and 550 students were trained to integrate democratic participation in the school decision-making processes and in the election of school and student boards. This is part of the ‘Democratic Schools’ approach, which aims to ensure that school governance mechanisms (school boards, student and parent councils, student organizations and other school bodies) are transparent and based on democratic principles.

Output 2.3 - Opportunities for interaction and dialogue created for children and youth in school and the community

Two new Youth Centres were officially opened in municipal premises in Struga and Kicevo. In order to respond to the increase in demand for multicultural extra-curricular activities offered by the Center the due to the popularity that these Youth Centers have gained over the past year, both, the Municipality of Kicevo and Municipality of Struga have made a commitment to provide the premises free of charge for the next five years. In addition, due to increased interest of the youth from Kumanovo for these joint activities, a second Multi Kulti Youth Center opened in June 2011.

Over 1,500 children and young people from Kicevo, Struga and Kumanovo have actively participated in extra-curricular programmes organized in the multicultural Youth Centers. During the reporting period new groups were formed. The Youth Centres in the three targeted Municipalities offer children and young people from ethnically mixed communities’ greater opportunities to socialize and to get to know peers from outside their own ethnic groups. In addition, these activities promote positive alternatives for children, and contribute to breaking down barriers between communities and reducing stereotypes.

The school based activities, supported by UNICEF, actively continued providing extracurricular activities for ethnically mixed groups. The extracurricular activities piloted in the workshops held in the 7 primary and 5 secondary selected schools were developed to contribute towards the national education programme and Manual for multicultural workshops.

In addition, the implementing partners developed and launched a strategy for extending the activities on municipal level, involving students and youth from other schools within the municipalities.

The Philosophical faculty at the University Sts. Cyril and Methodius submitted an application for a UNESCO Chair in Intercultural Studies and Research. The application is under review at UNESCO HQ.

The Chair Candidate and the UNESCO Venice Office (Project Office in Skopje) in cooperation with the Office of the OSCE High Commissioner on National Minorities organized International Conference on “The Role of Higher Education in Fostering Inter-cultural Dialogue and Understanding in a Multiethnic Society” from 16-17 March 2011 in the premises of UKIM in Skopje. The conference brought together higher education leaders, scholars and students to discuss how higher education today contributes or could contribute to creating a culture of dialogue at the institutional, local, regional and international levels.  It was attended by over 200 national and international delegates including government representatives, academics, experts, diplomats, NGOs, students, media and civil society.

Starting in April, 11 UNESCO Clubs around the country implemented project activities for enhancing interethnic dialogue in universities and the three pilot municipalities focusing on themes such as culture, environment and technology. Festivals, debates, round tables, workshops and discussions were held with over 500 participants.

UNESCO approved the application for UNESCO Chair on Media, Dialogue and Mutual Understanding to be established within the School of Journalism and Public Relations.

OUTCOME 3 - Society: By 2012, media, local and religious leaders and civil society organizations promote and practice a greater level of cultural sensitivity and civic awareness

OUTPUT 3.1 - Local and religious leaders and civil society are better able to participate in dispute resolution processes

As a result of the capacity development activities, community leaders from across the three municipalities, representing youth, religious, social and political communities were mobilized to promote and practice a greater level of cultural sensitivity and civic awareness. For example, in the municipality of Struga, for the first time after many years, the value of inter-religious dialogue was promoted and discussed in a wider public setting, involving leaders from different religions, local authorities, representatives of CICRs and civil society. This event was also broadcast on national and local TV stations, as a good example of inter-religious dialogue. A photo contest and an exhibition titled “Unity in Diversity” and the promotion of four multi-ethnic songs during the “Diversity Week” in Struga and Kumanovo advanced the values of cultural diversity.

“This Programme initiated changes on individual and community level. I believe that the individual knowledge, skills and attitudes will now be replicated on a community level.” Youth activist from Kumanovo

The level inter-ethnic and inter-cultural sensitivity among community leaders and citizens was successfully increased through the involvement of more than 3,000 participants from different ethnic, age, gender and other groups. Community participation was achieved through capacity development activities, the Grant Scheme and local development activities utilizing inter-municipal cooperation as a successful approach.

“Through the Programme, the citizens of Struga from different ethnic backgrounds were brought together. I am proud that they are now focused on how to contribute to the well-being of the Municipality of Struga.” Ramiz Merko, the Mayor of Struga

A more thorough monitoring of the implementation of the strategy for equal representation of the non-majority communities was conducted in order to help expand the role of civil society when it comes to improving inter-ethnic dialogue. In Kumanovo, the work of seven institutions was monitored and recommendations for their further improvement were then shared with the local self-government. Also, the work of the CICRs has been closely monitored by civil society organizations in all three municipalities.

In order to create a network of dispute resolution practitioners, representatives of civil society organizations and community leaders were trained in dispute resolution methodologies. They were taught how to exercise their role as community mobilizers, who can prevent conflicts by relying on tools and expert guidance in their practice as future mediators. The legal, strategic and institutional background of civic engagement and potential formats for citizen participation on problem solving and decision making were introduced in the period of January to March 2011. This was followed by negotiation techniques and steps, factors and phases needed for dispute prevention as well as models for improving communication skills.  These participants will become part of a cadre of dispute resolution practitioners connected to a larger national pool of facilitation experts.

“As a result of this Programme, the civil society in Kumanovo took an active role in identifying problems and designing solutions for positive social change.” A leader of a Civil Society Organization in Kumanovo

A handbook on “Diversity Reporting” was produced and printed in March 2011. The Toolkit offers guidelines and recommendations to journalists on the ways in which the media can better reflect diversity in their newsrooms and through daily journalistic work.  It covers the following topics:

- What is Diversity?

- Basic recommendations for the media to promote diversity in society

- Recommendations for initiation and maintenance of the concept of diversity in editor’s office

- Recommendations for the reporting on ethnic differences

- Recommendations for reporting on religious differences

- Recommendations on reporting related to gender issues

- Recommendations for reporting on sexual minorities

- Recommendations for reporting on persons  with special needs

- Recommendations for reporting on older persons

- Recommendations on reporting on refugees and internally displaced persons

- Recommendations for reporting on different races

- The concept of peace journalism

- Code of Journalists in the country.

The Handbook is intended for journalists, students, educators and activists in the field of diversity, as well as editors and executives of the media. It was published in a Macedonian, Albanian and English language version, (200 copies were printed in Macedonian and 50 copies in Albanian (50 pages volume)). The English version of the Toolkit is already uploaded on the web page of the School of Journalism and Public Relations and it will also be available at the web-portal that is currently under construction, as part of the Rapid Response Media Mechanism Project supported by this programme.

A journalist training/workshop titled “Principles of Diversity Reporting” was organized in March.  The principles of professional, inclusive, sensitive and accountable media reporting that contributes to dialogue and a better understanding of diversity was one of the main topics of the workshop. It was organized in partnership with the Association of Journalists. Two dozen journalists from national and local media from across the country attended the workshop. The participants at the workshop agreed that the media should serve as a public forum for advocacy and affirmation of a wide spectrum of diversities in the country, stressing that education for intercultural communication is crucial for journalists to report more on, while respecting professional principles. The general principles and practices in diversity reporting, as well as examples though which the awareness and knowledge in diversity reporting could be noticed were also introduced at the workshop. Participants also asked for additional initiatives for discussing issues related to diversity reporting and intercultural communication in the country.

The Handbook on Diversity Reporting was also promoted and shared with journalists/editors who participated at the workshop. It was also promoted in an interview with the Macedonian National Radio and Alfa TV. Additional arrangements are being made to promote the project to the media, thus providing its active use by journalists when reporting on diversity.

The new UNESCO Chair on Media, dialogue and Mutual Understanding was approved by UNESCO. The main priority of the UNESCO Chair will be to strengthen the component of inter-cultural communication in the postgraduate studies in Journalism and Communication. A range of courses will be introduced to furnish future students and active journalists with: knowledge and understanding of the concepts of multi- and inter-culturalism, competence for critical analysis of multicultural situations as well as with skills for preventing, mediating and resolving conflicts arising from multicultural situations. A new Web platform will be also developed to provide an online educational pool for active journalists related to intercultural communication, diversity reporting and peace journalism. A team composed of students and senior journalists will be engaged in different types of media productions (TV/radio shows/documentaries) focused on relevant topics of mutual interest related to the need for better understanding of ethnic, religious, cultural and other differences among communities. In addition, a four-year research project will be conducted to assess the level of media pluralism in the country with a specific focus on cultural and geographic aspects of media pluralism.

On June 28th, 2011, the UNESCO Chair held a Conference titled "Journalism Education, Professional Values and cultural Diversity" which was opened by the Minister of Education and Science and the Minister of Culture and brought academics and journalists together to discuss topics related to inclusive journalism practices. During this period a 2 day workshop was held with local and international partners on the development of a new set of specialization graduate degree programs for journalism and communications students with a special focus on intercultural communication and inclusive journalism, as separate subjects as well as infused in all other subjects in the program.

Output 3.3 - Rapid Response Media Mechanism to reduce social tensions created

Towards the development of the Rapid Response Media Mechanism, a number of activities were undertaken by the School of Journalism and Public Relations and its partners:

1) Analysis of media reporting on intercultural issues: The School of Journalism and Public Relations (SJPR) selected a team of experienced researchers to conduct the analysis. The research team have developed the methodology for the analysis, collected research data and relevant literature and other documents related to the research topic.  The Research team adopted the Concept for conducting the analysis with defined research questions, methodology, timetable, list of interviewees, relevant references and other necessary information.

2) Comparative Analysis: The SJPR selected a team of researchers to conduct the comparative analysis. The research team collected and analyzed a range of online resources including the one developed by the UN Alliance of Civilizations. During April, the collected data and information was summarized in a separate report which contains conclusions and recommendations for the development of a similar mechanism for the country. The first draft of the Report was completed and the report will be published by the end of July.

3) Expert team: The Working Group of experts from partnering institutions has been composed in order to coordinate further activities aimed at establishing RRMM. A list of domestic experts to be involved in the RRMM has been drafted.

END

# Footnotes

Committed here follows the instructions given for the Results Framework and refers to committed plus disbursed.

Ministry of Local Self-Government, Secretariat for the Implementation of Ohrid Framework Agreement, Agency for Realization of the Minority Rights, Association for Local Self-Government Units (ZELS), National Committee for Interethnic Community Relations

Not Established yet

attend planning meeting or submit official written opinion

Not established yet

training curricula developed: 1 point, 6 training sessions delivered for 60 participants: 1 point, How-To Guide produced: 1 point

methodology for monitoring and evaluating drafted: 1 point, M&E officers trained in methodology: 1 point, M&E officers produce first monitoring report: 1 point

institution that manages pool contracted: 1 point, experts in pool trained: 1 point, awareness campaign completed: 1 point

Not established yet

for all 13 grades in primary and secondary education

training curricula developed: 1 point, 1000 participants trained: 1 point

school boards, school communities, parents councils, students organizations

established: 1 point; needs assessment report with recommendations published: 1 point, at least 5 studies published: 1 point, recommendations published from conference on the role of higher education and the strategy for integrated education: 1 point, curriculum developed for inter-cultural communication and conflict resolution developed: 1 point

Value orientation towards content articles/publication analyzed subjects: positive where the  content is affirmative in relation to developing a culture of dialogue between different nations, religions and cultures within Macedonia, respect for diversity and otherness and respect for human rights and equality, or triggering events, which represent a concrete realization the above values; neutral are usually related to the conference and presentation of research, which in itself, as an initiative, deserve a positive assessment, but it is always followed by the presentation of negative information about a given topic due to what are ultimately rated neutral (contents simultaneously have positive and negative elements) and negatively evaluated articles/publication which presents examples of discrimination, disregard for human rights, ethnic exclusion and other phenomena that prevent the construction of Macedonia as a tolerant and intercultural society.

conferences, forums, round tables, community events, knowledge cafes

curriculum developed: 1, all planned resources developed: 1, programme accredited: 1 point

Not launched yet

contract signed with School of Journalism: 1 point, structure of MRRM designed: 1 point, quarterly media monitoring reports started: 1 point, panel of experts established: 1 point, website online: 1 point

# Text boxes

- National capacities to prevent, reduce, mitigate and cope with the impact of violent conflict strengthened

- National capacities to prevent, reduce, mitigate and cope with the impact of violent conflict strengthened

- Capacity to prevent, reduce, mitigate and cope with the impact of violent conflict strengthened

- Impact of violent conflict reduced and/or  mitigated