**Namibia**

|  |  |
| --- | --- |
| **Programme Title:** | Sustainable Cultural Tourism in Namibia |
| **Programme number & MDTF ref:** | MDGF-1799-G-NAM (67181) |
| **Window:** | Culture & Development |
| **Approved Budget by NSC (US$):** | 6 million |
| **Participating Organizations:** | UNHABITAT, UNESCO, ILO, UNEP |
| **First Tranche transferred on:** | 19-Feb-2009 |
| **Second Tranche transferred on:** | 22-Apr-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Local economic development activities aimed at empowering communities completed. Environmental impact assessment completed. Baseline data available for all pilot sites. Training provided in tangible cultural heritage documentation, intellectual property rights, digital cataloguing of cultural heritage, land use, and heritage policies. 9 regional community management committees operational. Draft manuals on cultural and natural heritage assets developed. Guidelines for training tour guides and land use planning developed. |
|  |
| **Problems and lessons learned:** |
| JP design (current M&E tools do not allow for capturing gender disaggregated information). Managerial (difficulty in setting up multi-partner agreements). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

