**Nicaragua**

|  |  |
| --- | --- |
| **Programme Title:** | Local and regional environmental management for the management of natural resources and provision of environmental services |
| **Programme number & MDTF ref:** | MDGF-1751-E-NIC Env Climate (67171) |
| **Window:** | Environment & Climate Change |
| **Approved Budget by NSC (US$):** | 4.5 million |
| **Participating Organizations:** | UNESCO, WFP, UNICEF, UNEP, UNDP, PAHO/WHO, UNIDO |
| **First Tranche transferred on:** | 18-Aug-2008 |
| **Second Tranche transferred on:** | 14-Jan-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| 60% of the population of 15 communities receiving energy from renewable sources. 65 mz. of agroforestry/cocoa mixed production benefitting 107 families. Training on cocoa production given to local producers and to agricultural extension workers. New warehousing facility for cocoa in Kukalaya now operational. 35 new hectares of land set aside for cocoa tree nurseries. 15 Local Water and Sanitation Committees have been organized and strengthened and4071 people have been benefitted with water and sanitation infrastructure (1875 men and 2196 women).  |
|  |
| **Problems and lessons learned:** |
| JP design (requires frequent adjustments). External to the JP (social strife causing strikes, road closures etc.). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** No |

CHARTS& FIGURES

As of 31 December 2010

