DATE: 2 August 2010

Award ID: 58607

Description: (PBF/EMER/13) Police and Public Security Reform in the Puntland State of Somalia (US$ 1.000.000)

Implementing Partner: PL Legal Aid Clinic, PSU, WAWA, Puntland Police

Period Covered: 1 January – 31 July 2010

Subject:

Q2 Report and Request for No-Cost Extension

Request for no cost extension PBF for the period of three (3) months, from 31 December 2010 until 31 March 2011.

Introduction:

The implementation of the Police And Public Security Reform in the Puntland State of Somalia is currently ongoing. In communication with the PB-office in NY (Mrs. Bertha Orema) it has been clarified that the end date of the project is 31 December 2010, instead of 16 November 2010 (one year after signature of the proposal).

The activities of Outputs 1, 2 and 4 are being designed, planned and implemented as foreseen (see Q2 report). Due to unforeseen developments the Civilian Police Project requests a no-cost extension for the period of three months.

Output 3:

Regarding the activities as described under Output 3, the prospect of successfully implementing activity 2 (the Puntland Police Reform Convention) in September 2010, has been put under severe pressure. The Puntland Government has communicated, in the person of the President that it is unwilling to engage with certain key non-governmental organizations until further notice.  This decision follows the suspension of a three day workshop on the rule of law which contained criticism of some aspects of the Puntland Government and its policies. This stance has created uncertainties regarding co-operation with the international community, especially where planned activity made use of such partners and this is currently impacting programming. The Civilian Police project had planned integral participation of CSO’s in the Puntland Police Improvement Convention and proposes, in the circumstances, to postpone this critical activity to Q4, with the effect that activity 5 (consultations of communities through so-called road-shows) will have to take place in Q1 of 2011.

Output 5:

Due to deterioration of the security situation in the area South of Bossaso, where government forces have engaged in military operations against insurgents and anti-government elements aligned with Al-Shabaab, the implementation of Activity 4 under Output 5 has become constrained. On 26 July 2010, the Police Commissioner of the Puntland Police Force has indicated that Armo Police Academy would not be a feasible location for training due to the insecurity of area. Armo Academy is located 100 kilometers south of Bossaso and lies on the edge of the area of operation of the insurgents. The Police Commissioner also indicated that it would be impossible due to the operational demands of the police, to release police officers for the Competency Assessment/Human Rights Training as planned (from 1 September 2010 onwards).

The Civilian Police project will seek to clarify the intent of the police commissioner and will redesign the activity, based on a smaller number of officers (250 per training) and with a postponement of the date of implementation from 1 September 2010 to 1 October 2010. If the Police Commissioner cannot guarantee the parameters for implementation of the activity, the Civilian Police project needs to redesign the activity and relocate implementation to areas unaffected by the conflict. This may mean that the activity cannot be finalized before the expiry of the project.

Therefore, the project requests a no-cost extension for the period of three months.

Nairobi, 2 August 2010

Timothy der Weduwen

Project manager

UPDATE 2 August

# Project Quarterly Report UNDP ROLS Civilian Police ‘Peace Building Fund’

| DATE: 2 August 2010 Award ID: 58607 Description: (PBF/EMER/13) Police and Public Security Reform in the Puntland State of Somalia (US$ 1.000.000) Implementing Partner: PL Legal Aid Clinic, PSU, WAWA, Puntland Police Period Covered: 1 January – 31 July 2010 1. Project Issues: |
| --- |
| Status of Project Risks: Security Risk has changed regarding the availability of Armo Police Training Academy due to conlicts in the area South of Bossaso. Polirical risk has changed due to changed stance of government regarding the participation of key NGO’s in peace-building activities. | Open Project Issues: Major Implementation projected for Q3/4, no cost extension requested for Q1 2011 |
| 2. Project Performance |
| OUTPUT 1: Attacks on International workers decreased Project ID: 60247 Description: To support professionalization of SPU officers, as such to deter attacks on international workers (EC/UNCT funded); Target: Refresher training conducted for 270 Puntland Police Special Protection Unit officers Achievement: N/A |
| Activity ID: N/A Deliverable Description: Training concluded, certified officers; Start and End Date: 1 May 2010 – 31 December 2010 % Progress to date: Activity 1: 31% |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Training conducted on basis of international standards including Human Rights and international monitoring; | 02-06-10 | Positive | Good | On track |
| Financial |
| Account | Fund | Donor | R. Party | Budget | Expenditure | Balance |
| 58607 | 33009 | 00280 | UNDP/CP | 30,000 | 10,000 | 20,000 |
| OUTPUT 2: Number of Victims of SGBV, armed conflict and armed robbery decreased Project ID: 60247 Description: Training and Capacity Building Target: Baseline survey conducted on Police Occurrence Book entries in Galkayo, Garowe, Qardho and Bossaso; Baseline victimization surveys conducted in Galkayo, Garowe, Qardho and Bossaso; Comparative analysis of observed violence conducted by Observatory for Violence; 500 firearms seized; 300 pirates arrested and referred to court of justice; 50 Police Officers trained in SGBV procedures, curriculum developed; Achievement: N/A |
| Activity ID: 2 Training and Capacity Building Deliverable Description: Documented baseline surveys and analysis Start and End Date: 1 January – 31 December 2010 % Progress to date: Activity 1: 0% Q3 Activity 2: 25% Q3 Activity 3: 25% Q4 Activity 4: unknown Activity 5: unknown Activity 6: 0% Q4 |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Multi agency/NGO cooperation | 02-06-10 | Neg on Act 1 Pos on Act 2/3 | MCG’s to be signed in June | On track |
| Financial Summary |
| Account | Fund | Donor | R. Party | Budget | Expenditure | Balance |
| 58607 58607 58607 | 60247 00141 60247 60247 | 11363 32045 11363 11363 | PLLAC UNDP/AVR UNDP/AVR PLPF/UNODC PLFP UNDP/CP | Act 1: 20,000 Act 2: 100,000 Act 3: 30,000 Act 4: unknown Act 5: unknown Act 6: 10,000 | 0 25,000 0 N/A N/A 0 | 20,000 75,000 30,000 N/A N/A 10,000 |
| OUTPUT 3: Citizens perception of security and trust in the police forces improved Project ID: 60247 Description: Training and Capacity Building Target: 20 Communities reached with public relations campaign focusing on the role of the police in serving and protecting communities and vulnerable groups; 150 CSO and state actor representatives present, contributing and cooperating in Puntland Police Reform Convention; 2500 Police officers informed on outcomes Puntland Police Reform Convention; 20.000 PL citizens informed on outcomes Puntland Police Reform Convention by local media and UNDP communication efforts; 20 Communities participated in consultations on Police Reform (road-shows) Achievement: N/A |
| Activity ID: 2 Training and Capacity Building Deliverable Description: Puntland Police Reform Convention held; Start and End Date: 1 May 2010 – 31 March 2011 % Progress to date: Activity 1: 100% Activity 2: 0% Q4 Activity 3: 0% Q4 Activity 4: 0% Q4 Activity 5: 0% Q1 2011 ( Partners being identified) |
| Quality Criteria Date Results of Activities User Perspective Resource Status Timeliness Convention conducted on basis of international standards including Human Rights; 02-06-10 Positive Good On track |
| Financial |
| Account Fund Donor R. Party Budget Expenditure Balance 58607 60247 11363 KMC UNDP UNDP/CP UNDP/CP NGO Act 1: 75,000 Act 2: 100,000 Act 3: 5,000 Act 4: 1,000 Act 5: 120,000 75,000 0 0 0 0 0 100,000 5,000 1,000 120,000 |
| OUTPUT 4:The PL Police is held accountable by other criminal justice institutions, members of parliament and the public Project ID: 60247 Description: Training and Capacity Building Target: Parliamentary Police Oversight Commission trained and established; CID dossiers template aligned with prosecutors and court procedures/templates; Complete analysis of police formation, deployment and number of officers concluded; Complete assessment of police needs and resources conducted; Police statutes and law reform committee trained and established; Baseline study completed, indicating police complaints levels and content; Police complaint procedure designed; Achievement: N/A |
| Activity ID: 2 Training and Capacity Building Deliverable Description: Commission in place, template, reports, procedures Start and End Date: 1 May 2010 – 31 December 2010 % Progress to date: Activity 1: 0% Q4 Activity 2: 0% Q3 Activity 3: 100% Q1 Activity 4: 0% Q3 Activity 5: 0% Q3/4 Activity 6: 0% Q3/4 Activity 7: 0% Q4 |
| Quality Criteria Date Results of Activities User Perspective Resource Status Timeliness Training conducted on basis of international standards including Human Rights and international monitoring; 02-06-10 Positive Good On track |
| Account Fund Donor R. Party Budget Expenditure Balance 58607 60247 11363 UNDP/CP PLLAC UNDP/CP UNDP/CP UNDP/CP UNDP/CP UNDP/CP Act 1: 10,000 Act 2: 10,000 Act 3: 10,000 Act 4: 5,000 Act 5: 10,000 Act 6: 10,000 Act 7: 5,000 0 0 0 0 0 0 0 10,000 10,000 10,000 5,000 10,000 10,000 5,000 |
| OUTPUT 5: Police Officers provide a security service which is consistent with international standards Project ID: 60247 Description: Training and Capacity Building Target: 100 Police Recruits trained in Basic Policing functions; 20 Police Officers enrolled in Law Faculty Puntland State University (2 year Diploma Trajectory) 500 Police officers trained in literacy and numeracy, curriculum developed; 1000 Police officers trained in UN basic Police Standards and Human Rights, curriculum developed; 100 Police officers trained in Management and Supervision, curriculum developed; 50 Senior Police Officers trained in Police & Accountability, curriculum developed; 50 Police Officers trained in Basic Crime Investigations procedures, curriculum developed; 200 Police Officers trained in Management & Criminal Procedural Code, curriculum developed; Achievement: N/A |
| Activity ID: 2 Training and Capacity Building Deliverable Description: Training concluded, certified officers; Start and End Date: 1 February 2010 – 31 March 2011 % Progress to date: Activity 1: 75% Q2/3 Activity 2: 50% Q1/2/3/4 Activity 3: 0% Q3/4 Activity 4: 0% Q4/ Q1 2011 Activity 5: 0% Q3/Q4 Activity 6: 0% Q4 Activity 7: 0% Q4 Activity 8: 0% Q4 |
| Quality Criteria Date Results of Activities User Perspective Resource Status Timeliness Training conducted on basis of international standards including Human Rights and international monitoring; 02-06-10 Positive Good On track |
| Account Fund Donor R. Party Budget Expenditure Balance 58607 30000 60247 10480 11363 UNDP/CP PSU WAWA UNDP/CP UNDP/CP UNDP/CP UNDP/CP UNDP/CP Act 1: 60.000 Act 2: 31,000 Act 3: 40,000 Act 4: 200,000 Act 5: 10,000 Act 6: 35,000 Act 7: 20,000 Act 8: 10,000 40,000 15,500 0 0 0 0 0 0 20.000 15,500 60,000 150,000 25,000 35,000 30,000 20,000 |