DATE: 8 February 2011

Award ID: 58607

Description: Police and Public Security Reform in the Puntland State of Somalia (US$ 1.000.000)

Implementing Partner: PL Legal Aid Clinic, PSU, WAWA, Puntland Police

Period Covered: 1 October 2010 – 31 December 2010

Subject:

PEACEBUILDING FUND PROPOSAL FOR SOMALIAPOLICE AND PUBLIC SECURITY REFORM

Q4-2010 Report

Introduction:

The implementation of the Police And Public Security Reform in the Puntland State of Somalia is currently ongoing. In communication with the PB-office in NY (the project has received permission for a no-cost extension until 30 June 2011 (see previous report Q3-2010).

The activities of Outputs 1, 2 and 4 are being designed, planned and implemented as foreseen (see Q2 report), except activity 2 under Output 2.

Output 1:

The situation concerning the security of International Humanitarian and Development workers has stabilized over the last quarter. Complaints about the performance of the SPU have been countered by the project through increased training and effective data-registration of all SPU officers in Puntland. Efforts to streamline the oversight and performance evaluation functions of the international community are under way to be effectively in place on 1 March 2011. These efforts are supported by the UN, NGO Consortium and donor community.

Output 2:

All activities are ongoing. Activity 1 has been postponed due to lack of support from the new police commissioner. This has been resolved and the activity will start in Q1 2011.

Output 3:

Regarding the activities as described under Output 3, the prospect of successfully implementing activity 2 (the Puntland Police Reform Convention) in September 2010, has been put under severe pressure. The Puntland Government has communicated in June 2010, through the authority of the President that it was unwilling to engage with certain key non-governmental organizations until further notice.  This decision followed the suspension of a three day workshop on the rule of law which contained criticism of some aspects of the Puntland Government and its policies. This stance has created uncertainties regarding co-operation with the international community, especially where planned activity made use of such partners and this is currently impacting programming. The situation seems now more or less resolved through active mediation between the Puntland Government and the key NGO, supported by the international community. The Puntland Government has reacted positively to the concept of a Police Reform Seminar, and negotiations (November 2010) regarding a technical support package are under way. The Civilian Police project had planned integral participation of CSO’s in the Puntland Police Improvement Convention and proposes, under these circumstances, to postpone this critical activity to Q1-2011, with the effect that activity 5 (consultations of communities through so-called road-shows) will also have to take place in Q1 of 2011.

Output 4: Implementation foreseen for Q2-2011.

Output 5:

Due to deterioration of the security situation in the area South of Bossaso, where government forces have engaged in military operations against insurgents and anti-government elements aligned with Al-Shabaab, the implementation of Activity 4 under Output 5 has become constrained. On 26 July 2010, the Police Commissioner of the Puntland Police Force has indicated that Armo Police Academy would not be a feasible location for training due to the insecurity of area. Armo Academy is located 100 kilometres South of Bossaso and lies on the edge of the area of operation of the insurgents. The Police Commissioner also indicated that it would be impossible due to the operational demands of the police, to release police officers for the Competency Assessment/Human Rights Training as planned (from 1 September 2010 onwards). The Civilian Police project has sought to clarify the intent of the police commissioner and has redesigned the activity, based on a smaller number of officers (250 per training) and with a postponement of the date of implementation from 1 September 2010 to 1 November 2010. In Q4 it became clear that the rehabilitation of critical infrastructure of Armo Academy (damaged in a storm) was not completed. Also, deficiencies in the general sanitation system were addressed. The Police Commissioner declared Armo safe and secure on October 1st 2010, but withheld his approval for the start of the training activities, until all issues were resolved. Preparations for the Capacity Assessment Training, which entails vetting and registration of police officers, continues and is now planned to commence in March 2010. The activity will be finalized on 1 June 2011.

Activity 7 has been completed for 50% in November 2010, with the delivery of a 3 weeks CID training to 28 investigative police officers, including SGBV (rape case management). The UN Counter Piracy Trust Fund has granted the project further funds to train additional officers in 2011.

Nairobi, 8 February 2011

Timothy der Weduwen

Project manager

# 4th  Project Quarterly Report UNDP ROLS Civilian Police ‘Peace Building Fund’

| DATE: 8 February 2011 Award ID: 58607 Description: Police and Public Security Reform in the Puntland State of Somalia (US$ 1.000.000) Implementing Partner: PL Legal Aid Clinic, PSU, WAWA, Puntland Police Period Covered: 1 October-31 December 2010 1. Project Issues: |
| --- |
| Status of Project Risks: Risk status not changed | Open Project Issues: Major Implementation projected for Q3/4 |
| 2. Project Performance |
| OUTPUT 1: Attacks on International workers decreased Project ID: 60247 Description: To support professionalization of SPU officers, as such to deter attacks on international workers (EC/UNCT funded); Target: Refresher training conducted for 270 Puntland Police Special Protection Unit officers Achievement: 160 Officers trained, all 264 SPU officers registered; |
| Activity ID: N/A Deliverable Description: Training concluded, certified officers; Start and End Date: 1 May 2010 – 31 December 2010 % Progress to date: 50% Activity 1: 50% |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Training conducted on basis of international standards including Human Rights and international monitoring; | 02-06-10 | Positive | Good | On track |
| Financial |
| Account | Fund | Donor | R. Party | Budget | Expenditure | Balance |
| 58607 | 33009 | 00280 | UNDP/CP | 30,000 | 20,000 | 10,000 |
| OUTPUT 2: Number of Victims of SGBV, armed conflict and armed robbery decreased Project ID: 60247 Description: Training and Capacity Building Target: Baseline survey conducted on Police Occurrence Book entries in Galkayo, Garowe, Qardho and Bossaso; Baseline victimization surveys conducted in Galkayo, Garowe, Qardho and Bossaso; 500 firearms seized; 300 pirates arrested and referred to court of justice; 50 Police Officers trained in SGBV procedures, curriculum developed; Achievement: N/A |
| Activity ID: 2 Training and Capacity Building Deliverable Description: Documented baseline surveys and analysis Start and End Date: 1 January – 31 December 2010 % Progress to date: Activity 1: 0% Q1 2011 Activity 2: 100% Q3 Completed Activity 3: n/a Activity 4: n/a Q1-Q3 Benchmark Completed Activity 5: 50% Q4/Q1 2011 |
| Quality Criteria | Date | Results of Activities |
|  |  | User Perspective | Resource Status | Timeliness |
| Multi agency/NGO cooperation | 02-06-10 | Neg on Act 1 Pos on Act 2/3 | MCG’s to be signed in June | On track |
| Financial Summary |
| Account | Fund | Donor | R. Party | Budget | Expenditure | Balance |
| 58607 58607 | 60247 00141 60247 | 11363 32045 11363 | PLLAC UNDP/AVR PLPF/UNODC PLFP UNDP/CP | Act 1: 30,000 Act 2: 100,000 Act 3: unknown Act 4: unknown Act 5: 10,000 | 0 25,000 N/A N/A 10,000 | 30,000 00.000 N/A N/A 00.000 |

OUTPUT 3: Citizens perception of security and trust in the police forces improved Project ID: 60247 Description: Training and Capacity Building Target: 20 Communities reached with public relations campaign focussing on the role of the police in serving and protecting communities and vulnerable groups; 150 CSO and state actor representatives present, contributing and cooperating in Puntland Police Reform Convention; 2500 Police officers informed on outcomes Puntland Police Reform Convention; 20.000 PL citizens informed on outcomes Puntland Police Reform Convention by local media and UNDP communication efforts; Public consultation with civil society representatives; Achievement: N/A

Activity ID: 2 Training and Capacity Building Deliverable Description: Puntland Police Reform Convention held; Start and End Date: 1 May 2010 – 31 October 2010 % Progress to date: On Schedule / Act 3 Delayed Activity 1: 100% Activity 2: 0% Q1 2011 Activity 3: 0% Q1 2011

Quality Criteria Date Results of Activities User Perspective Resource Status Timeliness Convention conducted on basis of international standards including Human Rights; 02-06-10 Positive Good On track

Financial

Account Fund Donor R. Party Budget Expenditure Balance 58607 60247 11363 KMC UNDP UNDP/CP Act 1: 74,000 Act 2: 130,000 Act 3: 74,000 73,183.69 0 0 816.31 130,000 00.000

OUTPUT 4:The PL Police is held accountable by other criminal justice institutions, members of parliament and the public Project ID: 60247 Description: Training and Capacity Building Target: Parliamentary Police Oversight Commission trained and established; Complete analysis of police formation, deployment and number of officers concluded; (included in Output 5 under activity 8) Complete assessment of police needs and resources conducted (idem) Police statutes and law reform committee trained and established; (included in Output 3, activity 2) Baseline study completed, indicating police complaints levels and content; Police complaint procedure designed; Achievement: N/A

Activity ID: 2 Training and Capacity Building Deliverable Description: Commission in place, template, reports, procedures Start and End Date: 1 May 2010 – 31 December 2010 % Progress to date: Delayed Activity 1: 0% Q4 Activity 3: 100% Q1 Activity 4: 0% Q4 Activity 5: 0% Q4 Activity 6: 0% Q4 Activity 7: 0% Q4

Quality Criteria Date Results of Activities User Perspective Resource Status Timeliness Training conducted on basis of international standards including Human Rights and international monitoring; 02-06-10 Positive Good On track

Account Fund Donor R. Party Budget Expenditure Balance 58607 60247 11363 UNDP/CP UNDP/CP UNDP/CP UNDP/CP UNDP/CP Act 1: 35,000 Act 3: 0 Act 4: 0 Act 5: 10,000 Act 6: 5,000 0 0 0 0 0 0 35,000 00.000 00.000 10,000 5,000

OUTPUT 5: Police Officers provide a security service which is consistent with international standards Project ID: 60247 Description: Training and Capacity Building Target: 100 Police Recruits trained in Basic Policing functions; 20 Police Officers enrolled in Law Faculty Puntland State University (2 year Diploma Trajectory) 500 Police officers trained in literacy and numeracy, curriculum developed; 500 Police officers trained in UN basic Police Standards and Human Rights, curriculum developed; 100 Police officers trained in Management and Supervision, curriculum developed; 50 Senior Police Officers trained in Police & Accountability, curriculum developed; 50 Police Officers trained in Basic Crime Investigations procedures, curriculum developed; 1500 Police Officers undergoing Capacity Assessment Training CAT Achievement: N/A

Activity ID: 2 Training and Capacity Building Deliverable Description: Training concluded, certified officers; Start and End Date: 1 February 2010 – 31 December 2010 % Progress to date: On schedule Activity 1: 100% Q2/3 Activity 2: 100% Q1-2011 Activity 3: 0% Q4/ Q1 2011 Activity 4: 0% Q4/Q1 2011 Activity 5: 100% Q2/3/4 Activity 6: 0% Q4 (Activity Suspended) Activity 7: 50% Q4 Activity 8: 0% Q1 2011

Quality Criteria Date Results of Activities User Perspective Resource Status Timeliness Training conducted on basis of international standards including Human Rights and international monitoring; 02-06-10 Positive Good On track

Account Fund Donor R. Party Budget Expenditure Balance 58607 30000 60247 10480 11363 UNDP/CP PSU WAWA WAWA UNDP/CP UNDP/CP UNDP/CP UNDP/CP Act 1: 60.000 Act 2: 31,000 Act 3: 40,000 Act 4: 35,000 Act 5: 34,000 Act 6: 10,000 Act 7: 45,000 Act 8: 310,000 60,000 31,074.46 0 0 34,000 0 36.000 67,824.66 00.000 {74.46} 40,000 35,000 00.000 10,000 11,000 242,175