PEACEBUILDING FUND

Strengthening Public Defense

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2010

| Programme Title & Number |  | Country, Locality(s), Thematic Area(s) |
| --- | --- | --- |
| Programme Title: Strengthening Public Defense Programme Number PBF/LBR/E-4 (PP/R3/A1/01) MDTF Office Atlas Number:00070496 |  | Improve Access to Justice and Rule of Law Priority Area: 3.1, 3.2 |

| Participating Organization(s) |  | Implementing Partners |
| --- | --- | --- |
| .UNDP-Liberia UNMIL Legal and Judicial Systems Support Division, The Carter Center |  | The Supreme Court of Liberia, James A.A. Pierre Judicial Institute, UNMIL Legal and Judicial Systems Support Division, The Carter Center. |

| Programme/Project Cost (US$ 750,066.00 ) |  | Programme Duration (months) |
| --- | --- | --- |
| MDTF Fund Contribution: by Agency (if applicable) |  |  | Overall Duration 12 months |  |
| Agency Contribution Technical support |  |  | Start Date March 2009 |  |
| Government Contribution In Kind |  |  | End Date or Revised End Date, December 2010 (if applicable) |  |
| Other Contribution (donor) (if applicable) |  |  | Operational Closure December 31, 2010 |  |
| TOTAL:750,066.00 |  |  | July 31, 2011 |

| Programme Assessments/Mid-Term Evaluation |  | Submitted By |
| --- | --- | --- |
| Assessment Completed - if applicable please attach Yes X No Date: __________________ Mid-Evaluation Report – if applicable please attach Yes No Date: __________________ |  | Name: James Verdier Title: Programme Manager Email address:james.verdier@undp.org |

Table of Content

Cover page ---------------------------------------------------------------------------------1

Acronyms ------------------------------------------------------------------------------------3

Purpose ---------------------------------------------------------------------------------------4

Resources ------------------------------------------------------------------------------------4

# Implementation and Monitoring Arrangements---------------------------------------4

Results------------------------------------------------------------------------------------------6

Pictorial of training Session ---------------------------------------------------------------7

Acronyms

CSOs			Civil Society Organizations

GOL			Government of Liberia

JTI			Judiciary Training Institute

LJSSD 			Legal and Judicial Systems Support Division

MPEA			Ministry of Planning and Economic Affairs

POB			Peace Building Office

TCC			The Carter Center

UNDP			United Nations Development Programme

UNMIL			United Nations Mission in Liberia

UNPBF			United Nations Peace Building Fund

# Purpose

The purposes of the project were to increase citizens’ confidence in public defence system and  to seek and rely on trained and equipped public defenders to ensure their rights to due process thereby leading to a reduction in the ratio of prolong pre-trial detentions. Citizens’ rights to due process would be protected with greater appreciation for a functional, trained and equipped criminal justice system comprising strong and effective prosecution and public defenders. Citizens would develop confidence in the ability of the criminal justice system to fairly and impartially dispose of matters and its capacity to respect basic rights of persons accused of crimes.

# Resources

Financial Resources:

UNDP received $750,066.00 USD for the project implementation.  One budget revision was done  in May 2010 due to the delay in the release of the funding which resulted in the extension of the project original end date.

Human Resources:

- National Staff: The Programme was managed by three national staffs i.e two Programme Associates and one Programme Manager.

- International Staff:  There were two international staffs, a Rule of law Specialist and one Chief  Technical Advisor for Rule of Law.

# Implementation and Monitoring Arrangements

For effective monitoring, the project recruited a project coordinator who among other duties was responsible for coordinating and monitoring of public defenders. In addition, to making regular quarterly reports, the Public Defence Coordinator monitored the public defenders and reported to the Technical Advisory Team of the project comprising  the JTI and the UNDP.  The technical team also monitored and participated in the implementation of activities of the project. Trainings were jointly organized by the public defenders coordinator, the UNDP and the JTI.  In addition, quarterly Project board meetings were held and reports were produced which highlighted successes and challenges for submission to the PBO. At the quarterly Project Board meetings, implementing partners and stakeholders reviewed the progress and challenges and made recommendations on the way forward. These meetings added value and guidance to the successful  implementation f the project.

The UNDP procurement section followed the standard procurement guidelines in undertaking all procurement related activities including payment of vendors for workshops.

- Results:

Targets/outputs									Achievements

| Output 1: 1. Training Coordinator at JTI identified and recruited. 2. Design and development of comprehensive training program and curricula for public defenders and other judicial sector personnel. 3. Local Consultant recruited to advise and assist with development of training program and curricula recruited. 4. Initial comprehensive training program and manual drafted. 5. Detailed draft curricula and training program presented to The Board of JTI and Chief Justice | Training coordinator was recruited in collaboration with judiciary ; One national consultant was recruited to design and produce a training manual, which will be utilized for a more coordinated training activities ; One national local consultant recruited who validated the training curriculum with stake holders; The most outstanding achievement was a joint training conducted for Public Defenders and Judges. This training created an avenue for Judges and Public defenders to dialogue on mutual issues affecting both portfolios. The second was the development of a training curriculum by two national consultants. This curriculum is expected to be used for all future trainings thus presenting an opportunity for coordinated approach for public defenders’ trainings. Five trainings were conducted during the life cycle of the project. Four of these trainings addressed trial techniques which sharpened the skills of the defenders and the last session was a joint training for public defenders and judges. The process of producing a curricula is ongoing and would be available for review by the Board of the JTI at the end of March 2011; |
| --- | --- |
| output 2: 1. Office space identified/refurbished and/or equipped for 8 public defenders. 2. Public Defenders identified and/or appointed and Legal Assistants recruited by the Supreme Court. 3. Public Defenders training needs and gaps identified by the Public Defender Training Coordinator (PDTC) and other stakeholders in a one-day workshop. 4. Comprehensive training programme developed and approved by the Board of the JTI. 5. Periodic reports produced by the PDTC for submission to the Board of the JTI setting forth its activities, lessons learned, and next steps | Office space and accommodation for the eight public defenders was paid by the project, even though, it was difficult in some cases to find a suitable office space. Notwithstanding, some defenders secured work stations while others experienced difficulties. 14 pick-ups trucks were procured to enable the public defenders access rural communities; Training needs and gaps were identified by the Training Coordinator in collaboration with the James A. A. Pierre Judicial training institute; Eight defenders were successfully recruited and deployed in keeping with the project’s activities. However, the legal assistance could not be recruited and deployed due to budget constraints as a result of the underestimated cost; A training programme was developed by the JTI and the project coordinator. This programme was used through the life of the project for the various trainings conducted; A work plan outlining priority areas was shared with the technical team and endorsed for the trainings activities; Periodic reports were presented by the Public Defenders Coordinators which highlighted progress made by the Public Defender especially as it speaks to the reduction in the number of pre-trial detainees, |
| Output 3: 1. Public defender office staffs trained in the use of the electronic database for case management, reporting and tracking results of service delivery. 2. Policies and procedures developed on attendance and performance monitoring and evaluation submitted to the Supreme Court for approval. 3. Approved policies and procedures developed on performance monitoring and evaluation disseminated to all courts and public defenders. 4. Mechanism established for receiving and addressing complaints regarding public defenders and staffs. | The office staffs were not recruited as proposed in the project due to budget shortfalls, thus could not be trained in the electronic case management. However, these trainings were highlighted during trainings conducted for public defenders on how to manage case files especially through electronic means. The Office of the Public Defenders Training Coordinator under the Supreme Court of Liberia put in place a monitoring system which was used to track performances of Public Defenders; The Public Defender Coordinator also served as Monitor and provided oversight responsibility to ensure the quality of work produced by the public Defenders were good. As a result of this project’s intervention/support to the Public, there has been an increased confidence in their work due to the number of representation made on behalf of indigents. Citizens now have access to public defenders due to their availability. This is evident by the number of cases defended by the public Defenders in under privileged Counties like Lofa, Bong, Grand Gedeh, Grand Kru, River Gee, Maryland and other counties. There are total of 21 public Defenders assigned in the 15 Counties |

Some pictorial of the training sessions

14 pick-up trucks procured under the Peace Building Funded  “Strengthening Public Defense” Project

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Priority Area for the Peacebuilding Fund; Sector for the UNDG ITF.

The start date is the date of the first transfer of the funds from the MDTF Office as Administrative Agent. Transfer date is available on the MDTF Office GATEWAY (http://mdtf.undp.org).

# Text boxes

UNDP Rule of Law Manager addresses hand-over ceremony

Cllr.Fayia (MOJ) presenting at one of the sessions

Public Defenders in a training session

Chief Justice, Johnnie N Lewis receives keys to the vehicles

Public Defenders in a training session

Her Excellency graces vehicle hand -over ceremony