# Liberia Peace Building Fund

# QUARTERLY STATUS REPORT AS of July-September 2010

| Recipient UN Organization: | UNDP | PBF Priority Area: | 3: Strengthening State Capacity for Peace Consolidation |
| --- | --- | --- | --- |
| Implementing Partner(s): | The Judiciary, Republic of Liberia |
| Project Number: | PBF//R3/A3/09 (PBF/LBR/E-4) |
| Project Title: | “Strengthening Public Defense” |
| Total Approved Project Budget | $750,066 USD |
| Project Objective and Scope | Long term war and insecurity has led to the disintegration of the Liberian legal system. Efforts to rebuild the trust of the Liberian people are ongoing by ensuring the rights of suspects, detainees and accused can be respected and provided access and opportunity for free and fair trials. One key area however, has not been adequately addressed: the rights of prisoners and defendants in the legal system. Pre-trial detainees are languishing in jail as a result of poor case management procedures, lack of transportation, and lack of legal representation. It is the responsibility of the Public Defenders’ Office to represent indigents, yet the office is poorly equipped to do so. The Public Defenders’ Office lacks both the logistical support and proper capacity to provide services so desperately needed by unrepresented indigents. While much emphasis has been placed on prosecution of the accused, the defence has not been given similar consideration. A fully functioning and just legal system should place equal emphasis on prosecution and defence and upholding the right to due process. This project duration is 12 months. |
| Funds Committed: | 750,066 USD | Percentage of Approved: | 100% |
| Funds Disbursed: | 723,634 USD | Percentage of Approved: | 96% |
| SC Approval Date: | January 22, 2009 |
| Expected Project Duration: | 12 Months | Forecast Final Date: | April 2010 | Delay (Months): | 4 Months |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| 1. Identify and recruit a Public Defence Training Coordinator to be assigned with the Judicial Training Institute (JTI) to coordinate the development of a curriculum for training. 2. A comprehensive training manual and program established to train public defender through the Judicial Institute (JI) | Public Defence coordinator has been recruited and the post of curriculum developer advertised. Short listing already done, interviews scheduled. | 100% 50% |
| 3.Office space for 8 public defenders is identified/refurbished | Continued maintenance of 14 vehicles procured under the Public Defenders project, salaries, accommodation and scratch card provided to the Judiciary to enhance the effectiveness of Public defenders. | 100% |
| 4.Public defenders are available and dedicated to represent and protect the legal interest of individuals declared indigents 5. Public Defence monitor recruited to provide oversight monitoring of public defenders alongside the Training Coordinator on a roving basis. | Public defenders have been identified and recruited by the Judiciary and deployed into counties. The Public Defender coordinator continues to play the role of monitor ensuring that they are making the required representation. | 100% 0% |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| outcomes: Peace building Impact: An effective and accessible public defence system that underprivileged and economically challenged individuals, though accused of crimes, can rely and trust for adequate legal representation and protecting the right to due process. Key Outcomes: Citizens will have increasing confidence in public defence system and will begin to seek and rely on trained and equipped public defender for their day in court. | As a result of this projects’ intervention/support to the Public, there has been an increased confidence in their work due to the number of representation made on behalf of indigents. Citizens are now having access to public defenders due to their availability. This is evident by the number of cases defended by the public Defenders in the underprivileged Counties like Lofa, Bong, Grand Gedeh, Grand Kru, River Gee, Maryland and other counties. There are total of 21 public Defenders assigned in the 15 Counties | N/A |
| Number of prolonged pre-trial detentions in withholding centres and at the Central Prison will decrease. Citizens rights to due process protected with greater appreciation of the cliché – “an accused is deemed innocent until proven guilty | Visitation to courts and prisons have increased in the respective assigned areas of the Public Defenders with the aim of providing legal services for indigent where required. |  |
| ”. A functional, trained and equipped criminal justice system comprising both strong and effective prosecution and public defence system. Citizens develop confidence in the fairness of the criminal justice system and its capacity to respect basic human rights. | Pursuant to building a strong and competent justice system, ongoing training for Public Defenders continued with the last session held from September 2nd -3rd 2010 covering the following topics, cross examination, expert witness, and preservation of evidence. |  |

Qualitative achievements against expected results:

Key Achievements: Third phase of training conducted for public defenders on 2nd -3rd September 2010 and the provision of salaries for the 8 public defenders under the project, accommodation, and scratch cards. Additional provision of maintenance/ repairs and fuel for vehicles. Next Steps: The final set of training will be conducted from October 26-27 2010. The training will be held for judges and public defenders following recommendations for a joint training with judges. Recruitment of the curriculum developer in line with the project.

Challenges{If Necessary}:

The late start of project implementation activities due to delay in funds being made available will impact heavily on the completion of the project as originally planned. Delay in the submission of narrative and financial reports from national partners and the UNDP procurement processes continue to present some bottlenecks when recruiting and procuring services and logistics

Annex 1 (Additional elements such as photos, list of workshop participants etc

Pictorial of the Public Defenders Training

# Text boxes

Cllr.Fayia (MOJ) presenting at one of the sessions

Public Defenders in training session

Public Defenders in Training

Public Defense in training session