# Liberia Peacebuilding Fund

# QUARTERLY STATUS REPORT AS OF SEPTEMBER 30, 2010

| Recipient UN Organization: | UNDP | PBF Priority Area: | Critical Interventions to Promote and Resolve Conflict/ Governance |
| --- | --- | --- | --- |
| Implementing Partner(s): | Liberia Anti-Corruption Commission (LACC) |
| Project Number: | PBF/LBR/E-8 (PBF/ PP/R5/A3/01) (ID-70666) |
| Project Title: | Supporting the Liberia Anti-Corruption Commission |
| Total Approved Project Budget | $500,000 |
| Project Objective and Scope | The underlying objective of the project is catalytic, that is, to respond the immediate need of the Commission to achieve functionality as key institution of good governance, by investigating allegations of corruption, building operational and public engagement capacity, and deterring corruption. The project, “Supporting the Liberia Anti-Corruption Commission (LACC)” seeks to address the challenges of corruption that threaten peace in Liberia, by fostering democratic governance—good governance through the establishment of an integrity system in government, to enhance transparency and accountability in the management of state resources and assets. The scope of the project is the fifteen counties of Liberia. |
| Funds Committed: | $500,000 | Percentage of Approved: | 100% |
| Funds Disbursed: | $460,000 | Percentage of Approved: | 92% |
| SC Approval Date: | 22 March 2009 |
| Expected Project Duration: | 18 Months | Forecast Final Date: | September 2010 | Delay (Months): | Three Months |
| Outputs: | Progress: | Percentage of planned: |
| To enhance the capacity of LACC to investigate allegations of corruption and collaborate with national institutions of integrity, and strengthen institutional capacity. | Provided support for initial development of National Transparency index and monitoring checklist in collaboration with CSO; | 70% |
| To enhance the capacity of LACC to investigate allegations of corruption and collaborate with national institutions of integrity, and strengthen institutional capacity. | Provided support to elaboration of MOUs between/ amongst institutions of integrity, including the GAC, MOJ, GC, and the LACC. | 90% |
| Enhanced public awareness/ sensitization through the printing and disseminations of anti-corruption materials | Organized and conducted public awareness campaigns on anti-corruption in the form of county forums in Bong, Lofa, and Nimba Counties. Procured and distributed Anti-Corruption promotional t-shirts, banners for County Forum; | 100% |
| Increased public awareness and sensitization nationwide through print media | Provided support for the printing and disseminations of anti-corruption awareness T-shirts and flyers in Bong, Lofa, and Nimba Counties. | 100% |
| Qualitative achievements against expected results: |
| Key Outputs Achieved Of the numerous achieved outputs, during the reporting period, the LACC has increased public awareness and participations in the fight against corruption and acquired immense support from the citizens. Notably, citizens are now involved in the works of the LACC and have been contributing enormously by providing tips leading to investigations and apprehensions, as well as suggestion for policy improvements. Additionally, there has been enhanced synergies and coordination amongst institutions of integrity, including the MOJ, GAC, GC and LACC through the drafting of MOUs. Next Steps: Support for the conduct of the remaining nationwide anti-corruption county forums. Building on lessons learned, the need for additional funding and support under the PBF is paramount to sustaining peace and combating the ills in corruption along the pathway of democratization and the Rule of Law in post-war Liberia. In addition, , there remains a need for anti-corruption advocacy and staff capacity development initiatives/ training at the LACC, especially for the Executive Director, line managers, and other Commissioners, most of whom have not had the opportunity to benefit from past training initiatives. If additional funds are provided, this can be addressed. Activities planning: Since the beginning of 2010, the LACC has made remarkable strides in gaining public support in the fight against corruption. Meanwhile, in completion of the planned nation-wide anti-corruption campaign, the Commission is left with 4 remaining counties to complete the planned nation-wide anti-corruption forums. |
| Challenges{If Necessary}: |
| During the reporting period, the LACC has made remarkable progress, including investigating and recommending for prosecution a number of alleged corruption cases across Liberia. However, the head of the Investigation Unit at the LACC has recently resigned, and efforts are being made for a suitable replacement. Also, due to the ongoing rainy season in the country, slight changes had to be made for the conduct of the remaining county forums. |
| List of Acronyms and Abbreviations |
| AU………………………………..……………………..............................................………………..African Union AWP…………………………………………………………….…................................................Annual Work Plan CENTAL…………………….................................................Centre for Transparency and Accountability in Liberia CSOs…………………………………….………………….............................................Civil Society Organizations DEX……………………………………………………………………............................................Direct Execution ECOWAS……………………….………........................................... Economic Community of West African States GC………………………………..……................................................................................Governance Commission GOL...........................................................................................................................................Government of Liberia GAC…...................................…………………………………………….………….. General Auditing Commission IMF……………………………………………..….……..........................................…..International Monetary Fund LACC………………………………………..…..............................................Liberian Anti-Corruption Commission MIA……………………………………………..….........................................…………. Ministry of Internal Affairs MPEA………………………………………........................................... Ministry of Planning and Economic Affairs MOU…………………………………..……………….........................................…Memorandum Of Understanding MOJ.................................................................................................................................................. Ministry of Justice NPRS……………………………………………............................................…National Poverty Reduction Strategy PBF……………………………………………..……..………….…...........................................Peace Building Fund TOR………………………………………….…………………..….........................................…Terms Of Reference TRC………………………………………….…….......................................... Truth and Reconciliation Commission UNDP…………………………………………...........................................United Nations Development Programme UNMIL……………………………………….…..……..........................................United Nations Mission in Liberia USAID……………………………...........................................United States Agency for International Development ULSU…………...................................................................................................University of Liberia Student Union WONGOSOL……………………………………….. .........................................Women NGO Secretariat of Liberia |
| Photos of Some of PBF Sponsored Activities |