# Liberia Peacebuilding Fund

# QUARTERLY STATUS REPORT AS OF JUNE 30, 2010

| Recipient UN Organization: | UNDP | PBF Priority Area: | Critical Interventions to Promote and Resolve Conflict/ Governance |
| --- | --- | --- | --- |
| Implementing Partner(s): | Liberia Anti-Corruption Commission (LACC) |
| Project Number: | PBF/LBR/E-8 (PBF/ PP/R5/A3/01) |
| Project Title: | Supporting the Liberia Anti-Corruption Commission |
| Total Approved Project Budget | $500,000 |
| Project Objective and Scope | The underlying objective of the project is catalytic, that is, to respond the immediate need of the Commission to achieve functionality as key institution of good governance, by investigating allegations of corruption, building operational and public engagement capacity, and deterring corruption. The project, “Supporting the Liberia Anti-Corruption Commission (LACC)” seeks to address the challenges of corruption that threaten peace in Liberia, by fostering democratic governance—good governance through the establishment of an integrity system in government, to enhance transparency and accountability in the management of state resources and assets. The scope of the project is the fifteen counties of Liberia. |
| Funds Committed: | $500,000 | Percentage of Approved: | 100% |
| Funds Disbursed: | $385, 372,000 | Percentage of Approved: | 79% |
| SC Approval Date: | 22 March 2009 |
| Expected Project Duration: | 18 Months | Forecast Final Date: | September 2010 | Delay (Months): | Three Months |
| Outputs: | Progress: | Percentage of planned: |
| To enhance the capacity of LACC to investigate allegations of corruption and collaborate with national institutions of integrity, and strengthen institutional capacity. | Provide support for initial development of National Transparency index and monitoring checklist in collaboration with CSO; | 30% |
| Enhanced and public awareness/ sensitization through the printing and disseminations of anti-corruption materials | Organized and conducted public awareness campaigns on anti-corruption in the form of county forums in Gbarpolu, Rivercess and Grand Bassa Counties... Procured and distributed Anti-Corruption promotional T-Shirts, Banners for County Forum; | 100% |
| Enhanced awareness/ sensitization, partnering with citizens and stakeholders through anti-corruption education campaigns | Provided support for the organizations of anti-corruption county forums; and conducted public awareness campaigns on anti-corruption forums in in Gbarpolu, Rivercess and Grand Bassa Counties; | 100% |
| Increased public awareness and sensitization nationwide through print media | Provided support for the printing and disseminations of anti-corruption awareness T-shirts in Gbarpolu, Rivercess and Grand Bassa Counties. | 100% |
| Increased public awareness and sensitization nationwide through electronic media | Provided support for the publications and publishing of information on anti-corruption activities/ forums in Gbarpolu, Rivercess and Bassa Counties. | 100% |
| Qualitative achievements against expected results: |
| Key Outputs Achieved Of the numerous outputs achieved, during the reporting period, the LACC and increased public awareness and participations in the fight against corruption and the establishments of institutions of integrity. Interestingly, citizens are now involved in the works of the LACC and have been contributing enormously by providing tips leading to investigations and apprehensions, etc. Additionally, staff members of the LACC, especially the Commission’s investigative Unit has an enhanced capacity as the results of past capacity building training and seminar provided. Next Steps: Support to elaboration of MOUs between/ amongst institutions of integrity: Building on lessons learned, it has been agreed during the recently conducted project board meeting that support will be provided to LACC for the conduct of the remaining anti-corruption sensitization county forums and, for the elaboration of an MOU between/ amongst public institutions of integrity, including MOJ, GAC, GC, and LACC. There are yet countless needs for anti-corruption advocacy and staff capacity development initiatives/ training at the LACC, especially for the Executive Director, line managers, and other Commissioners, most of whom have not had the opportunity to benefit from past training initiatives; continued support will be provided along this conduit. Activities planning: Since the beginning of 2010, the LACC had embarked two (2) important activities: The Conduct of an Interactive Forum with MOJ, GC, GAC, LACC; and the Development of National Transparency Index and Monitoring Checklist. These activities are well on course, with active involvements of CSOs. Similarly, dialogs leading to the crafting of the MOU between the LACC has completed and there are plans to conduct and complete such interactive forum during the beginning of quarter 3. |
| Challenges{If Necessary}: |
| It’s important to note that during the reporting period, the LACC did make remarkable progress, including the investigation of indict, investigate and recommend for prosecution a number of alleged corruption cases across Liberia. However, there are great concerns from citizens regarding the partiality of a few cases, given that all of the Commissioners at the LACC are political/ presidential appointees, and at such could hold loyalty to the appointer(s)/ political party. Also, it’s worth noting that another major challenge is the ongoing rainy season, which could potentially delay most of the planned activities, especially in rural Liberia. |
| List of Acronyms and Abbreviations |
| AU………………………………..……………………..............................................………………..African Union AWP…………………………………………………………….…................................................Annual Work Plan CENTAL…………………….................................................Centre for Transparency and Accountability in Liberia CSOs…………………………………….………………….............................................Civil Society Organizations DEX……………………………………………………………………............................................Direct Execution ECOWAS……………………….………........................................... Economic Community of West African States GC………………………………..……................................................................................Governance Commission GOL...........................................................................................................................................Government of Liberia GAC…...................................…………………………………………….………….. General Auditing Commission IMF……………………………………………..….……..........................................…..International Monetary Fund LACC………………………………………..…..............................................Liberian Anti-Corruption Commission MIA……………………………………………..….........................................…………. Ministry of Internal Affairs MPEA………………………………………........................................... Ministry of Planning and Economic Affairs MOU…………………………………..……………….........................................…Memorandum Of Understanding MOJ.................................................................................................................................................. Ministry of Justice NPRS……………………………………………............................................…National Poverty Reduction Strategy PBF……………………………………………..……..………….…...........................................Peace Building Fund TOR………………………………………….…………………..….........................................…Terms Of Reference TRC………………………………………….…….......................................... Truth and Reconciliation Commission UNDP…………………………………………...........................................United Nations Development Programme UNMIL……………………………………….…..……..........................................United Nations Mission in Liberia USAID……………………………...........................................United States Agency for International Development ULSU…………...................................................................................................University of Liberia Student Union WONGOSOL……………………………………….. .........................................Women NGO Secretariat of Liberia |
| Photos of Some of PBF Sponsored Activities |