SIERRA LEONE

PEACEBUILDING FUND

PROJECT STATUS REPORT

30 JUNE 2010

| Project No & Title: | PBF/SLE/A-6 |
| --- | --- |
| Recipient UN Organization: | IOM | Priority Sector: | Democracy and Good Governance |
| National Authority: | Attitudinal and Behavioral Change (ABC) Secretariat |
| Location: | Nation wide |
| Project Cost: | USD 140,000 |
| SC Approval Date: | June 2009 | Starting Date: | August 2009 | Completion Date: | July 2010 |
| PBF Outcome and Priority area | Priority 2. Good governance and reconciliation Outcome 6: National reconciliation and inclusion |
| Project Description: | One of the causative factors of the decade long civil war is the negative attitude of Sierra Leoneans towards state property and the citizenry. It is the view of government to change this negative trend by re-orientating the minds of our citizens through continuous engagement and discussions on the need to change their attitude towards work, authority, state property and fellow citizens. There are challenges the country needs to overcome in order to achieve the intended goal; principal among these is the fear of change manifested by the tendency for Sierra Leoneans to continue doing things that are not in the interest of the country. |
| Immediate Objectives: | Citizens understand their roles and responsibilities, and exercise their rights. Sierra Leoneans demonstrate responsible and commitment to upholding the laws, values and ideals which promote peaceful coexistence and development in their country. Increased transparency and accountability with enhanced productivity in major sectors of the economy. The Attitudinal Change Secretariat capacitated for sustained project implementation. |
| Project Progress as at June, 2010 |
| Funds disbursed: | 140,000 USD |
| Delivery rate: | 100% |
| Output delivered: | Produced 250,000 promotional materials to promote No- Drink and Drive Campaign. Held TV discussions and reproduced 250,000 leaflets, distributed in government offices on Lateness and Absenteeism. Produced 500,000 brochures and 2,000 T-shirts distributed during the donor conference for sierra Leone in the UK Proper handling of currency notes awareness campaign undertaken. . The ABC in collaboration with the First Lady’s Attitudinal Change program (FLAXIS) completed visits to ten schools in the western area. Joint police, city council and ABC sensitization seminar held in Freetown, on the role of the police and city council in promoting attitudinal change, particularly in the enforcement of laws and tax collection. Met with parliament and deliberated on how Attitudinal Change impact on their work. Launched No Violence and Drugs in night clubs campaign and distributed 1000 leaflets Visited the Makeni offices of the APC, PMDC and SLPP parties and held deliberations on political and peaceful coexistence. Organized TV program on corruption and lateness at work. Organized ABC Awareness Campaign for fishermen at the Lumley community in and for market traders at Sewa grounds in Freetown. Organized dialogue session on Work Responsibility, Honesty and integrity with the departments of Immigration and Births and Deaths Corruption with the Police Media Unit. TV talk show on corruption and respect for one another. The ABC in collaboration with Children’s Unite for Attitudinal and Behavioral Change Campaign, organized TV and radio programs on No Violence in school sports. Organized and paid visits to the university, schools and a few communites to assess how the sensitization on change of attitudes is impacting on election violence, attitudes towards school work and treatment of public facilities respectively Local goverenmt was also visited to determine the level of political tolerance and response to payment of local taxes in the area. Salary support to Secretariat staff. |
| Achievements/ challenges: | During the assessment exercise, it was observed that after the ABC awareness campaign on civic responsibilities and rights, more Sierra Leoneans now understand and appreciate their civic responsibilities and rights. More Sierra Leoneans now understands than before why they should pay their taxes and are now willing to pay such taxes. During the session with the Traffic Police and Traffic Wardens it was revealed that there have been an increase in the understanding and respect drivers ,passengers and pedestrians have for traffic rules and regulations. The tense student political tension in Fourah Bay college campus during the 2010 student union elections was defused by the timely intervention of the ABC. The elections were conducted in peace to the surprise and admirations of the general public. This is a great achievement towards eliminating student violence in schools and colleges. During the discussions with local councils, paramount chiefs and political youth groups, it was observed that as a result of the ABC political t as a result of the ABC political tolerance campaigns tolerance campaigns, councillors and youths groups regardless of their ethnic or political affiliations are now being united in their approach towards national peace and development. |