SIERRA LEONE

PEACEBUILDING FUND

EMMERGENCY PROJECT STATUS REPORT

30 JUNE 2010

| Project No & Title: | PBF/SLE/J-3 Supporting the Implementation of the Joint Communiqué through the refurbishment of the SLPP Headquarters |
| --- | --- |
| Recipient UN Organization: | UNDP | Priority Sector: | Democracy and Good Governance |
| National Authority: | Sierra Leone People’s Party |
| Location: | Freetown |
| Project Cost: | USD 69,550 |
| SC Approval Date: | June 2009 | Starting Date: | August 2009 | Completion Date: | Extended to September 2010 |
| PBF Outcome and Priority area | Priority 2: Good governance and national reconciliation. Outcome 6: national reconciliation |
| Project Description: | In March 2009, Sierra Leone was hit by the biggest eruption of violence since the end of the war between the two main political parties –the ruling APC and the opposition SLPP that lead to injuries, loss of property and alleged rape of SLPP supporters. This political impasse was further heightened by the party owned radio stations. The clashes which had started in the south of the country in a period preceding a by-local council election degenerated in a few days to what has been described as the greatest pointer yet to the fragility of the peace in Sierra Leone. The UNIPSIL and UNCT brokered peace talks that resulted in the signing of a joint communiqué which attempted to address the key issues brought forward by both parties. |
| Immediate Objectives: | l. .A maximum of damaged windows rehabilitated 2. A maximum of damaged doors rehabilitated 3. A maximum area of walls re-painted |
| Project Status as at June 2010 |
| Funds disbursed: | USD 60,000 |
| Delivery rate: | 86% |
| Outputs delivered: | Overall progress of refurbishment is 50% of total construction. Refurbishment of items below has been progressed; [Inside the building] Reinforcement of retaining wall – 67% Plumbing system (including the toilets) – 75% Repairmen of doors and windows – 55% Electrification –55% Painting – 65% [External works] Repairmen of perimeter fencing – 80% |
| Achievements and challenges | Challenges the contractor faced during the reporting period included the early start of the rainy season which impeded access and completion of the work by the end of the 2nd quarter. The SLPP also authorized and incurred costs for additional works. UNIPISL visited the construction site on a regular basis, to ensure the pace and quality of work was maintained as much as possible. Frequent communication and consultation between UNIPSIL, and the SLPP/ the contractor also enhanced the work. Through discussions to determine the programme extension period, SLPP demonstrated a high commitment to complete the programme within the minimally required period which has been caused by the modification of the scope of the work. The confidence among the parties has been strengthened. |