SIERRA LEONE

PEACEBUILDING FUND

EMMERGENCY PROJECT STATUS REPORT

30 SEPTEMBER 2010

| Project No & Title: | PBF/SLE/J-2 Special Initiative to promote Community Women’s participation in Security Sector Reform (SSR) Process in Sierra Leone |
| --- | --- |
| Recipient UN Organization: | IOM | Priority Sector: | Justice and Security |
| National Authority: | WIPSEN-Africa/ Ministry of Social Welfare, Gender and Children’s Affairs |
| Location: | Boarder areas (North, South and East) |
| Project Cost: | USD 45,261 |
| SC Approval Date: | June 2009 | Starting Date: | August 2009 | Completion Date: | July 2010 |
| PBF Outcome and Priority area | Priority 1. Implementation of peace agreement. Outcome 1: Strengthen security sector |
| Project Description: | The central logic of the intervention is to engage community women as well as female security personnel at the provincial District and chiefdom levels in a systematic dialogue on the SSR processes is Sierra Leone with a view to assessing its gender disaggregated impact particularly as it relates to opportunities for women’s full and active involvement in the governance of security, conflict prevention, peace building, sustainable development and democratization at the community level. The project shall target communities in the north, south and east particularly the boarder areas. The project seeks to compliment and add value to an on-going support to the ONS which provides training for security personnel but which failed to target women. |
| Immediate Objectives: | Create and interactive platform for community women, female security personnel and provincial and district security personnel Empower key female security personnel and community women’s groups to mainstream gender perspectives in the newly decentralized security structures and operations e.g. DISECs, PROSECs Sensitize community members to promote active participation of women in the security sector |
| Project Status as at September, 2010 |
| Funds disbursed: | 45, 261USD |
| Delivery rate: | 100 % |
| Outputs delivered: | In Pujehun District 20 women and 5 men were introduced to the SSR Process. In Kailahun District 20 women and 5 men were introduced to the SSR Process. In both districts women were drawn from: Female Security Sector Personnel, Ward Committee Members, Counselors, Community Based Associations, and Chiefs. In both districts men were drawn from: Provincial Security Committees and District Security Committees. 2 days training for Provincial Security Committees (PROSECs), District Security Committees (DISECs) and Chiefdom Security Committees (CHISECs) was organized in Kenema. This training attracts participants from the PROSECs in the Northern, Southern, Eastern and Western regions; the DISECs in the targeted communities of the project, i.e. Kambia, Pujehun and Kailahun; representatives of the newly formed women’s security groups in these three districts and representatives of the Office of National Security (ONS )and women’s CSOs in Kenema. Rural women community security groups were established in the Kailahun, Pujehun and Kambia districts and received gender Training on Decentralized Security Structures. Women in Security Marches and Panel Series were organized in Kambia , Pujehun and Kailahun Districts |
| Achievements and challenges | With the formation of women security groups at community level in the project targeted districts and with the relevant security training provided to them, Women at community level for the first are accepted by their male counterpart as an integral part of the national security structures and key players in the Security Sector Reform (SSR) process. With the successful implementation of the project, community women now realised that they and their communities have vital roles to play in the SSR process and they are willing to accept and play their roles. Community women in security hour in Kambia, Pujehun and Kailahun districts and the Panel series and women in security marches in Kambia, Pujehun and Kailahun Districts will be achieved ion this quarter. The reasons for postponing were first, the Beijing +15 celebrations and UN Commission on the Status which most of the women (especially at the level of the project implementing partners) were participating in. Second, is the national level celebrations of the International Women's Day in Sierra Leone in which majority of the community women are expected to attend? During the trainings the implementing partner identified the need to develop guidelines to build the capacity of participants to engage in the security hour radio program. The guiding manual was not completed during this quarter. |