|  | Insert Fund specific logo, if applicable |
| --- | --- |

[UN Peacebuilding Fund]

PROJECT COMPLETION report

REPORTING PERIOD: JULY 2007 – December 2009

| Submitted by: Yuichiro Sakai, Programme Officer, UNDP Sierra Leone yuichiro.sakai@undp.org |  | Country and Thematic Area Justice and Security |
| --- | --- | --- |

| Programme No: 00047718 MDTF Office Atlas No: 00057546 Programme Title: Capacity Development of the Human Rights Commission of Sierra Leone |  | Participating Organization(s): UNDP |
| --- | --- | --- |

| Implementing Partners: UNDP UNIPSIL Human Rights Commission of Sierra Leone (HRCSL) |  | Programme Budget (from the Fund): UNDP : USD 1,522,055 |
| --- | --- | --- |
| Programme Duration (in months): Start date: July 2007 End date: Original: 1 year from the start date Revised end date: March 2009 Operational Closure Date, if applicable: March 2009 Budget Revisions/Extensions: Budget revision in November 2008 |
| Introduction: The Narrative Progress Report template is in line with the UNDG Standard Progress Report. Building on continued efforts made in the UN system to produce results-based reports, the progress report should describe how the activities (inputs) contributed to the achievement of specific short-term outputs during the twelve month reporting period, and to demonstrate how the short-term outputs achieved in the reporting period collectively contributed to the achievement of the agreed upon outcomes of the Strategic (UN) Planning Framework guiding the operations of the Fund. In support of the individual programme reports, please attach any additional relevant information and photographs, assessments, evaluations and studies undertaken or published. The information contained in the Programme Summaries and Quarterly Updates prepared by the Participating Organizations may be useful in the preparation of the Annual Narrative Progress Report. These Summaries and Updates, where applicable, are available in the respective Fund sections of the MDTF Office GATEWAY (http://mdtf.undp.org/). |
| Formatting Instructions: The report should not exceed 10-15 pages. The report should be submitted in one single Word or PDF file. Annexes can be added to the report but need to be clearly referenced, using footnotes or endnotes within the body of the narrative. Do not change the Names and Numbers of the Sections below. |

# NARRATIVE REPORT FORMAT

# Purpose

Abuse of Human rights has been identified as one of the root causes of the conflict in the TRC report.  The Government with the assistance of the international community established Human Rights Commission of Sierra Leone (HRCSL), in 2004, to advocate, monitor and redress cases of human rights abuses particularly those affecting for women, children, and former war victims. This project relates to Justice and Security area of the PBF Priority Plan.  The project proposal was approved in July 2007 to support institutional establishment and capacity building of the SLHRC to improve the culture of respect and protection of human rights in the country.

# Resources

Financial Resources:

PBF-Funding: USD 1,522,055

In addition to funding from PBF, UNDP received US$ 175,000 from DGTTF for the Capacity Development of the National Human Rights Commission which complemented this project in 2007.

Budget revision was approved by the project steering committee in November 2008.

Human Resources:

- International Staff: 1 Programme Officer is attached to this project and supported by a Senior Advisor on Human Rights funded directly by UNDP

# Implementation and Monitoring Arrangements

The HRCSL is the implementing institution while the UNDP is primarily responsible for the institutional building including technical assistance and procurement as well as fiduciary oversight and accountability. UNIPSIL provides the technical assistance and guidance to the HRCSL on specific issues relating to human rights, justice delivery and security.  The secondary beneficiaries of the project include civil society organizations and the general public. CSOs are targeted for specific training on human rights monitoring and public education.

The Steering Committee supervises the implementation process. The Committee is chaired by the chairperson of the HRCSL and comprised of representatives from the Ministry of Finance and Economic Development (MoFED), Ministry of Justice, UNDP, OHCHR, and UNIPSIL and civil society organizations. The Steering Committee meets quarterly to review implementation progress of activities earmarked in the annual work plan and when necessary take critical and appropriate decisions in the interest of the project.  UNDP‘s programme officer meets with the secretariat of HRCSL on a weekly basis to coordinate and support the management of project activities. In addition, meetings are regularly scheduled between the Commission and UNDP’s Senior Advisor on Human Rights to discuss substantive human rights issues.

The project is implemented under the DEX modality, and all procurement for this project has been conducted in accordance with UNDP policies and procedures.

The HRCSL is responsible for producing quarterly progress reports for the Steering Committee. Programme officers of both the HRCSL and UNDP meet at least once a week to review project activities.  The mid-term review meeting of the project was conducted in March 2008 with participation from civil society, government and donors on achievements, challenges and way forward. This meeting aimed to document progress made, key lessons learned and recommendations to enhance service delivery.

The mid-term evaluation of the Peacebuilding Fund (PBF) for Sierra Leone was conducted in April 2009.

# Results

Through the PBF support, the HRCSL has established itself as a justice institution in the country able to systematically address one of the root causes of the conflict through the promotion of improved human rights norms and access to justice. The annual State of Human Rights Report was launched in 2008, the first by a state institution, providing important recommendations to government. The HRCSL judicial powers could help to bridge the gap between the inaccessible and daunting formal Justice Sector and the accessible but abuse-prone informal system. Since its creation the Commission has identified over 300 cases alleging human rights violations, paid visits to prisons and police cells to make recommendations on meeting basic human rights standards, and conducted training for civil society and traditional stakeholders on gender laws and human rights based approach.

FULLY STAFFED AND FUNCTIONING COMMISSION

The Commission came into operations in 2007. The initial focus was primarily on establishing the operational foundation of the institution with the requisite logistical and institutional support. Consequently, major procurement activities were embarked upon with the aim of ensuring a fully equipped, furnished office of HRCSL.

With the HRCSL physical location finally established, and the appointment of Senior Advisor for Human Rights in 2008, by UNDP, the focus of support and Commission’s activities shifted from enhancing logistical capacity to a more programmatic and activity based approach aimed at facilitating the promotion of human rights and monitoring of implementation of the TRC recommendations. This included strengthening of management and human resources capacity of the HRCSL.

IMPROVED HUMAN RIGHT NORMS AND ACCESS TO JUSTICE

With the establishment of the HRCSL, there has been an improvement in the human rights norms where national policy is concerned.  The HRCSL played an instrumental role in the formulation and subsequently the enactment of 3 gender bills – the Domestic Violence Act 2007, Registration of Customary Marriage and Divorce Act 2007, and the Devolution of Estate Act 2007.

The Commission received 244 complaints on human rights violations by the end of 2008, which is an indication that the HRCSL is increasingly gaining the trust of the public as capable of justice delivery. Additionally, the project assisted the HRCSL to publish and launch the first Annual Report on Human Rights in Sierra Leone 2008.  In 2008, the HRCSL embarked on the national sensitization on human rights through various consultative meetings and workshops with stakeholders including the local government, police, traditional authorities and a wide range of civil society organizations.  The 3 regional offices in Bo, Makeni, and Kenema have been established to make the Commission more accessible for the rural population. By having offices in the region, the rural populace does not have to travel to Freetown to lodge their grievances thereby saving time and costs. These regional offices can now receive complaints, address these complaints in a timely manner and where necessary provide the required legal advice and support.

PBF support has enabled the HRCSL to be functional, with core staff, equipment and capacity to intervene in HR issues, and promote and protect the culture of human rights in Sierra Leone.  The HRCSL is now able to launch the annual report on the state of human rights, address the backlog of state reporting obligations, and effectively monitor the state of observance of the International Convention on Human Rights. A medium-term Strategic plan, with technical guidance from the Institutional Development Advisor for the next 3 years has been developed to guide the priority action of the HRCSL and its CSO partners.

In the period since it was established, the HRCSL has been a strategic entity in bringing access to justice closer to the general population. It has managed to dispel the misconceived notion that the justice system is alienating and complicated. As evident from the number of cases received through 2008 (244 cases ranging across 51 types of violations), the Commission have made access to justice less intimidating and user-friendly. In this way, the Commission has complemented the gaps in the justice system and therefore contributing to the overall quality of the justice delivery in the country.

The key outputs achieved during the reporting period include:

- The Annual State of Human Rights Report detailing the achievements, challenges in the country, and recommendations produced and launched by President Koroma in the Kroobay Slum in Freetown

- 750 copies of the Annual State of Human Rights Report produced and disseminated to various Ministries and civil society organisations with the aim of providing strategic direction and guidance on incorporating human rights component in their project activities

- Monitoring on human rights situations in local elections campaign activities conducted in the East, South, North and Western regions in the country by human rights officers of the HRCSL

- Training sessions were conducted for chiefs and other traditional leaders on human rights and human rights based approach to local governance held in Northern, Eastern, Southern and Western Area.

- Training by HRCSL on the substantive aspects and technicalities were conducted for members of civil society organizations and HR Committees in 12 Districts on the monitoring of the implementation of the Child Rights Acts and the Gender Justice Laws conducted.

- Collaborated with the Anti-Corruption Commission to organize the 60th Anniversary Celebration of the Universal Declaration of Human Rights featuring town hall meetings, inter-religious vigils and child-to-child sensitization programs nationwide.

- Report of the baseline survey on the knowledge, attitude and perception of human rights in Sierra Leone developed

- 3 regional offices in Bo, Makeni, and Kenema secured and equipments and furniture transferred

- Received 244 cases of complaints on human rights violation from Sierra Leoneans including for domestic violence, matrimonial dispute, due process, right to property, and assault

As this is considered a pioneering project with no precedence, the project faced some challenges.  At the beginning of the project, the lack of staffing to manage the running of this project on a dedicated basis posed some operational challenge for project implementation.

In the early stages of the programme, it was noted that there was low understanding on UNDP procedures and general business procedures. To address this situation, UNDP conducted a one-day session on UNDP procedures and regulations with main national counterparts. This training also coincided with the objective of building the institution’s capacity in areas such as financial resources and procurement. UNDP also recruited a Finance Analyst to assist the HRCSL in expediting project implementation and to ensure that UNDP policies are followed accordingly. To build the institutional capacity of the Commission to manage its financial operations, the Finance Analyst ensured that there were transfers of knowledge to national counterpart on financial procedures and reporting.

An Institutional Development Advisor (IDA) with extensive experience on national human rights institutions was recruited by UNDP to provide overall guidance and backstopping on the operation of the HRCSL, and to provide technical guidance on the substantive issues.  .

The management of the project was complimented by technical assistance and knowledge provided by UNIPSIL Human Rights and Rule of Law Section, in addition to UNDP’s recruitment of a Senior Advisor on Human Rights..UNIPSIL has been instrumental in providing technical support and transfers of knowledge to the Commission.  Furthermore, partnership with Irish Aid has been established whose seed money for a basket fund will guarantee the sustainability of the support to the HRCSL.

Promoting the rights of the vulnerable, especially for women and children is one of the focus areas of the HRCSL’s work.  In Sierra Leone, three key gender laws were enacted in 2007, namely the Domestic Violence Act 2007, Registration of Customary Marriage and Divorce Act 2007, and the Devolution of Estate Act 2007. The HRCSL provided technical assistance to the government in the formulation of these laws.  In addition, in order to popularize the three acts and to develop a partnership with the civil society for joint monitoring and reporting, the HRCSL conducted a workshop for stakeholders on the content of the Gender Acts and Child Rights Acts a

The majority (96 %) of the project activities were completed by the end of 2008.  In 2009, remaining activities were completed before the operational project closure in March 2009.   HRCSL developed results-oriented Strategic Plan in order to identify new sets of outputs and results to achieve further strengthening of the capacity of the HRCSL and improving the culture for respect and protection of human rights in the country.  Further, a report of the baseline survey on the knowledge, attitude and perception of human rights in Sierra Leone was developed, and the Commission responded to 56 cases of allegations on human rights violation from Sierra Leoneans including for domestic violence, matrimonial dispute, due process, right to property, and assault.  Additionally, consultative meetings with civil society organizations were conducted nationwide in order to discuss and raise awareness for the Annual State of Human Rights Report and the Strategic Plan of the HRCSL.

# Future Work Plan (if applicable)

Project was operationally closed in 2009.

# Performance Indicators (optional)

# Abbreviations and Acronyms

- HRCSL - Human Rights Commission of Sierra Leone

- UNDP – United Nations Development Programme

- UNIPSIL – United Nations Peace building Office in Sierra Leone

- CSOs – Civil Society Organizations

- DGTTF – Democratic Governance Thematic Trust Fund

# Footnotes

E.g. Priority Area for the Peacebuilding Fund; Thematic Window for the Millennium Development Goals Fund (MDG-F); etc.

The start date is the date of the first transfer of funds from the MDTF Office as Administrative Agent.

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office.

E.g. in the case of the MDG-F, it is important to show how the programme relates to the UNDAF and how it aims to support national development goals, including the Millennium Development Goals. The causal links and rationale between the joint programme, the thematic window of the MDG-F and the MDGs should be clearly stated. In the case of the Peacebuilding Fund’s Peacebuilding and Recovery Facility (PRF), show how the programme relates to the PBF Priority Plan’s objectives. For the UNDG Iraq Trust Fund, explain how the programme relates to the UN Assistance Strategy for Iraq, UN MDGs, ICI, NDS, etc.

E.g. for the UNDG Iraq Trust Fund and the MDG-F.