**Peru**

|  |  |
| --- | --- |
| **Programme Title:** | Perú: Promotion of employment and MSEs for youth and managment of juvenile labor migration |
| **Programme number & MDTF ref:** | MDGF-1901-H-PER Employment and (67200) |
| **Window:** | Youth, Employment & Migration |
| **Approved Budget by NSC (US$):** | 3.025million |
| **Participating Organizations:** | ILO, UNFPA, IOM, UNDP |
| **First Tranche transferred on:** | 21-Feb-2009 |
| **Second Tranche transferred on:** | 23-Apr-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| National study on employment and migration being published. Draft national employment policy under review. The Certi-jovenprogramme started in selected cities (1460 beneficiaries). Youth employment web portal for the national employment system designed. 67,214 visits received. Infomigra programme started. 280 persons benefitted. Staff of the national directorate for migration and employment trained. |
|  |
| **Problems and lessons learned:** |
| **Problems:** High rotation of public servants in some governmental counterparts.  Relations between central government and regional governments – need for enhanced coordination between government levels and between JP and regional governments. External to the JP (revaluation of the local currency - Peruvian sol - required re-dimensioning certain activities.  **Lessons learnt:** 1) Need for enhanced RBM M&E capacities; 2) Importance of articulation channel between central and regional governments. |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** There is a communication strategy based on governmental counterparts. |

CHARTS& FIGURES

As of 31 December 2010

