**Philippines**

|  |  |
| --- | --- |
| **Programme Title:** | Strengthening the Philippines’ Institutional Capacity to Adapt to Climate Change |
| **Programme number & MDTF ref:** | MDGF-1656-E-PHL Strength. Inst (67145) |
| **Window:** | Environment & Climate Change |
| **Approved Budget by NSC (US$):** | 8 million |
| **Participating Organizations:** | UNEP, WHO, UNHABITAT, ILO, FAO, UNDP |
| **First Tranche transferred on:** | 18-Dec-2008 |
| **Second Tranche transferred on:** | 26-May-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Methodology for determining vulnerability and assessing socio economic impact completed and under stakeholder review. Draft communications plan on CCA prepared. First phase of capacity assessment completed. Climate Change Academy in one of the demonstration sites established. Pilot testing for early surveillance completed in two areas. Vulnerability assessment and shelter plan for Sorsogon developed. Guidelines for innovative financing developed and ready for pilot-testing. Market research for viable economic options completed. |
|  |
| **Problems and lessons learned:** |
| Managerial. JP Design. UN Agency coordination (differing regulations), including direct execution by certain agencies which undermines country ownership and use of country mechanisms. |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

.CHARTS& FIGURES

As of 31 December 2010

