Joint Programme Monitoring Report:

Development and Private Sector Window

The monitoring report should be submitted to the MDG-F Secretariat on a bi-annual basis.  The report is due no later than 20 days following the end of June and December (20 July and 20 January).  The monitoring report will replace the existing quarterly narrative reports which will no longer need to be submitted to the Secretariat.  Please submit to the MDG-F Secretariat at: mdgf.secretariat@undp.org

Section I: Identification and Joint Programme Status

a. Joint Programme Identification and basic data:

| Date of Submission: 20 July 2011 Submitted by: Borka Jeremic Name: Karlo Puskarica Title: Joint Programme Manager Organization: UNDP Contact information: karlo.puskarica@undp.org |  | Country and Thematic Window Serbia/Development and Private Sector |
| --- | --- | --- |

| MDTF Atlas Project No: 00070513 Title: Sustainable Tourism for Rural Development |  | Report Number: 3 Reporting Period: 1/1/2011 – 30/6/2011 Programme Duration: 30 months Official starting date: 04/12/2009 |
| --- | --- | --- |

| Participating UN Organizations FAO, UNEP, UNDP, UNWTO, UNICEF |  | Implementing partners Ministry of Economy and Regional Development; Ministry of Agriculture, Forestry and Water Management; National Tourism Organization of Serbia |
| --- | --- | --- |

The financial information reported should include overhead, M&E and other associated costs.

| Budget Summary |
| --- |
| Total Approved Joint Programme Budget | UNEP: 333,709 UNWTO: 1,026,211 FAO: 1,160,238 UNICEF: 431,018 UNDP: 1,028,824 Total: 3,980,000 |
| Total Amount Transferred to date | UNEP: 293,793 UNWTO: 826,426 FAO: 1,002,172 UNICEF: 348,243 UNDP: 824,250 Total: 3,294,884 |
| Total Budget Committed to date | UNEP: 0 UNWTO: 130,524 FAO: 114,287 UNICEF: 82,260 UNDP: 370,906 Total: 697,977 |
| Total Budget Disbursed to date | UNEP: 54,190 UNWTO: 143,161 FAO: 180,861 UNICEF: 63,852 UNDP: 171,220 Total: 613,284 |

Note: The report does not include formulation advance (USD 20,000).

BENEFICIARIES

The column “expected” refers to the target of beneficiaries you planned to reach by the end of the joint programme and the column “to date” refers to the actual number of beneficiaries you have reached up to the end of the reporting period. The beneficiaries must be counted on a cumulative basis.

| Indicate Beneficiary type | Expected number of Institutions | Number of Institutions to date | Expected Number of Women | Number of Women To date | Expected number of Men | Number of men to date | Expected number of individuals from Ethnic Groups | number of individuals from Ethnic Groups to date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Institutions | 5 | 3 | 10 | 6 | 10 | 5 |  |  |
| Local Institutions |  | 48 | 50 | 25 | 30 | 27 | n/a |  |
| Urban |  |  |  |  |  |  |  |  |
| Rural | 556 |  | 350 | 305 | 520 | 151 | n/a |  |
| Total | 561 | 51 | 410 | 336 | 546 | 183 |  |  |

Direct Beneficiaries: “The individuals, groups, or organizations, targeted, that benefit, directly, from the development intervention”.

Indirect Beneficiaries: “The individuals, groups, or organizations, not targeted, that benefit, indirectly, from the development intervention”

| Indicate Beneficiary type | Expected number of Institutions | Number of Institutions to date | Expected Number of Women | Number of Women To date | Expected number of Men | Number of men to date | Expected number of individuals from Ethnic Groups | number of individuals from Ethnic Groups to date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Institutions | 3 | 4 | 5 | 2 | 5 | 1 |  |  |
| Local Institutions | 124 | 30 | 408 | 25 | 25 | 18 |  |  |
| Urban |  |  | 40 | 4 | 4 | 1 |  |  |
| Rural | 1500 | 20 | 650 | 200 | 180 | 9 |  |  |
| Total | 1624 | 54 | 1098 | 231 | 214 | 29 |  |  |

- Joint Programme M&E framework

This template is the same as the one you will find in the JP documents. We have added 3 columns to provide spaces for baselines of the indicators as well as targets. All the values for indicators in this template are cumulative. This means the past values obtained accumulate (add up over time) as the joint programme gets implemented. We are expecting you to include not only the indicators but the value of these indicators. If you do not provide them, please explain the reason and how you are going to obtain this information for the next reporting period.

| Expected Results (Outcomes & outputs) | Indicators | Baseline | Overall JP Expected target | Achievement of Target to date | Means of verification | Collection methods (with indicative time frame & frequency) | Responsibilities | Risks & assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| From Results Framework (Table 1) | From Results Framework (Table 1) | Baselines are a measure of the indicator at the start of the joint programme | The desired level of improvement to be reached at the end of the reporting period | The actual level of performance reached at the end of the reporting period | From identified data and information sources | How is it to be obtained? | Specific responsibilities of participating UN organizations (including in case of shared results) | Summary of assumptions and risks for each result |
| 1. JP Outcome 1: Legal and policy framework for supporting diversification of rural economy through tourism is developed and contributes to achievement of Millennium Development Goals. |
| 1.1. National Rural Tourism Master Plan for Serbia developed and submitted to the Government | Outcome Indicators -Serbia Rural Tourism Master Plan finalised and adopted by national partners at the beginning of Year 2. -Serbia Rural Tourism Master Plan is approved/ adopted by the Inter-ministerial Group and submitted to the Government for approval by end of first trimester of Year 2. -Number of tourists (domestic and international) and number of their overnight stays. -Number of beds. -Number of women employed in tourism related activities. -Number of new rural tourism businesses / number of households in tourism business. Amount of funds dedicated to rural tourism development, adopted and contained within MERD and MAFWM policy documents. | Baseline: 11 individual Master Plans for various tourist destinations in Serbia; 4 in progress; but no broad-based Rural Tourism Master Plan / Policy with national strategy Data on international migration flows of young people are not collected in a systematic way. The migration profile of Serbia still does not exist. The Office also lacks more recent data on internal migration Social protection indicators for youth are not defined and means of their regular collection not identified. Indicators for youth labour market, youth migration and social protection not integrated into DevInfo database system. | SRTMP: National partners and Inter-ministerial Group submitted SRTMP to the Government. | The Sustainable Rural Tourism Development Master Plan was approved by the Government and has since been submitted to Parliament for approval. The Master Plan formulation and approval process was highly consultative with interviews and workshops conducted periodically with Government, partner UN agencies, and rural tourism stakeholders of Serbia. Child, youth and family tourism development framework defined | Inter-ministerial working group meeting minutes & attendance. Complete deliverables for all Master Plan components. Progress reports working group and contractor. Workshops/presentations attendance records. Surveys databases. | Annual Monitoring | . Lead Agency: UNWTO Contributing Agencies: UNICEF, UNEP, FAO Partner: MERD Inter-ministerial working group, led by chairperson | Risks -Political and/or economic shocks shift the attention of policy-makers away from tourism and rural development. -Delays due to contracting procedures or performance. -National institutions fail to agree or cooperate on activities, or fail to honour prior commitments. -Turnover of policy makers and civil servants results in delays. -Private, public and/or civil society sectors are reluctant to cooperate. -RTMP not fully developed through a participatory process, i.e. few rural tourism entrepreneurs and other stakeholder representatives participated, resulting in lack of full commitment to the implementation of the Master Plan. Assumptions -No major institutional change of any partner occurs during the implementation of the project. -The commitments taken at policy level are executed. -There is a reliable and timely flow of information and data among the partners and within the working group. -No changes in roles and responsibilities of partners, contributing local organizations. Existing obligatory system of charging for rural tourism services via intermediary (travel agents and LTOs) changed, rural households allowed to charge directly to guests. |
| 1.2. Rural Development Program Planning: Rural Development Program planning is mainstreamed in Serbia's | -IPARD Axes 2 & 3 measures prepared & submitted to Government by end of JP. -Number and type of organizational stakeholders & partners involved in development of Rural Development Program: At least 100 stakeholders - LTO representatives, local governments’ representatives, farmers, rural entrepreneurs, civil sector. -At least 20% of all stakeholders representatives included in development of Rural Development Program are representing rural women. -Number of workshops, presentations & coordination meetings held during preparation and adoption of IPARD Axes 2 & 3 measures: At least 4 strategic planning workshops and 4 project planning workshops. | Baseline: IPA financial envelope 2007-2013: €10.2 billion (all candidate countries). | -IPARD National Agriculture & Rural Development Program (2010-2013): Strategic guidelines for inclusion of rural tourism & related activities to Axes 2 & 3 developed, facilitating Serbia’s access to EC IPARD Axis 2 & 3 funds -IPARD Life-Conditions Study: Provide strategic input into IPARD with life-conditions so as to ensure integrated rural tourism development addresses issues of access to services (health, education & social protection) for children & women in rural areas | Study on Access to Services of Women and Children in Rural Areas containing recommendations for national institutions and IPARD measure completed. The Study will be published in August. | Complete deliverable of IPARD Axes 2 & 3 measures submitted to Government. Workshops/presentations/meetings/ attendance reports. Working Group(s) meeting minutes & attendance. | Annual Monitoring | Lead Agency: FAO Contributing Agencies: UNICEF Working group, led by chairperson. Partner: MAFWM |  |
| 1.3. Investment Mainstreaming: Sustainable tourism investments mainstreamed in Serbia's national policies. | Output Indicators: -Amount of public investment made in line with Investment plan as part of Rural Tourism Master Plan. -Number of individual public investments made in line with Investment plan as part of Rural Tourism Master Plan. -Amount of private funds secured for realization of Rural Tourism Master Plan. -Number of tourist destinations (municipalities) receiving public investment. -M&E strategy and indicators developed and adopted by Government for Rural Development Fund & Fund for Tourism Development. -Amount of MAFWM funds dedicated to support rural tourism. -Number and structure of users of MAFWM funds. -Ratio of MAFWM fund beneficiaries coming from the JP target regions (number of beneficiaries and amount of awarded funds to total. -Number of users and amount received from MERD tourism development loans for rural tourism. -Ratio of MERD tourism development fund beneficiaries coming from the JP target regions (number of beneficiaries and amount of awarded funds). | 2008 public tourism investment: €50M. 2009 public tourism investment: €22M. Due to the complexity of calculating public investments made by various government institutions, the amount included in the project document was only an estimate, which has now been refined through detailed follow up. in 2008 was EUR 46.608.133 (USD 68.380.302) and in 2009 it was EUR 21.702.759,22 (USD 30.221.390) | Public Investments toward Rural Tourism Master Plan: Serbia public sector commits minimum $75 million in rural tourism initiatives and supporting infrastructure in line with Rural Tourism Master Plan by end of JP. Public-Private Partnership Guidelines: Functional guidelines for successful public-private partnerships developed and institutionalized, evidenced by completion of at least six PPP initiatives by end of JP. SIFT Network: National focal point established for Sustainable Investment and Finance in Tourism (SIFT) Network. Investment Monitoring & Evaluation Strategy: Formal process installed to feed lessons learned from Outcome 2 into public tourism investments. | Public funding for tourism development has being reviewed at the national level, in preparation for the Investment Forum which will take place in the second half of the 2nd year. SIFT Focal Point organized investment workshop, in cooperation with UNDP 3 projects aiming Diversification of Rural Economy through Tourism were supported through grants. 3 NGOs in partnerships with public and private sector were granted, and these partnerships are very important for establishment of LAGs. | Copies of project payments and delivery receipts through public investment. Reports & public records of investments. Reports from M&E monitoring agency on fund investments. Report on investment workshop | Annual Monitoring | Lead Agency: UNDP Contributing Agencies: UNEP Partner: MERD Local agent ultimately tasked with Government investment M&E. UNEP/UNDP | Risks economic shocks shift. -National institutions fail to agree or cooperate on activities. -Private, public and/or civil society sectors are reluctant to cooperate. Assumptions -No major institutional change of any partner occurs during the implementation of the project. -There is a reliable and timely flow of information and data among the partners and within the working group. No changes in roles and responsibilities of partners, contributing local organizations |
| 2. Local rural tourism and support industries are better linked and organized; and local stakeholders’ capacity is improved for delivering services and products in line with national strategies. |
| 2.1. Capacity developed for sustainable rural tourism in order to enhance rural development | Outcome Indicators: Number of projects developed as a result of JP capacity building, mentoring support. Number of new products developed and marketed. Visitor satisfaction levels. Increase in the training participants' income from rural tourism activities. Output Indicators: Number of LAGs established and trained. Number of tourism stakeholders trained (with exam based certificates, where applicable), disaggregated by gender and public vs. private sector. Number of local development strategies that include rural tourism. Number and type of different training courses provided over life of JP. | -Rural Development Network is existing & functional. -Projects supported through public funds are not accessible for persons with disabilities. -Ministry of Agriculture, Forestry and Water Management provides grants for rural women's NGOs. -Tourism Governance Organizations do not exist in Serbia. | - Local Action Groups: Capacity of public, private and civil society sector stakeholders strengthened to enable establishment of six Local Action Groups (representing 10,000-100,000 citizens) and develop local rural development strategies, by end of JP. -Rural Development Network: Capacity of national Rural Development Network strengthened in the target regions to lead development and facilitation of Local Action Groups, independently lobby for development initiatives and secure resources for regional development by end of JP. - Local planning: All 19 target municipalities have included sustainable rural tourism measures in local development strategies, by the end of JP. -Organizational Capacity Development: 500 individuals trained via 20 workshops, representing at least 50 different tourism and rural stakeholder entities trained on organizational subjects by end of JP. Marketing & Promotion: local tourism stakeholders trained via 15 workshops on product development issues, marketing and promotion in Years 2 and 3 of the JP. -Energy Efficiency & Alternative Energy: 300 individuals via 12 workshops trained representing at least 100 different organizations, architecture & engineering firms, construction firms, and public officials trained on energy efficiency and alternative energy technical matters and funding opportunities by end of JP. -Rural Tourism-Oriented Networks: Twelve groups of regional tourism-oriented producers and processors provide a common touristic offer (integrating local services and products) by end of JP. -Product Development: Local tourism stakeholders actively participating in Product Development discussions through the TGOs and are trained to become active stakeholders in Tourism Master Plan Implementation. -Sustainable Resource Management: 300 individuals trained via 12 workshops, representing at least 100 different tourism stakeholders in sustainable resource management by end of JP. - Agriculture Quality Standards Training: 600 producers, farmers and processors trained in agriculture quality production and standards. | 11 regional trainings on Standards for processing meat, fruits and vegetables in rural households; culinary standards and techniques for rural tourism providers with about 176 trainees will help in adjusting to new regulations which will be introduced during Serbian accession to the EU. Study Tour to Slovenia on child tourism for local and national partners conducted. 14 stakeholders visited 17 destinations and processed the lessons learnt through workshops. Workshops regarding the inclusion of tourism in municipal strategies were organised in 2 regions, for municipal structure. In total 20 participants were actively took part on these two workshops. | Training attendance records, tabulated & recorded in M&E system. Training participants profile information collected. Copies of project payments and delivery receipts. Reports on two workshops | Annual Monitoring | Contributing Agencies: UNWTO, FAO, UNEP, UNICEF Partners: MERD & MAFWM, by output level. Programme activities, results, participation, information tracking: UNDP | Risks Political and/or economic shocks shift the attention of policy-makers away from tourism & rural development. Delays due to contracting procedures or performance. Local institutions fail to agree or cooperate on activities, or fail to honour prior commitments. Turnover of local government officials and civil servants results in delays. Private, public and/or civil society sectors are reluctant to cooperate. Governments see rural tourism purely as tool for diversification of rural economy, failing to recognize it as local development tool. Assumptions No major institutional change of any partner occurs during the implementation of the project. No changes in roles and responsibilities of partners, contributing local organizations |
| 2.2 . Tourism governance structures enhanced in target regions through dedicated organizations, pilot projects, investment promotion | -Number of TGOs established and trained based on needs assessment and with attention to gender and PPP. -Amount of public and private investment leveraged through JP pilot projects and investments. -Guidelines/standards for schools and tourism service providers catering for children submitted to the Ministry of Education for endorsement by the end of JP. -Number of pilot projects financed and functional over life of project. -Number of pilot projects supported through the JP, which are accessible to persons with disabilities. -Number of pilot projects supported through the JP, which specify rural women as beneficiary. | Rural Development Network is existing & functional. -Tourism Governance Organizations do not exist. Statistical offices of the republic of Serbia ,Local tourism organisation and regional rural development network offices are limited to obtaining the data needed | - Tourism Governance Organizations (TGOs) in four regions (one per target region) established throughout JP through expert support, while engaging local stakeholders. -Child-Related Tourism Supply & Demand: Guidelines/standards for schools and tourism service providers catering for children submitted to the Ministry of Education for endorsement by the end of JP. -Investment Forum: One national investment forum organized in Year 2 of JP. Joint UN Fund for Sustainable Rural Tourism -Thematic window on Diversification of Rural Economy through Tourism: 23 projects for developing rural tourist sites, products & services supported by the end of JP. -Thematic window on Tourism Destination Development: Basic tourism services, Development of attractions, specific niche products and tourism clusters in target regions enhanced, in the last two years of JP. -Thematic Window on Active-Learning Tourism Investments: 4 tourist sites developed through child- , family-, and school-centred tourism | -Tourism governance organizations are well-defined in the first draft of the Master plan since it evaluates the potentials in each existing structure and proposes new mechanism for support tourism to be established. Grants scheme for new call for grants is currently being prepared for launching in the second half of 2011. Draft Guidelines for tourism service providers completed. Active Learning Tourism Grant Scheme developed and promoted. Minimum 6 child, youth and/or family tourism will be developed with max 120.000 USD | Training attendance records, tabulated & recorded in M&E system. Copies of project payments and delivery receipts. | Annual Monitoring | Contributing Agencies: UNWTO, FAO, UNEP, UNICEF Partners: MERD & MATFWM Programme activities, results, participation, information tracking: UNDP |  |

c. Joint Programme Results Framework with financial information

This table refers to the cumulative financial progress of the joint programme implementation at the end of the semester. The financial figures from the inception of the programme to date accumulated (including all cumulative yearly disbursements). It is meant to be an update of your Results Framework included in your original programme document. You should provide a table for each output. 
Definitions on financial categories
• Total amount planned for the JP: Complete allocated budget for the entire duration of the JP.
• Estimated total amount committed: This category includes all amount committed and disbursed to date.
• Estimated total amount disbursed: this category includes only funds disbursed, that have been spent to date.
• Estimated % delivery rate: Funds disbursed over funds transferred to date.
• Estimated % delivery rate: Funds disbursed over funds transferred to date.

| JP Outcome 1: Legal and policy framework for supporting diversification of rural economy through tourism is developed and contributes to the achievement of Millennium Development Goals. |
| --- |
| Please highlight the rate of delivery for each joint programme’s output: |
| a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 f. More than 80% |
| Output | Activity | YEAR 2 | UN Agency | Responsible Party | Source of Funding | Budget Description | Amount Planned | Estimated amount Committed | Estimated Amount Disbursed | Estimated % Delivery rate |
|  |  | Q1 | Q2 |  |  |  |  |  |  |  |  |
| 1.1. National Rural Tourism Master Plan for Serbia developed and submitted to the Government. |
| 1.1.1 National Rural Tourism Master Plan for Serbia developed and submitted to the Government. *Point 1.1.1 sumerizes all financial data regarding UNWTO activities! | 1.1.1.a. In cooperation with FAO and lead ministries, establish an inter-ministerial working group, with a sub-group for development of National Rural Tourism Master Plan. |  |  | UNWTO | MERD | MDG-F | *Point 1.1.1 summarizes all financial data regarding UNWTO activities! | 602,255 | 130,524 | 143,161 | 24% |
|  | 1.1.1.b. Conduct permanent information and decision making activities with all stakeholders and ensure incorporation of studies by other participating UN agencies (1.1.2-4 and 1.2.1). |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.1.c. Develop specific programs within the National Rural Tourism Master Plan in the following fields: analyzing, sustaining, knowing, excelling, innovating, promoting and governing. |  |  |  |  |  |  |  |  |  |  |
|  | 1.1.1.d. Make formal official presentation of National Rural Tourism Master Plan |  |  |  |  |  |  |  |  |  |  |
| 1.1.3. National Study on Sustainable Tourism: Provide environmental information for the development of the National Rural Tourism Master Plan, including recommendations following first draft of this Policy, within the first 12 months of JP. | 1.1.3 a.. Conduct a National Environmental Study to assess capacity by collecting and using locally available environmental information/data. |  |  | UNEP | MERD | MDG-F |  | 0 | 0 | 0 | 76% |
|  | 1.1.3.b. Identify potential impact of National Rural Tourism Master Plan by examining: i) potential impacts on ecosystems from proposed options; ii) energy consumption & efficiency; iii) buffer zone management; iv) other environmental impacts. |  |  |  |  |  |  | 21,400 | 0 | 16,276 |  |
|  | Total | 21,400 | 0 | 16,276 | 76% |
| 1.2. Rural Development Program Planning: Rural Development Program planning is mainstreamed in Serbia's national policies; National Program for Rural Development for IPARD Axes 2 & 3 developed & submitted to Government. |
| 1.2.1. IPARD National Agriculture & Rural Development Program (2010-2013): Strategic guidelines for inclusion of rural tourism & related activities to Axes 2 & 3 developed, facilitating Serbia’s access to EC IPARD Axis 2 & 3 funds. | 1.2.1.a. In cooperation with UNWTO and MoERD, establish an inter-ministerial working group, with a sub-group for elaboration of National Rural Development Programme. |  |  | FAO | MOA | MDG-F |  | 64,200 | 24,082 | 40,026 | 62% |
|  | 1.2.1.b. Identify & engage expert group of outside & supporting resources to complete program development, including studies undertaken as part of Output 1.1. |  |  |  |  |  |  | 0 | 0 | 0 |  |
|  | 1.2.1.c. Conduct assessment & prepare plan in accordance with requirements, including detailed description of Axis 2 and 3 (measures related to rural economy diversification with emphasize on rural tourism and measures related to preparation of measures to support sustainable management of the natural resources and environmental protection in rural areas). |  |  |  |  |  |  | 0 | 0 | 0 |  |
|  | Total | 64,200 | 24,082 | 40,026 | 62% |
| 1.3. Investment Mainstreaming: Sustainable tourism investments mainstreamed in Serbia's national policies. |
| 1.3.1. Public Investments toward Rural Tourism Master Plan: Serbia public sector commits minimum $75 million in rural tourism initiatives and supporting infrastructure in line with Rural Tourism Master Plan by end of JP. | 1.3.1.a. Identify public, private and external resources that can leverage one another in rural tourism initiatives. |  |  | UNDP | MERD | MDG-F |  | 45,000 | 39,950 | 0 | 0% |
|  | 1.3.1.b. Engage with all relevant line ministries to promote public investments that are in line with Rural Tourism Master Plan and environmentally sustainable. |  |  |  |  |  |  |  |  |  |  |
| 1.3.2. Public-Private Partnership Guidelines: Functional guidelines for successful public-private partnerships developed and institutionalized, evidenced by completion of at least six PPP initiatives by end of JP. | 1.3.2.a. Produce strategy guidelines for securing and leveraging public-private partnerships |  |  | UNDP | MERD | MDG-F |  | 0 | 0 | 0 | 44% |
|  | 1.3.2.b. Provide strategic investment training for target group of public decision-makers and private investors. |  |  |  |  |  |  | 55,000 | 35,320 | 24,464 |  |
|  | 1.3.2.c. Support and monitor at least six PPP initiatives in rural tourism. |  |  |  |  |  |  |  |  |  |  |
| 1.3.3. SIFT Network: National focal point established for Sustainable Investment and Finance in Tourism (SIFT) Network. | 1.3.3.a. Identify organizations and/or individuals to serve as SIFT focal point and/or working group members. |  |  | UNEP | MERD | MDG-F |  | 0 | 0 | 0 | 72% |
|  | 1.3.3.b. Provide training to focal point or working group on benefits and expectations as member of SIFT network. |  |  |  |  |  |  | 6,318 | 0 | 13,317 |  |
|  | 1.3.3.c. Engage SIFT network to share best practices, match destination demand with financial resources, & build network capacity. |  |  |  |  |  |  | 17,222 | 0 | 3,611 |  |
|  | Total | 123,540 | 75,270 | 41,392 | 34% |
| JP Outcome 2.: Local rural tourism and support industries are better linked and organized; local stakeholders’ capacity is improved for delivering services and products in line with national strategies. |
| Please highlight the rate of delivery for each joint programme’s output: |
| a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 f. More than 80% |
| Output | Activity | YEAR 2 | UN Agency | Responsible Party | Source of Funding | Budget Description | Amount Planned | Estimated amount Committed | Estimated Amount Disbursed | Estimated % Delivery rate |
|  |  | Q1 | Q2 |  |  |  |  |  |  |  |  |
| 2.1. Capacity developed for sustainable rural tourism in order to enhance rural development |
| 2.1.1. Local Action Groups: Capacity of public, private and civil society sector stakeholders strengthened to enable establishment of six Local Action Groups (representing 10,000-100,000 citizens) and develop local rural development strategies, by end of JP. | 2.1.1.a. Identify resources and existing initiatives to serve as possible foundation for LAGs. |  |  | UNDP | MOA | MDG-F |  | 176,982 | 106,517 | 75,140 | 42% |
|  | 2.1.1.b. Using the EU's Leader approach, mobilize public, private & civil society actors to engage in Local Action Groups and support them in increasing benefits for rural population from available financing & donation instruments. |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.1.c. Build capacity & cohesiveness of Local Action Groups through trainings suited to target region and expert support, including to strengthen the role of women in LAGs. |  |  |  |  |  |  |  |  |  |  |
| 2.1.2. Rural Development Network: Capacity of national Rural Development Network strengthened in the target regions to lead development and facilitation of Local Action Groups, independently lobby for development initiatives and secure resources for regional development by end of JP. | 2.1.2.a. Provide capacity building and Training-of-Trainers for RDN to serve as outreach & implementation tool to i) promote Ministry programs & IPARD; ii) support and mentor local NGOs and other groups in local initiatives and proposal development; iii) facilitate and promote local partnerships; iv) motivate and mobilize local partners for LAG development; v) provide inputs for policy changes at the national level. |  |  | FAO | MOA | MDG-F |  | 26,750 | 13,665 | 6,000 | 22% |
| 2.1.3. Local planning: All 19 target municipalities have included sustainable rural tourism measures in local development strategies, by the end of JP. | 2.1.3.a. Follow-up with target municipalities on the implementation of gender-responsive local development strategies and provide expert support for inclusion of sustainable rural tourism initiatives where appropriate. |  |  | UNDP | MOA | MDG-F |  | 50,000 | 50,000 | 0 | 0% |
| 2.1.4. Organizational Capacity Development: 500 individuals trained via 20 workshops, representing at least 50 different tourism and rural stakeholder entities trained on organizational subjects by end of JP. | 2.1.4.a. In cooperation with UNWTO (activity 2.1.5.a), survey RDN, LAGs, DMOs, and agriculture & non-agriculture producer groups on organizational capacity and needs. |  |  | FAO | MOA | MDG-F |  | 2,284 | 1,134 | 1,134 | 68% |
|  | 2.1.4.b. Provide targeted training, technical assistance and mentoring on topics of organizational management; project management; fundraising; proposal development and advocacy; product creation & management; competitiveness, marketing & commercialization. |  |  |  |  |  |  | 9,630 | 2,630 | 7,000 |  |
| 2.1.5. Marketing & Promotion: local tourism stakeholders trained via 15 workshops on product development issues, marketing and promotion in Years 2 and 3 of the JP. *all financial data contained in point 1.1.1 | 2.1.5.a. Local Stakeholders helping designing strategic marketing (including positioning issues) and collaborating in promotional campaigns |  |  | UNWTO | MERD | MDG-F | *Point 1.1.1 sumerizes all financial data regarding UNWTO activities! |  |  |  | n/a |
|  | 2.1.5.b. Provide training to targeted stakeholders and organizations, especially pilot project stakeholders, in rural tourism quality standards. |  |  |  |  |  |  |  |  |  |  |
| 2.1.6. Energy Efficiency & Alternative Energy: 300 individuals trained via 12 workshops, representing at least 100 different organizations, architecture & engineering firms, construction firms, and public officials trained on energy efficiency and alternative energy technical matters and funding opportunities by end of JP. | 2.1.6.a. Assess regional initiatives in energy efficiency and alternative energy, including potential for improvements in this field, both locally and through funding opportunities, and provide technical input for FAO activity 2.2.7. |  |  | UNEP | MERD | MDG-F |  | 13,910 | 0 | 0 | 0% |
|  | 2.1.6.b. Deliver training to building and residence designers, construction firms, public officials, tourism providers and other interested stakeholders. |  |  |  |  |  |  | 25,160 | 0 | 0 |  |
| 2.1.7. Rural Tourism-Oriented Networks: Twelve groups of regional tourism-oriented producers and processors provide a common touristic offer (integrating local services and products) by end of JP.2011 | 2.1.7.a. Develop database of agriculture and non-agriculture products important for tourism development in targeted geographic regions. |  |  | FAO | MOA | MDG-F |  | 0 | 0 | 0 | 22% |
|  | 2.1.7.b. Conduct market analysis of traditional and regional products and craft markets in targeted regions. |  |  |  |  |  |  | 0 | 0 | 0 |  |
|  | 2.1.7.c. Support producer groups through training, capacity building and organizational development activities, including branding of products and regions. |  |  |  |  |  |  | 21,400 | 1,400 | 1,000 |  |
|  | 2.1.7.d. Organize networking events of tourism and agriculture stakeholders (women & men) in pilot project areas to improve linkages and strengthen local and regional brands and present themselves together with regional tourism offer on the national and international tourism markets. |  |  |  |  |  |  | 65,454 | 4,358 | 18,000 |  |
| 2.1.8. Product Development: Local tourism stakeholders actively participating in Product Development discussions through the TGOs and are trained to become active stakeholders in Tourism Master Plan Implementation 2011 | 2.1.8.a. Facilitate active participation of local stakeholders in fine-tuning of National Rural Tourism Master Plan through established TGOs, especially with regards to product development. |  |  | UNWTO | MERD | MDG-F | *Point 1.1.1 sumerizes all financial data regarding UNWTO activities! |  |  |  | n/a |
|  | 2.1.8.b. Provide training through workshops and seminars, engaging when necessary UNWTO experts and delegates of steering group |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.8.c. In coordination with all agencies, include strategies and management techniques for environmental and cultural issues within the National Rural Tourism Master Plan. |  |  |  |  |  |  |  |  |  |  |
|  | 2.1.8.d. Address all issues regarding quality and consumer satisfaction through the establishment of quality circles and expertise as needed. |  |  |  |  |  |  |  |  |  |  |
| 2.1.9. Sustainable Resource Management: 300 individuals trained via 12 workshops, representing at least 100 different tourism stakeholders in sustainable resource management by end of JP.2011 | 2.1.9.a. Identify tourism stakeholders, including destination managers, tourism offices, park & nature reserve managers, RDN, DMOs, LAGs, private companies, and local officials who are impacted by improved (or lack of) sustainable resource management principles. |  |  | UNEP | MOA | MDG-F |  | 0 | 0 | 0 | 32% |
|  | 2.1.9.b. Adapt UNEP Sustainable Management Training for delivery in targeted Serbian regions; provide training to identified stakeholders. |  |  |  |  |  |  | 28,287 | 0 | 0 |  |
|  | 2.1.9.c. Conduct environmental studies of the target regions examining that aspect of rural tourism sustainability, and present at trainings. |  |  |  |  |  |  | 36,872 | 0 | 20,986 |  |
| 2.1.10. Agriculture Quality Standards Training: 600 producers, farmers and processors trained via 25 workshops in agriculture quality production and standards. | 2.1.10.a. Provide 4 Training-of-Trainers (one in each target region) and coordination for National Agriculture Extension Services, Cooperative Union of Serbia and Rural Development Network in organic production and ECEAT certification. |  |  | FAO | MOA | MDG-F |  | 0 | 0 | 0 | 12% |
|  | 2.1.10.b. Train formal and informal groups of farmers in resource-based planning, quality and production standards, HACCP, GlobalGAP quality standards & certification. |  |  |  |  |  |  | 53,500 | 13,552 | 6,520 |  |
|  | Total | 510,229 | 193,256 | 135,780 | 27% |
| 2.2. Tourism governance structures enhanced in target regions through dedicated organizations, pilot projects, investment promotion |
| 2.2.1. Tourism Governance Organizations (TGOs) in four regions (one per target region) established throughout JP through expert support, while engaging local stakeholders. | 2.2.1.a. Assess the needs of the Tourism Governance Organizations in the target regions, including possible models and existing capacities (namely the Local Action Groups and local tourism organizations) |  |  | UNWTO | MERD | MDG-F | *Point 1.1.1 sumerizes all financial data regarding UNWTO activities! |  |  |  | n/a |
|  | 2.2.1.b. Establish Tourism Governance Organizations according to results of Assessment in the target regions. |  |  |  |  |  |  |  |  |  |  |
| 2.2.2. Child-Related Tourism Supply & Demand: Guidelines/standards for schools and tourism service providers catering for children submitted to the Ministry of Education for endorsement by the end of JP. | 2.2.2.a. Provide input, through presentations and facilitation, into workshops, seminars & planning processes organized with LAGs, RDN and DMOs on child-related tourism issues. |  |  | UNICEF | MERD | MDG-F |  | 16,573 | 10,878 | 10,878 | 44% |
|  | 2.2.2.b. Promote guidelines for rural tourism service providers and schools on catering to children and pupils. |  |  |  |  |  |  | 21,984 | 12,611 | 6,191 |  |
| 2.2.3. Investment Forum: One national investment forum organized in Year 2 of JP. | 2.2.3.a. Identify existing initiatives which can collaborate in the Investment Forum organization (Tourism Fair, NALED, Standing Conference of Towns & Municipalities, Municipal Investment Forum). |  |  | UNEP | MERD | MDG-F |  | 0 | 0 | 0 | 0% |
|  | 2.2.3.b. Organize the Investment Forum. |  |  |  |  |  |  | 43,870 | 0 | 0 |  |
| 2.2.4. Joint UN Fund for Sustainable Rural Tourism / Thematic window on Diversification of Rural Economy through Tourism: 23 projects for developing rural tourist sites, products & services supported by the end of JP. | 2.2.4.a. In cooperation with participating UN agencies, support Local Action Groups in defining priority interventions and designing the ToR for this Thematic Window, to be approved by PMC. |  |  | FAO | MOA | MDG-F |  | 53,500 | 8,871 | 9,471 | 27% |
|  | 2.2.4.b. LAG subcommittees collect & evaluate proposals in (i) Integrated rural tourism and agriculture development on the rural community level; (ii) Conservation & maintenance of traditional rural cultural & natural heritage for integrated rural and rural tourism development; (iii) Diversification and upgrade of the production of food and non-food products and activities for local/regional rural tourist markets. |  |  |  |  |  |  | 317,253 | 44,595 | 91,710 |  |
| 2.2.5. Joint UN Fund for Sustainable Rural Tourism / Thematic window on Tourism Destination Development: Basic tourism services, Development of attractions, specific niche products and tourism clusters in target regions enhanced, in the last two years of JP. (Average project investment $10,000) | 2.2.5.a. Support the development of basic tourism services such as accommodation, food and beverage, reservation systems and tourism offices. |  |  | UNWTO | MERD | MDG-F | *Point 1.1.1 sumerizes all financial data regarding UNWTO activities! |  |  |  | n/a |
|  | 2.2.5.b. Support the development of attractions (tourism products such as tourism cultural activities, activities in nature, interpretation, etc.) |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.5.c. Support the development of specific attractive niche products. |  |  |  |  |  |  |  |  |  |  |
|  | 2.2.5.d. Complete all aspects of tourism cluster development. |  |  |  |  |  |  |  |  |  |  |
| 2.2.6. Joint UN Fund for Sustainable Rural Tourism Fund / Thematic Window on Active-Learning Tourism Investments: 20 tourist sites developed through 8 child- , family-, and school-centered tourism competitions organized (4 per year, 2 in Lower Danube region due to higher number of municipalities; top 3 awards per competition). | 2.2.6.a. Establish criteria for school-centered rural tourism activities to be Ministry of Education-approved course curricula. |  |  | UNICEF | MERD | MDG-F |  | 32,100 | 31,986 | 31,986 | 24% |
|  | 2.2.6.b. Organize school committees of students & teachers in the 4 regions; assess regional rural tourism sites & opportunities for active learning elements & organized school field trips. |  |  |  |  |  |  | 5,350 | 5,350 | 2,889 |  |
|  | 2.2.6.c. Conduct training and workshop on active learning and child-centered tourism to tourism stakeholders; stakeholders form consortia to compete for active learning programs. |  |  |  |  |  |  | 21,400 | 16,085 | 11,908 |  |
|  | 2.2.6.d. Presentations & competition organized; students and teachers vote for winning sites and programs; winning competitors work with UNICEF to detail and install child-centered and active-learning components. |  |  |  |  |  |  | 0 | 0 | 0 |  |
|  | 2.2.6.e. Announce active learning tourism grant scheme, based on the findings, results and framework designed in year 1; Select the winning sites and programmes; winning competitors work with UNICEF to detail and install child-centered and active-learning components. Support the implementation and realization of the projects |  |  |  |  |  |  | 133,750 | 5,350 | 0 |  |
|  | Total | 645,780 | 135,726 | 165,033 | 26% |
| Joint Programme Management, Coordination and Monitoring & Evaluation |
| Please highlight the rate of delivery for each joint programme’s output: |
| a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 f. More than 80% |
| Output | Activity | YEAR 2 | UN Agency | Responsible Party | Source of Funding | Budget Description | Amount Planned | Estimated amount Committed | Estimated Amount Disbursed | Estimated % Delivery rate |
|  |  | Q1 | Q2 |  |  |  |  |  |  |  |  |
| JP Management & Coordination |
| A functioning and coordinated Program Implementation Unit (PIU) is established and operating throughout the life of the JP. | Establish a Program Implementation Unit (PIU) under direction of Program Manager. Operational functioning of the office. |  |  | UNDP | MOA/MERD | MDG-F |  | 160,390 | 90,959 | 66,296 | 41% |
| Baseline Assessment The content posted to the right in this row represents key pieces of knowledge or data that are either useful or necessary to gain prior to undertaking activities. Objective 1 generally includes the collection of key gender disaggregated data as part of National Rural Tourism Master Plan creation; therefore, this information applies primarily to Objective 2. | Stakeholder Capacity & Training Needs Local Action Group Members Existing Groups & Organizational Capacity Local Tourism Investment Priorities Municipal Capacity Index Assessment Quality Rating System Outlined/Identified Beds & Overnights (previous period) Destination Visits & Current Market Socio-Economic Indicators, including the Role and Benefits Women and Men in this Sector |  |  | UNDP | MOA/MERD | MDG-F |  | 67,712 | 48,160 | 5,320 | 8% |
| Monitoring & Evaluation System An information-management M&E system is developed and used to assess the performance of the program in terms of relevance, effectiveness, efficiency and impact by the end of the first six months. | a. Design M&E system requirements for each outcome of the JP. b. Conduct regular program performance monitoring to measure relevance and efficiency; input findings into the JP implementation system. c. Present monitoring & evaluation information back to key stakeholders and partners to improve programming. |  |  |  |  |  |  |  |  |  |  |
|  | Total | 228,102 | 139,119 | 71,616 | 31% |

SECTION II: Joint Programme Progress

The second section of the report is intended to shed light on the major advances and difficulties of the Joint Programme. It also aims to collect information on two important objectives that all joint programmes are contributing towards (interagency work, delivering as One and Development effectiveness as described by the Paris Declaration and the Accra Action Agenda).

- Narrative on progress, obstacles and contingency measures

- Please provide a brief overall assessment (250 words) of the extent to which the joint programme components are progressing in relation to expected outcomes and outputs, as well as any measures taken for the sustainability of the joint programme during the reporting period. Please, provide examples if relevant. Try to describe facts avoiding interpretations or personal opinions.

Are there difficulties in the implementation? What are the causes of these difficulties? Please check the most suitable option

b.

UN agency Coordination

Coordination with Government

Coordination within the Government (s)

Administrative (Procurement, etc) /Financial (management of funds, availability, budget revision, etc)

Management: 1. Activity and output management 2. Governance/Decision making (PMC/NSC) 4. Accountability

Joint Programme design

c.

External to the Joint Programme (risks and assumptions, elections, natural disaster, social unrest, etc)

Other, please specify:  Global Financial Crisis was not expected, which had a negative impact on the tourism

Please, briefly describe (250 words) the current difficulties the Joint Programme is facing. Refer only to progress in relation to the planned in the Joint Program Document. Try to describe facts avoiding interpretations or personal opinions.

- Coordination with Government is no longer a cause for difficulty in the project.  Still, national implementing partners MoERD and NTOS strongly requested from Programme Implementation Unit to increase the visibility of the Programme

- Key Statistical data are insufficient for effective monitoring of programme implementation. The Official data from the Serbian Statistical Office are not disaggregated and need to be updated for 2009 and 2010.  The real picture on the number of rural tourism service providers, the income generated from the tourism and the levels of partnerships will be therefore collected and analysed.

Please, briefly explain (250 words) the actions that are or will be taken to eliminate or mitigate the difficulties (internal and external referred B+C).

- Inter-Agency Coordination and Delivering as One

The MDG-F Secretariat asks the office of the Resident Coordinator complete this subsection, briefly commenting on the joint programme, providing its perspective from within the broader country context. The aim is to collect relevant information on how the joint programme is contributing to inter-agency work and Delivering as One.

You will find some multiple choice questions where you can select the most appropriate to the case, text boxes to provide narrative information and 2 indicators on common processes and outputs to measure interagency coordination. These indicators have been already used to measure progress on the One UN pilot countries. Please, refer to the examples in the subsection to complete the information requested.

- Is the Joint Programme still in line with the UNDAF? Please check the relevant answer

Yes No

- If not, does the Joint Programme fit into the national strategies?

Yes No

If not, please explain:

What types of coordination mechanisms and decisions have been taken to ensure joint delivery?

Are different joint programmes in the country coordinating among themselves? Please reflect on these questions above and add any other relevant comments and examples if you consider it necessary:

Please provide the values for each category of the indicator table described below:

| Indicators | Baseline | Current Value | Means of Verification | Collection methods |
| --- | --- | --- | --- | --- |
| Number of managerial practices (financial, procurement, etc) implemented jointly by the UN implementing agencies for MDG-F JPs. | 2 |  |  | Online submissions |
| Number of joint analytical work (studies, diagnostic) undertaken jointly by UN implementing agencies for MDG-F JPs. | Strategic rural tourism development document for Serbia |  | Published on the MoERD website | Surveys , interviews |
| Number of joint missions undertaken jointly by UN implementing agencies for MDG-F JPs. | Regional Conferences :1 Workshops: 8 Regional events : 4 |  | Internal reports | Internal surveys |

Please provide additional information to substantiate the indicators value (150 words). Try to

describe qualitative and quantitative facts avoiding interpretations or personal opinions.

- Development Effectiveness: Paris Declaration and Accra Agenda for Action

This subsection seeks to gather relevant information on how the joint programme is fostering the principles for aid effectiveness by having appropriate ownership, alignment, harmonization and mutual accountability in the last 6 months of implementation.

You will find some multiple choice questions where you can select the most appropriate to the case, text boxes to provide narrative information and 2 indicators on ownership ad alignment. These indicators have been used extensively to measure progress on the Paris Declaration. Please, refer to the examples in the subsection to complete the information requested.

Ownership: Partner countries exercise effective leadership over their development policies, and strategies and co-ordinate development actions

Are Government and other national implementation partners involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the government involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Who leads and/or chair the PMC and how many times have they met?

Institution leading and/or chairing the PMC: UNWTO, MoERD, FAO, alternating. Number of meetings: 6

Is civil society involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the civil society involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Are citizens involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities are citizens involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Where is the joint programme management unit seated?

National Government  Local Government  UN Agency  By itself  other, specify

Based on your previous answers, briefly describe the current situation of the government, civil society, private sector and citizens in relation of ownership, alignment and mutual accountability of the joint programmes, please, provide some examples. Try to describe facts avoiding interpretations or personal opinions.

- Communication and Advocacy

Has the JP articulated an advocacy & communication strategy that helps advance its policy objectives and development outcomes?  Please provide a brief explanation of the objectives, key elements and target audience of this strategy, if relevant, please attach (max. 250 words).

Yes   No

What concrete gains are the advocacy and communication efforts outlined in the JP and/or national strategy contributing towards achieving?

Increased awareness on MDG related issues amongst citizens and governments

Increased dialogue among citizens, civil society, local national government in relation to

development policy and practice

New/adopted policy and legislation that advance MDGs and related goals

Establishment and/or liaison with social networks to advance MDGs and related goals

Key moments/events of social mobilization that highlight issues

Media outreach and advocacy

What is the number and type of partnerships that have been established amongst different sectors of society to promote the achievement of the MDGs and related goals? Please explain.

Faith-based organizations     	Number

Social networks/coalitions    	Number

Local citizen groups                	Number 20

Private sector 		      	Number 17

Academic institutions              	Number 1

Media groups and journalist   	Number 7

Others (use box below)          	Number 19

What outreach activities do the programme implement to ensure that local citizens have adequate access to information on the programme and opportunities to actively participate?

Focus groups discussions

Household surveys

Use of local communication mediums such as radio, theatre groups, newspapers, etc

Open forum meetings

Capacity building/trainings

Others

Section III: Millennium Development Goals

- Millennium Development Goals

The MDG-F main objective is to contribute to progress to the attainment of the Millennium Development Goals worldwide. This subsection aims to capture   data and information on the joint programmes contribution to 1 or more Millennium Development Goals and targets.

| MDGs | Joint Programme Outcome 1 | MDG Target 1 and 7 | # Beneficiaries reached | MDG Indicators | JP Indicator |
| --- | --- | --- | --- | --- | --- |
| Goal 1:Halve the poverty rate Goal 7:Ensure environmental sustainability Goal 8: Develop global partnerships for development | Legal and policy framework for supporting diversification of rural economy through tourism is developed and contributes to achievement of Millennium Development Goals. | MDG 1. Eradicate Extreme Poverty & Hunger 1.1. Reduce unemployment rate of young by at least one third. 1.2. Reduce unemployment rate of persons with disabilities by at least 20%. 1.3. Reduce unemployment rate of women by over 45%. | Ministry of Education, Local Institutions, and Ministry of Agriculture, Trade, Forestry and Water Management | By 2015, reduce the unemployment rate by at least 50%/ Total unemployment rate (15-64) Youth unemployment rate (15-24 years) By 2015, reduce the poverty rate of the entire population/ Rural areas poverty rate | IPARD axis 2 and 3 measures prepared & submitted to MAFWM by end of JP. Number and type of organizational stakeholders & partners involved in development of IPARD. Representatives of rural women included in development IPARD. Number of workshops, presentations & coordination meetings held during preparation and adoption of IPARD. Serbia Rural Tourism Master Plan is submitted to the Government contributing to: 1. The creation of direct and indirect employment through the stimulation of the rural tourism sector. 2. Support and activation of the participation of women in rural areas in the tourism sector, thereby, creating employment and contributing to the reduction of unemployment. 3. Provision of training to provide skills for unemployed people to enter the tourism market. -Sustainable development principles included in the rural tourism Master Plan to ensure that the development of rural tourism protects natural resources and prevents their deterioration. -The revitalising of natural assets which are not being used to benefit the rural communities are encouraged through the Master Plan. - The principles of sustainability are key principles which underlie the development of any tourism activity related to rural tourism. -Where possible, the rural tourism Master Plan identifies ways in which energy can be used in an efficient way. Number and type of organizational stakeholders & partners involved in development of the Master Plan. Representatives of rural women included in the development of the Master Plan. Number of workshops, presentations and coordination meetings held during preparation and adoption of the Master Plan. All Input Assessments are completed, reviewed, presented and adopted in theMaster Plan. Specific niche products and services targeted for development. Resources and basic factors for tourism inventoried and evaluated. Necessary support structures identified and evaluated. Product Priority Plan agreed. Indicators continued: IPARD measures of the axis 2 and 3 related to rural tourism and submitted to the Government for adoption by end of JP. Number and type of organizational stakeholders & partners involved in development of Rural Development Program. Representatives of rural women included in development of specified IPARD measures. Number of workshops, presentations & coordination meetings held during preparation of specified IPARD measures. |
|  |  | MDG 7. Ensure Environmental Sustainability 7.1. Integrate sustainable development principles in national documents, stop the loss of natural resources and encourage their revitalization. 7.2. Adopt and implement national programmes, strategies & laws governing sustainable development and environmental protection in Republic of Serbia by 2015. 7.5. Increase energy efficiency & usage of renewable energy. |  | Integrate principles of sustainable development into country policies, stop the loss of environmental resources and encourage their revitalization/ Percentage of investments in the protection of the environment in relation to the achieved GDP (%) |  |
|  | Joint Programme Outcome 2 | MDG Target 8 |  |  |  |
|  | Local rural tourism and support industries are better linked and organized; and local stakeholders’ capacity is improved for delivering services and products in line with national strategies | MDG 8. Develop a Global Partnership for Development 8.1.Dynamic & sustainable GDP growth based on assumptions established by the National Investment Plan, the Strategy for Promotion and Development of Foreign Investments and the Strategy for Economic Development until 2012. 8.3Increase investments in human resource development by 70%. | National rural development network, Local self-authorities Local education institutions, Local Culture centres, Local tourism organisations, NGOs, representatives of the local farmers and entrepreneurs in tourism. | Dynamic and sustainable growth of gross domestic product /GDP Growth rate | Number of LAGs established and trained. Number of local development strategies that include rural tourism. Number and type of different training courses provided over life of JP. Number of TGOs established and trained based on needs assessment and with attention to gender and PPP. Amount of public and private investment leveraged through JP pilot projects and investments. Guidelines/standards for schools and tourism service providers catering for children submitted to the Ministry of Education for endorsement by the end of JP. Number of pilot projects financed and functional over life of project. Number of pilot projects supported through the JP which are accessible to persons with disabilities. Number of pilot projects supported through the JP which specify rural women as beneficiary. |

Additional Narrative comments

Please provide any relevant information and contributions of the programme to the MDGs, whether at national or local level.

Please provide other comments you would like to communicate to the MDG-F Secretariat:

Section 4: General Thematic Indicators

| Number of laws, policies or plans supported by the Joint Programme related to the advancement of enterprises (including agro industry) Applies Does not apply, if so, please move to section 2 |
| --- |
| Policies Laws Strategies | No. National No. National 1 No. National 1 | No. Local No. Local No. Local 13 |
| Please briefly provide some contextual information on the law, policy or plan and the country/municipality where it is going to be implemented (base line, stage of development and approval, potential impact of the policy): The development of the National Rural Tourism Master Plan will synchronize, clarify and unify all existing local plans and strategies. The creation of the IPARD plan will enable the access to IPARD resources. The Public Private Partnership Guidance will merge efforts of both Ministries in regards to creation of partnerships. 13 local, municipal and regional strategies will be revised with regards to tourism and gender. |
| Number of entrepreneurs and/or entities that the law, policy or strategy directly affects: |
| Farmers Entrepreneurs Micro enterprises Small enterprises Medium enterprises Large enterprises Financial providers Business development providers Other, please specify: Agricultural/Farming enterprises | Total No. 1.039.886 Total No. Total No. 300 Total No 350 Total No 20 Total No. Total No. Total No. Total No. 1.040.556 | No. Urban No. Urban No. Urban No. Urban No. Urban No. Urban No. Urban No. Urban No. Urban | No. Rural 1.039.886 No. Rural No. Rural 300 No. Rural 350 No. Rural 20 No. Rural No. Rural No. Rural No. Rural 1.040.556 |

| Please indicate the sector of focus of the law, policy or plan: Agro-industry Textile and manufacturing Trade Tourism Service industry across all sectors Other, please specify: | Comments: Joint programme introduced changes to the law on tourism |
| --- | --- |
| Government’s budget allocated to support enterprise development before the implementation of the Joint Programme: Government’s budget allocated to support enterprise development before the implementation of the Joint Programme: National budget : total public support for tourism in 2008 was EUR 46,608,133 (USD 68,380,302) and in 2009 it was EUR 21,702,759 (USD 30,221,390) Local budgets will be analyzed in 2011. | Comments: Due to the complexity of calculating public investments made by various government institutions, the amount included in the project document was an estimate, which has now been refined through detailed follow up. At the moment, tourism funds of local governments and projects that are implemented at the local level could not be taken into consideration and this remains as an activity for 2011. Also, the effects of the funds allocated from the government budget to rural tourism will be analyzed. It is very difficult to perform an analysis of budget support for 2010 at this moment without clear statistical data. |
| Variation (%) in the government’s budget allocated to programmes or policies on enterprise development from the beginning of the joint programme to present time: National budget: % Overall % Triggered by the Joint Programme |  |
| Local budget: % Overall % Triggered by the Joint Programme |  |

| 2.1 Type and number of programmes or interventions supported by the joint programme aiming to improve enterprises’ capacities, competitiveness, and / or access to market: Applies Does not apply, if so, please move forward to section 3 |
| --- |
| Technical assistance Business Development Services Access to finance Certification Other: | No.5 No. No. No. No. | Direct beneficiaries: Microenterprises SMEs Farms Cooperatives Other: _______ Microenterprises SMEs Farms Cooperatives Other: ________ Microenterprises SMEs Farms Cooperatives Other: ________ Microenterprises SMEs Farms Cooperatives Other: ________ Microenterprises SMEs Farms Cooperatives Other: ________ |
| 2.2 Total number of individuals directly assisted through those interventions: |
| Technical assistance Business Development Services Access to finance Certification Other: | Farmers 7 Entrepreneurs Employees Other: ________ 260 Farmers Entrepreneurs Employees Other: ________ Farmers Entrepreneurs Employees Other: ________ Farmers Entrepreneurs Employees Other: ________ Farmers Entrepreneurs Employees Other: ________ | Men 134 Women 126 Men Women Men Women Men Women Men Women |
| 2.3 What impacts have these interventions had? |
| Livelihoods improvement Increased level of production Increased level of commercialization Higher quality of products and services Access to new markets National International | Obtaining financing Aggregation and integration of small producers Increase profits Adoption of new technologies Other: |

| 3.1 Type and number of organizations created or strengthened Applies Does not apply |
| --- |
| Clusters Cooperatives Farmers Associations Business groups Other Rural development network, Tourist organizations High schools | No. No. No. No. No. 31 | Number of participating business: No. No. No. No. No. | Number of participating individuals: No. 523 men 313 women 210 No. men women No. men women No. men women No. men women |
| 3.2 Number of target enterprises who realize a financial benefit as a result of the joint programme’s contribution Applies Does not apply |
| Clusters Cooperatives Farmers Associations Business groups Other | No. No. No. No. No. | Number of participating business: No. No. No. No. No. | Number of participating individuals: No. men women No. men women No. men women No. men women No. men women |

# Footnotes

Please list all the partners actually working in the joint’s programme implementation, NGOs, Universities, etc

Please note that the figures provided here are estimates based on input from three participating agencies. The ‘formula’ used to calculate the total is as follows: National Institutions plus Local Institutions. The understanding is that Local Institutions include urban and local.

Please note that data on economic activities in the rural areas is limited. All figures are provided by the National Statistical Office. The figures for farmers relate to rural households and are based on information from 2002.  Other figures are from 2006.

For indicators 1.5 and 1.6 the Secretariat acknowledges the potential difficulties to obtain the information requested. Therefore, if not available,  please provide the best available estimate you have.

Small and Medium Enterprises as defined by national legislation.

# Text boxes

Progress in outcomes:

Joint Programme Outcome 1: Legal and policy framework for supporting diversification of rural economy through tourism is developed and contributes to achievement of Millennium Development Goals

Outcome 1.1: National Rural Tourism Master Plan for Serbia developed and submitted to the Government.

The National Sustainable Rural Tourism Master Plan for Serbia was approved by the Government of Serbia. It comprises a Diagnostic, Strategy, Action Plan and Implementation Plan.  All phases of the formulation and approval of the Master Plan were consultative with workshops organized at a national and regional level. Overall, more than 250 stakeholders attended those workshops including municipality representatives from all 19 municipalities, MOeRD, NTOS, UN partners agencies, local NGO’s and media. The Master Plan is currently being submitted to Parliament for ratification. The National Rural Tourism Master Plan contains the framework for the development of child, youth and family tourism. Child and youth related tourism models were promoted and presented in 2 rounds of workshops.

Outcome 1.2: Rural Development Program Planning: Rural Development Program planning is mainstreamed in Serbia’s National policies; National Program for Rural Development for IPARD Axes 2&3 developed and submitted to Government for adoption

The Study on Access to Services of Women and Children in Rural Areas was completed. The Study contains recommendations for national institutions dealing in key services, such as health, social care and education, as well as on other issues crucial for life quality in rural areas. The Study also contains an IPARD measure (Axis 3, measure code 302, Diversification and development of rural economic activities – sector services).  The Study will be published in August and promoted in target regions and on national level.

Outcome 1.3: Investment Mainstreaming: Sustainable tourism investments mainstreamed in Serbia’s national policies.

Review of public support to rural tourism at the national level for the period 2008 – 2010 providing important data for activities related to promotion of investment in 2011 was completed.  During 2011, the program will research all opportunities to enhance public support for the creation of partnerships in rural areas and the results of the research will become an essential part of the Guidance for Partnership Creation. The first step in this direction is the training „Investment and Financing in Sustainable Tourism“, which was held in Kladovo in March 30th/31st, 2011. The training was organized by the National Corporation for Tourism Development (NCTD), as SIFT focal point within JP. The participants in the training were representatives of Ministry of Economy and Regional Development, Ministry of Agriculture, Trade, Forestry and Water Management, municipalities involved in project (local economic development), local travel organizations and local SME representatives from tourism sector. The training was held as an interactive workshop and all participants showed a great interest for presentations of the speakers and had an active role in discussion during the training.

Progress in outcomes continued:

Joint Programme Outcome 2: Local rural tourism and support industries are better linked and organized; and local stakeholders’ capacity is improved to deliver services and products in line with national strategies

Outcome 2.1 Capacity developed for sustainable rural tourism in order to enhance rural tourism:

Over 300 rural tourism stakeholders were trained through workshops, practical trainings and coaching mainly concerning quality standards.

Awareness raising campaigns following regular programme activities helped in adjusting to the new regulations (concerning IPARD measures and LEADER concept) which will be introduced during Serbian accession to the EU. These trainings are particularly relevant for ensuring the implementation of food quality standards, which is a key aspect of the rural tourism offer in Serbia;

The study tour to Slovenia for the representatives of national institutions and local stakeholders was conducted from June 13 to 19, 2011. 14 participants and three UN representatives visited 17 child, youth and family destinations dealing in educational tourism. After active tour and workshops during the trip, the follow-up process was initiated immediately after the Tour so that the participants would continue developing active learning tourism models in the four target regions.

A Memorandum of Understanding was officially signed by the EU-funded ’LEADER initiative Serbia’ and the UN JP ’Sustainable Tourism for Rural Development’ in Kladovo on 5th July 2011, ensuring strong cooperation in the implementation of the LEADER approach and joint working towards rural development in Serbia. The two programmes – in close cooperation with the national partners – conducted two training seminars (Kladovo and Divcibare) on the “LEADER Approach and Methodology with Special Focus on Local Action Groups”, which saw the participation of more than 70 key local stakeholders from the public, private and civil sectors (http://rs.one.un.org/strd/media-room/186/).

Outcome 2.2 Tourism governance structures enhanced in target regions through dedicated organizations, pilot projects and investment promotions.

Tourism governance organizations are well-defined in the Master plan since it evaluates the potentials in each existing structure and proposes new mechanism for support tourism to be established.

The Guidelines for tourism service providers catering to children and pupils was drafted. The Guidelines defines key categories in child, youth and family tourism and represents the first document of this kind in Serbia. The document opened numerous questions and represents a good basis for constant scaling up.

The Active Learning Tourism Grant Scheme is prepared. Its aim is to pilot educational tourism for children, youth and their families through minimum 4 projects. With the amount of 120.000 USD available, maximum funding per project proposal of cca 20.000 USD and enough quality applications, minimum six projects can be supported. The community and key stakeholders are well acquainted with the overall concept which is a new tourism niche in Serbia.

Progress in Outputs continued:

Governance and Coordination:

- The PIU retreat was held in April 2011. During the retreat, the participating agencies reflected on 2010 and lessons learnt, discussed the detailed plan of activities and defined priorities for 2011.

- The sixth PMC meeting was held on 08 April 2011 with the participation of all UN agencies.

- PIU meetings are held regularly and provide an effective mechanism to jointly plan and execute activities.

- JP contributes to the monthly NSC letter, which the RC sends to NSC members and participating agencies and national partners, to share information in regards to progress made.

Joint Programme Visibility:

- Programme Communication and Advocacy Strategy created and implemented.

- The programme was promoted on several occasions such Belgrade Tourism Fair, Danube Floating Conference and through printed and electronic media.

- In addition to the media coverage of the visibility events, news pieces on these visibility events have been written and posted on UN Serbia websites.

- Visual identity tools such as JP logo, letterhead, PowerPoint presentation have been developed and are used by the team and partners.

- 4 regional workshops were organized mainly in rural tourism households, together with UNICEF and UNWTO. (Promotion of upcoming activities in 2011).

- The programme was promoted during the event PREPARE Gathering 2011 that took place from 29th June until 1st July in Zlatibor, Serbia. PREPARE international gathering is the main annual event of the Pan-European PREPARE network, organized each year in different country and region. The gathering was an important opportunity to discover Serbia's rural life, to exchange experiences from across Europe and to contribute to integrated and sustainable development of rural areas.

- The Tourism Fair and local stakeholders presented during the fair rural tourism potentials from their regions. All the participating agencies and national partners promoted the programme, its key components and rural tourism in general at the International Tourism Fair in Belgrade from February 24 to February 27, 2011.

Joint Programme Management, Implementation & Operations:

- All agencies actively participated in the submission of the Master Plan. Relevant inputs were exchanged between teams working on the Master Plan and on IPARD measures including studies on the importance of rural tourism for small farming sector and analysis of local products of importance for rural tourism and included into the Master Plan.

- 4 regional rural development centres organised capacity building through trainings and mentoring for strategic and action planning.

- The cooperation with SIFT focal point progresses well.

- Regional environmental studies initiated to explore opportunities and challenges and examine the sustainability of tourism development in target regions.

- Study on access to services in rural areas, barriers to access and potential solutions is complete.

- Revision of local strategies in terms of inclusion of rural tourism initiatives and gender-responsive aspects finalised and work on introducing proposed recommendations begun.

- Joint Call for Proposals for Diversification of Rural Economy through Tourism being prepared.

- Framework for the development and stimulation of child-related tourism is shaped through the documents (Master Plan and the guidelines for tourism service providers catering to children and pupils) and prepared for dissemination.

Monitoring and Evaluation:

- Baseline analysis report has been delivered. The company for collecting the data needed for Monitoring and evaluation of whole JP is contracted. Key objective is to collect data for M&E and to provide data to national stakeholders for future planning and policies for rural development purposes. The key data need to be gathered: Estimate the income generated from rural tourism in 19 target municipalities during 2009 and 2010, Identify the number and quality of functional partnerships for rural tourism in 19 target municipalities until 2010 and analyze the effects that the public investment (national, local and international) had on diversification of economy towards rural tourism in 19 target municipalities.

- A report on conducted  surveys  related to income generation from rural tourism in 19 target municipalities.

Measures taken for the sustainability of the joint programme:

National and Local Partner Ownership:

The representatives of the national partners have actively participated in organised workshops;  collecting the data for policy documents; participated in all PMCs and additional meetings have been organized to share and include national partners in decision-making and implementation processes.

Rural Development Network (RDN):

The Rural Development Network (RDN) has been implemented following actions: organisation of workshops and collect the data for policy documents. RDN also actively participated in the development of a stakeholder database for the target regions.

Local tourism organisations and other local institutions: Key local tourism organizations take active part in data gathering and in participation on most important educational events such as EIAT conference, Green Hotels Forum, International Rural Tourism Congress, International ENAT conference, International Belgrade Tourism fair, Danube floating conference, as well at national and local tourism events.

The decline in living standards will negatively affect tourism in Serbia, this will be demonstrated in 2010 statistics:

According GFK extensive regional survey

- The 60 %of the population in Serbia had decline in living standards in Serbia.

- The 20 % of them had a drastic drop in standards.

.

Given that the Joint Programme was launched in the midst of the economic crisis and faces unforeseen challenges, additional effort and creativity is required to adapt its activities to the difficult economic circumstances.

b) Actions regarding Coordination with Government and Joint Programme design challenges:

1. Timely and extensive dissemination of information is the key for a positive change:

- Exchange of ideas at the early planning stage of the planned activities.

- Factsheet updates (summary information products) circulated to the national partners on a regular basis by the JPM.

- Communication and exchange of programme information through governance mechanisms (via STRD PMC/NSC meetings and reports);

- Inclusion in STRD activities, e.g. invitations to special events (grant signing ceremony. certificates for trainings).

- In-person meetings on key topics as required – establishment and maintenance of professional relationships, fostered by the JPM; meeting reports to be shared with the STRD team.

- JPM liaises with the Ministries to obtain the contact person and deputy contact person of each of the implementing partners and shares those details with the team and any other relevant stakeholder.

- Monthly meeting with contact persons from the partner ministries (JPM and POs (with the Pos rotating each month).

- Establishment and maintenance of professional relationships between STRD “expert” staff with specific agencies.

- Communication and advocacy strategy provides an excellent platform for all to implement the above-mentioned points.

- Joint programme already took some actions to overcome communication issues. Efforts have been made on revising of the master plan with national partners, and have shown good results and positive reactions, so this practice will continue.

2. In order to measure the project results and to give recommendations for the further public investments, it is necessary to collect and analyze rural tourism related data in 19 target municipalities. This will enable the evidence based situation and results monitoring and provide up-to-date information to national stakeholders for planning and policy development purposes. Official data from the Serbian Statistical Office need to be disaggregated and updated for 2009 and 2010.  The real picture on the number of rural tourism service providers, the income generated from the tourism and the levels of partnerships will be therefore collected and analysed. That is why the revision and inclusion of the new baseline data is needed.

Actions regarding the negative effects of the financial crisis: Potentials for rural tourism to increase revenue for the public and the private sector and other stakeholders are more highlighted in public discussions and events like International tourism fair in Belgrade and International Danube floating tourism conference.

More than 250 representatives of the national partners, local self-governments, regional and local tourism organisations, NGOs, private rural households, rural tourism associations and LAGs had the opportunity to influence the Master Plan for rural tourism during public discussions regarding the Master Plan.

What types of coordination mechanisms and decisions have been taken to ensure joint delivery?

Are different joint programmes in the country coordinating among themselves? Please reflect on these questions above and add any other relevant comments and examples if you consider it necessary:

In order to ensure smooth communication between the PMC and NSC, the PMC for DPS is attended by the Spanish Embassy representative, UN Coordination Officer and SEIO/DACU Representative.

The PMC has rotational chair between the Ministry of Agriculture/FAO and Ministry of Economy and Regional Development /UNWTO. This mechanism proves to function very well.

The horizontal cooperation between STRD and other programmes is most appreciated by donors, particularly in the context of the contribution that STRD and other programmes make to the EU integration processes in the country.

The last PMC meeting that was held in Kosjeric in April, the representatives from EC/SDC funded project PROGRES attended in order to ensure synergies and complementarities between the STRD and PROGRES. Tourism Master Plan is the key programmatic tool that will be used by other programmes. Linkages between STRD and other EC funded programmes in the domain rural development have been established as well.

The National Steering Committee worked and communicated by e-mail during the reporting period (approving numerous documents/requests submitted to it). The national representative to the NSC changed in late 2010. Ms Milica Delevic, the Serbian EU Integration Office Director, is the new co-chair from Government side. The NSC meeting took place in June 2011. The NSC appreciated the progress and value brought in by the three MDG F JPs and in particular the contribution that the programmes bring to the EU integration processes. National ownership promoted through the JPs is seen to pave the way for the forthcoming decentralized implementation modality to be put in place on the way to the EU integration.

Regular meetings for the MDG F JPM and UN RC and RCO are held regular communication/cooperation maintained.

JPM takes part at UNCT meetings and other related activities.

STRD from Serbia was given visibility at the recent MDG F hosted workshop held in Morocco.

STRD was given also great visibility during the Tourism Fair in Belgrade held in February 2011. The quality of STRD work, presentation of activities was most appreciated by all partners, including the Spanish Embassy.

The key statistical data for rural tourism in Serbia are missing and the Programme is trying to find a solution to the problem. The problem is more severe because the selected 19 municipalities in Serbia cannot be representative of the whole Serbian population. However, the Programme will continue in gathering data jointly.

Coordination between the Agencies in the Programme in gathering data for different policy documents have so far been one of the key successes in the Programme implementation.

Key points in relation to ownership to be mentioned are the following:

National ownership

- All national implementing partners are members of the JP PMC.

- The Government of Serbia – through the Ministry of Economy and Regional Development, the Ministry of Agriculture, Trade, Forestry and Water Management, and the National Tourism Organization of Serbia - is included into all aspects of implementation of the JP.

- Rural Development Council established.

- The JP Manager regularly liaises with the national implementing partners.

Regional and local ownership

- Rural Development Network as well as local Tourism Organizations actively participated in programme implementation through various activities

The JP has articulated a communications and advocacy strategy, outlining 4 most important objectives

- Guide JP Communications internally among partner agencies to support JP implementation.

- Provide guidance and quality assurance for JP external communication in order to ensure consistent and appropriate visibility for JP activities, and to support the creation and maintenance of positive and successful relationships with STRD stakeholders.

- Outline JP communication activities’ framework to support the achievement of programme outputs and outcomes.

- Provide the basis for co-ordinate advocacy action among all JP partners and team members, utilizing advocacy opportunities and resources to help achieve the positive change identified, contributing to advocacy around the achievement of JP goals and MDGs.

The JP Communication and Advocacy Strategy contains a matrix on stakeholder communication, which outlines the stakeholder groups, communication goals, and communication tools and processes to be used; detailed guidelines on visibility of the JPand C&A events and products; and the framework for the implementation of the C&A activities over the course of the JP as well as a template for quarterly C&A work plans. The Communication and Advocacy Analyst works closely with the PIU team and other partners (see Joint Programme Visibility under the ‘Progress section above). Some aspects of enhanced communication include the following:

1. Clear and effective visual identity of the JP,

2. Targeted promotional activities at the local, national and international levels,

- 3. Media presence in the local and national media,

- 4. Partnership building with relevant organizations.

Municipal authorities.

Most important region based events

Comments obtained from participating agencies on their contribution include the following:

At the national level

- The Master Plan for Sustainable Rural Tourism Development  targets achievement of the MDGs: to reduce poverty, achieve gender equality, foster sustainable development and a Global Partnership for Development.

- The creation and implementation of the Master Plan for rural tourism should ensure that rural development contributes to the improvement of living conditions of the rural population, primarily of women and children and to create opportunities for job creation in rural communities.

- Introducing two sets of measures of the Axis 2 and Axis 3 related to nature protected areas and sustainable environmental management connected to the farming sector and tourism and rural tourism development as a component of the rural economy diversification (on-farm and rural community based) into the Serbian IPARD plan.

- Providing input to build capacities on the Governmental level to deal with decision making for rural development on the inter-ministerial level.

- In order to support rural development, contributes to both outcomes that will be achieved only through cooperation between the partners on the national and on the local level and capacity building for local level to be able to channel and lobby for their interest with governing structures and cultivate community interests in rural development through local partnerships.

- The creation of strategy guidelines for securing and leveraging public-private partnerships and provision of strategic investment training for target group of public decision-makers and private investors.

- Partnerships for development and fight against poverty are the cornerstone of the Millennium Development Goals (MDGs).This commitment embedded in MDG 8 calls for partnerships between governments, civil society, private sector and other stakeholders to develop and implement strategies that would improve the quality of living for children, women and men in rural areas.

Comments obtained from participating agencies (continued):

At the local level:

- Contributing through capacity building for local stakeholders, which should provide services to local beneficiaries of rural development support programmes (national and IPARD).

- Provide support through  variety of trainings specified in programme document

- Thought grant schemes to all local stakeholders ready to work in the partnership

- Institutional and governance structure of rural tourism development.

- Market-oriented products.

- Sustainable quality of tourism services.

- Promote and support national and local policies and programmes in favour of enterprise development

2. Provision of technical assistance and capacity development activities

3. Creating or strengthening organizations and partnerships to contribute to enterprise development and competitiveness