**Turkey**

|  |  |
| --- | --- |
| **Programme Title:** | Growth with Decent Work for All |
| **Programme number & MDTF ref:** | MDGF-1928-H-TUR Growth with De (67208) |
| **Window:** | Youth, Employment & Migration |
| **Approved Budget by NSC (US$):** | 3.98 million |
| **Participating Organizations:** | FAO, ILO, IOM, UNDP |
| **First Tranche transferred on:** | 2-Oct-2009 |
| **Second Tranche transferred on:** | 11-Oct-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Background studies and surveys planned for the first year of the JP execution completed as foreseen. Institutional needs assessment of government institutions involved YEM within the JP scope completed. A capacity-building plan agreed upon with İŞKUR and a series of training seminars delivered at central and local level. Assessment of agricultural vocational services requirement completed. A new Vocational Training Module for rural youth initiated. Work started on drafting a National Youth Employment Action Plan (NYEAP) by a National Technical Team (NTT) as a participatory mechanism. A Vocational Training (VET) programme agreed upon with İŞKUR to be implemented in Antalya in 2011-2012 for unemployed youth. Baseline Research on the local monitoring of migration impacts on the labor market and employment started. A new training module on basic life skills started for supporting employability of migrant youth. Strategic and emerging sectors in Antalya determined in Antalya for sector development road maps presenting employment opportunities for youth and women. |
|  |
| **Problems and lessons learned:** |
| Coordination within government. Managerial (qualified staff shortages in area). External to the JP (insufficient dialogue between labor market actors)). Ownership and involvement of the regional/provincial government is sine qua non for the success of the programme; |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS& FIGURES

As of 31 December 2010

